## Roadmap Timeline
SwachERP — Generic ERP Roadmap Timeline | [5 empty] | WEEK-BY-WEEK GANTT (each shaded cell = 1 week of work)
Phase | Feature / Deliverable | Priority | Effort (wks) | Target Industries | Status | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
[6 empty] | M1 |  |  |  | M2 |  |  |  | M3 |  |  |  | M4 |  |  |  | M5 |  |  |  | M6 |  |  |  | M7 |  |  |  | M8 |  |  |  | M9 |  |  |  | M10
Phase 1 Foundation | Leave Management (apply / approve / balance) | Critical | 3 | All industries | Planned
| ESS Portal — leave + payslip self-service | Critical | 2 | All industries | Planned
| Configurable module labels / terminology | High | 3 | Non-manufacturing tenants | Planned
| Custom fields on invoices & items | High | 2 | All industries | Planned
Phase 2 Service Biz | Service billing (time+material / milestone) | Critical | 3 | IT, consulting, agencies | Planned
| Recurring invoices (AMC / SaaS / rent) | High | 2 | SaaS, AMC, rentals | Planned
| Proforma to Invoice workflow | Medium | 1 | Exporters, traders | Planned
| Service invoice with TDS deduction | High | 2 | Consulting, agencies | Planned
| Expense reimbursement claims | Medium | 2 | Any company with field staff | Planned
Phase 3 Inventory+ | Multi-location / multi-warehouse inventory | High | 4 | Retail, distribution, construction | Planned
| Serial number & lot tracking | Medium | 3 | Electronics, pharma, auto parts | Planned
| Unit of measure conversion | Medium | 2 | Pharma, textiles, chemicals | Planned
Phase 4 Project+ | Project cost centre (P&L by project) | High | 5 | Construction, consulting, events | Planned
| Progress billing / milestone billing | High | 3 | Construction, IT projects | Planned
| Timesheet & billable hours | Medium | 3 | IT, consulting, agencies | Planned
| BOQ (Bill of Quantities) | Medium | 2 | Construction | Planned
Phase 5 Advanced | Multi-currency (buy/sell in foreign currency) | Medium | 4 | Exporters, importers | Planned
| Fixed asset management + depreciation | Medium | 3 | Construction, hospitality, mfg | Planned
| Performance appraisal module | Low | 3 | All industries | Planned
| Retention management (subcontractor payments) | Low | 2 | Construction | Planned

## Phase Summary
SwachERP — Phase Summary & Business Case
Phase | Timeline | Features | Total Effort | Key Industries Unlocked | Business Impact | Target
Phase 1 — Foundation | Month 1-4 | 4 | 10 weeks | All industries | Removes manufacturing-only lock-in. Every new vertical becomes sellable. | Q3 2026
Phase 2 — Service Biz | Month 3-6 | 5 | 10 weeks | IT, consulting, AMC, agencies | Unlocks ~40% of Indian GST filers who are pure service companies. | Q3 2026
Phase 3 — Inventory+ | Month 4-6 | 3 | 9 weeks | Retail, distribution, pharma, auto parts | Multi-branch clients: potential 2x revenue per account. | Q4 2026
Phase 4 — Projects | Month 6-9 | 4 | 13 weeks | Construction, IT projects, events, consulting | Construction alone: Rs 12 lakh crore sector. Opens premium project tier. | Q1 2027
Phase 5 — Advanced | Month 8-10 | 4 | 12 weeks | Exporters, large enterprises, all industries | Enterprise ACV uplift. Multi-currency + assets = large company readiness. | Q1 2027
TOTAL ROADMAP |  | 20 | ~54 weeks

## Gap Analysis
SwachERP — Detailed Gap Analysis: Manufacturing vs Generic
Category | Gap | Current State | What Is Needed | Priority | Effort | Phase
Terminology | Hardcoded Production Orders | Fixed label shown to all tenants | Configurable per tenant: Work Order, Job, Project | Critical | 2 wks | Phase 1
Terminology | Hardcoded BOM | Bill of Materials only | Recipe / Service Package / Scope of Work | High | 1 wk | Phase 1
Terminology | Gatepass shown to everyone | Delivery challan term baked into navigation | Hide or relabel for non-manufacturing tenants | High | 1 wk | Phase 1
Terminology | Machine Startup Checklist visible | WhatsApp machine checklist in nav always | Show only if tenant has machines / production lines | Medium | 1 wk | Phase 1
HR | No leave management | Attendance only. No apply/approve/balance | Leave types, application, approval, running balance | Critical | 3 wks | Phase 1
HR | No expense claims | Not present | Employee submits claim, manager approves, finance pays | Medium | 2 wks | Phase 2
HR | No timesheet / billable hours | Shift attendance only | Daily timesheet linked to project or client | Medium | 3 wks | Phase 4
HR | No performance appraisal | Not present | Appraisal cycles, KRA, ratings, increment link | Low | 3 wks | Phase 5
Billing | No service billing | Product invoices (HSN) only | Service lines: time+material, milestone, retainer | Critical | 3 wks | Phase 2
Billing | No recurring invoices | Manual invoice creation only | Auto-generate monthly/quarterly invoices on schedule | High | 2 wks | Phase 2
Billing | No proforma invoice | Tax Invoice only — no pre-invoice stage | Proforma -> convert to Tax Invoice flow | Medium | 1 wk | Phase 2
Billing | TDS not on service purchase bills | TDS tracking exists, not on bill creation | Auto-calculate TDS on applicable service vendor bills | High | 2 wks | Phase 2
Billing | No progress/milestone billing | Full invoice only | Running Account bill, partial billing on milestones | High | 3 wks | Phase 4
Inventory | Single warehouse only | Company-level stock, no site/branch | Site/branch/godown-wise stock with stock transfers | High | 4 wks | Phase 3
Inventory | No serial / lot tracking | Batch FIFO only | Per-unit serial tracking and lot traceability | Medium | 3 wks | Phase 3
Inventory | No UOM conversion | Single unit per item | Buy in kg, sell in grams — convert at transaction | Medium | 2 wks | Phase 3
Projects | No project cost centre | No project entity in system | Project master, link POs, invoices, costs to project | High | 5 wks | Phase 4
Projects | No BOQ tracking | Not present | BOQ vs actual material and labour by project | Medium | 2 wks | Phase 4
Finance | No multi-currency | INR only throughout | Forex invoices, bank accounts, gain/loss accounting | Medium | 4 wks | Phase 5
Finance | No fixed asset register | Not present | Asset master, depreciation schedule, disposal | Medium | 3 wks | Phase 5
Finance | No retention management | Not present | Hold % of subcontractor payment until project done | Low | 2 wks | Phase 5
Configuration | No custom fields | Fixed schema on all forms | User-defined fields on invoices, items, employees | High | 2 wks | Phase 1
Configuration | No doc numbering config | System-generated fixed format | Tenant configures prefix, year, series (PROJ-24-001) | Medium | 1 wk | Phase 1