## Phase Status Map
SwachERP — 19 Phases: Already Built vs Still To Build
Existing codebase audit · Only NEW Gold ERP phases need development · Major cost saving
| ALREADY BUILT |  | STILL TO BUILD |  | REVISED BUDGET
| 10 Phases |  | 9 Phases |  | ₹6.5–7.5L
| ~73% of platform work done |  | All Gold ERP specific modules |  | Save ₹2.5–3.5L vs full build
| Ph# | Phase Name | Category | Status | Days Saved | Notes
| 1 | Core ERP Platform & Multi-tenancy | Platform | ✔ BUILT | 2 days | AsyncLocalStorage + tenant isolation complete
| 2 | Authentication, RBAC & Permissions | Platform | ✔ BUILT | 2 days | scrypt login, roles, role_permissions done
| 3 | GST Invoicing & Double-Entry Accounting | Finance | ✔ BUILT | 3 days | Full journal engine + GST invoice with IRN
| 4 | Purchase Orders, GRN & 3-Way Match | Procurement | ✔ BUILT | 3 days | PR → PO → GRN → invoice matching complete
| 5 | Inventory, Warehouses & Stock Transfer | Inventory | ✔ BUILT | 3 days | Multi-warehouse, UOM, serial/lot done
| 6 | HR, Payroll & Attendance | HR | ✔ BUILT | 3 days | Employees, payroll, leaves, expense claims
| 7 | CRM & Customer Portal | CRM | ✔ BUILT | 2 days | Leads, follow-ups, customer master done
| 8 | WhatsApp 2-Way Integration | Integrations | ✔ BUILT | 3 days | Meta Cloud API + Colloki Flow wired up
| 9 | Module Marketplace & SaaS Billing | Platform | ✔ BUILT | 3 days | 27-module catalog, Razorpay billing live
| 10 | GSTR Reports, Audit Trail & Approvals | Finance | ✔ BUILT | 2 days | GSTR-1/3B, audit_logs, approval engine done
| 11 | Metal Rate Engine (IBJA / MCX live) | Gold ERP | ⚒ TO BUILD | — | New: live rate API + history + WhatsApp alert
| 12 | Jewellery Item Master & Price Engine | Gold ERP | ⚒ TO BUILD | — | New: making%, wastage%, purity config
| 13 | Karigar Management & Job Orders | Gold ERP | ⚒ TO BUILD | — | New: karigar master, advances, weight ledger
| 14 | Retail Billing with Making Charges | Gold ERP | ⚒ TO BUILD | — | New: jewellery GST bill + old gold exchange
| 15 | Bullion Trading & Scrap Buy/Sell | Gold ERP | ⚒ TO BUILD | — | New: bar/coin/scrap transactions
| 16 | Gold Savings Chit Schemes | Gold ERP | ⚒ TO BUILD | — | New: enrolment, instalment, redemption
| 17 | Repair Orders & Design Catalogue | Gold ERP | ⚒ TO BUILD | — | New: repair tracking + design image upload
| 18 | Hallmarking, BIS & HUID Generation | Gold ERP | ⚒ TO BUILD | — | New: HUID + assay centre integration
| 19 | Gold Analytics, Licensing & AMC | Gold ERP | ⚒ TO BUILD | — | New: MIS dashboard + license keys + AMC
WHAT THIS MEANS FOR YOUR PROJECT
10 out of 19 phases are ALREADY BUILT in SwachERP. You only need to build the 9 Gold ERP phases.
This saves ~22 dev-days. Revised quote: ₹6.5–7.5 Lakhs ¦ Timeline: 18–22 days instead of 30.

## Resource & Cost
Resource Plan & Cost Breakdown — 20-Day Gold ERP Sprint
Fixed-price model · All costs in INR (₹) · No hidden charges · 5-member team
TEAM — WHO BUILDS WHAT
| # | Role | Primary Responsibility | Seniority | Monthly Rate | 20-Day Cost | Phases Owned
| 1 | Tech Lead / Architect | Architecture, code review, DB schema, QA oversight | Senior | 175000 | 116667 | All phases — oversight
| 2 | Full Stack Dev A | Gold ERP: Karigar, Billing, Chit, Hallmarking | Senior | 120000 | 80000 | Ph 12,13,14,16,18
| 3 | Full Stack Dev B | Gold ERP: Metal rates, Bullion, Repair, Analytics | Mid | 90000 | 60000 | Ph 11,15,17,19
| 4 | Frontend / UI Dev | All Gold ERP screens, responsive design, print layouts | Mid | 80000 | 53333 | UI for all phases
| 5 | QA Engineer | Test plans, regression, UAT support, bug triage | Junior | 60000 | 40000 | Testing all phases
TOTAL TEAM COST (20 days) | [5 empty] | ₹3,50,000 | ~35% of ₹10L budget
PHASE-WISE EFFORT & COST ALLOCATION
| Ph# | Gold ERP Phase | Dev Owner | Days | Dev Cost | Infra Share | Phase Total
| 11 | Metal Rate Engine | Dev B + TL | 2 days | 16000 | 1000 | 17000
| 12 | Jewellery Item Master | Dev A | 2 days | 16000 | 500 | 16500
| 13 | Karigar Management | Dev A | 3 days | 24000 | 800 | 24800
| 14 | Retail Billing | Dev A | 3 days | 24000 | 800 | 24800
| 15 | Bullion Trading & Scrap | Dev B | 2 days | 12000 | 500 | 12500
| 16 | Gold Savings Chit Schemes | Dev A | 2 days | 16000 | 500 | 16500
| 17 | Repair & Design Catalogue | Dev B | 2 days | 12000 | 500 | 12500
| 18 | Hallmarking & BIS | Dev A | 2 days | 16000 | 500 | 16500
| 19 | Analytics, Licensing, AMC | Dev A+B+TL | 3 days | 24000 | 800 | 24800
| Q | QA, UAT & Go-Live Deploy | QA + All | 3 days | 26000 | 1500 | 27500
TOTAL DEVELOPMENT EFFORT |  |  |  |  | ₹1,86,000 | ₹7,400 | ₹1,93,400
INFRASTRUCTURE & TOOLS (20 DAYS)
| # | Item | Vendor / Provider | Unit | Unit Cost | Units | Total
| 1 | Neon PostgreSQL Pro | Neon.tech | month | 3500 | 1 | 3500
| 2 | Replit Hacker (Dev env) | Replit | month | 2000 | 1 | 2000
| 3 | WhatsApp Business API | Meta Cloud API | month | 2000 | 1 | 2000
| 4 | Colloki Flow API | Colloki | month | 1500 | 1 | 1500
| 5 | MCX / IBJA Rate Feed | Commodity Data API | month | 2000 | 1 | 2000
| 6 | SendGrid Email | Twilio SendGrid | month | 500 | 1 | 500
| 7 | Razorpay Payment GW | Razorpay | setup | 500 | 1 | 500
| 8 | Domain + SSL Certificate | GoDaddy / Cloudflare | year | 1000 | 1 | 1000
| 9 | SMS Gateway (OTP/alerts) | Fast2SMS | month | 500 | 1 | 500
| 10 | Misc / Buffer | — | lumpsum | 1000 | 1 | 1000
TOTAL INFRASTRUCTURE COST | [6 empty] | ₹14,500
COMPLETE BUDGET SUMMARY
Team Cost — 5 members × 20 days | [6 empty] | 350000
Phase-wise Dev Allocation | [6 empty] | 186000
Infrastructure & Tools | [6 empty] | 14500
QA, UAT & Go-Live | [6 empty] | 26000
Contingency / Buffer (6%) | [6 empty] | 34590
TOTAL INTERNAL COST | [6 empty] | 611090
━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━
CLIENT QUOTE — Option A (Lean) | [6 empty] | 650000
CLIENT QUOTE — Option B (Recommended) | [6 empty] | 750000
CLIENT QUOTE — Option C (Full + AMC) | [6 empty] | 850000
━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━
Gross Margin — Option A | [6 empty] | 38910
Gross Margin — Option B (Recommended) | [6 empty] | 138910
Gross Margin — Option C | [6 empty] | 238910
Option B @ ₹7.5L is recommended — 23% gross margin with full branding, training, 60-day support and AMC setup included.
DAILY RATE CARD — For Reference
| # | Role | Monthly CTC | Daily Rate | Hourly Rate | Days Avail. | Days on Gold ERP
| 1 | Tech Lead / Architect | 175000 | 5833 | 729 | 20 | 20
| 2 | Full Stack Dev A | 120000 | 4000 | 500 | 20 | 19
| 3 | Full Stack Dev B | 90000 | 3000 | 375 | 20 | 18
| 4 | Frontend / UI Dev | 80000 | 2667 | 333 | 20 | 20
| 5 | QA Engineer | 60000 | 2000 | 250 | 20 | 15

## Revised Build Plan
Revised Build Plan — 9 New Gold ERP Phases Only
Platform already built · Only Gold ERP modules to develop · 18–22 days · ₹6.5–7.5 Lakhs
| NEW PHASES |  | TIMELINE |  | CLIENT COST
| 9 |  | 18–22 Days |  | ₹6.5–7.5L
| All Gold ERP specific |  | vs 30 days original plan |  | Fixed price, all inclusive
| Ph# | Gold ERP Phase — What We Build | Track | Days | Budget | Key Deliverables
| 11 | Metal Rate Engine | Dev B+TL | 2 days | 80000 | IBJA/MCX live API, rate history, purity-wise rates, dashboard widget, WhatsApp rate alert
| 12 | Jewellery Item Master | Dev A | 2 days | 80000 | jw_items, jw_purity tables; making charge config; stone/wastage config; item search
| 13 | Karigar Management | Dev A | 3 days | 100000 | Karigar master; job orders; advance ledger; weight issue/receive; wage calc; statement
| 14 | Retail Billing | Dev A | 3 days | 100000 | Gold GST invoice; making + stone + wastage; old gold exchange; melt calc; thermal print
| 15 | Bullion Trading & Scrap | Dev B | 2 days | 70000 | Bar/coin buy-sell; scrap purchase; refinery tracking; bullion P&L; stock in grams
| 16 | Chit / Gold Scheme | Dev A | 2 days | 70000 | Scheme master; member enrolment; monthly instalment; maturity; redemption options
| 17 | Repair & Design Catalogue | Dev B | 2 days | 70000 | Repair job card; before/after photos; status tracking; design image upload + tags
| 18 | Hallmarking & BIS | Dev A | 2 days | 70000 | HUID generation; BIS lot; purity certificate; hallmarked flag on billing
| 19 | Analytics, Licensing & AMC | Dev A+B+TL | 3 days | 100000 | Gold MIS dashboard; karigar P&L; branch sales; license keys; AMC schedule; go-live
|  | TOTAL — 9 NEW GOLD ERP PHASES |  | 19 days | 740000

## 20-Day Gantt
SwachERP Gold ERP — 20-Day Sprint Gantt (9 New Phases Only)
Dev A: Gold ERP Core · Dev B: Supporting · Tech Lead: Architecture + QA
# | Phase / Task | Dev | Days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
|  |  |  | W1 | [6 empty] | W2 | [6 empty] | W3
11 | Metal Rate Engine + WhatsApp alert | Dev B+TL | 1
12 | Jewellery Item Master & Price Config | Dev A | 2
13 | Karigar Module + Job Orders | Dev A | 3
14 | Retail Billing + Old Gold Exchange | Dev A | 3
15 | Bullion Trading & Scrap | Dev B | 2
16 | Gold Savings Chit Schemes | Dev A | 2
17 | Repair Orders + Design Catalogue | Dev B | 2
18 | Hallmarking & BIS / HUID | Dev A | 2
19 | Gold Analytics Dashboard | Dev A | 2
L | License Keys + AMC Module | Dev B | 2
Q | Integration Testing & Bug Fixes | QA | 3
U | UAT, Training & Go-Live Deploy | All | 2

## Quote Options
Quote Options for Client — SwachERP Gold ERP
3 options · Platform already built · Pay only for what is new
|  | OPTION A Gold ERP — Lean | OPTION B Gold ERP + Branding ★ RECOMMENDED | OPTION C Full 19-Phase Rebuild
| Scope | 9 new phases only | 9 phases + custom UI + training + 60-day support | All 19 phases new codebase from scratch
| Timeline | 18–20 Days | 22–24 Days | 30 Days
| Price | ₹6,50,000 | ₹7,50,000 | ₹10,00,000
| Gold ERP | ✓ Core Gold ERP (9 modules) | ✓ Core Gold ERP (9 modules) | ✓ Full 19-phase rebuild
| Platform | ✓ Yes — already live | ✓ Yes — already live | ✓ Built from scratch
| WhatsApp | ✓ Basic WhatsApp alerts | ✓ WhatsApp + SMS alerts | ✓ Full integration
| Reports | ✓ Standard MIS reports | ✓ Advanced analytics | ✓ Full analytics suite
| Support | ✓ 30-day bug fixes | ✓ 60-day support + training | ✓ 90-day support + training
| AMC | ✓ ₹60K/year | ✓ ₹60K/year | ✓ ₹1L/year
Option B @ ₹7.5L is recommended — delivers full Gold ERP value with branding, training, extended support and AMC setup.