## Overview
Kinto Smart Ops — HR Module
Full Implementation Plan
Total Phases | 6
Total Timeline | 3 Months (13 Weeks)
Total Modules | 11
Phase | Modules | Timeline | Status
Phase 1 | Masters & Employee Master | Week 1–2 | Pending
Phase 2 | Attendance & Leaves | Week 3–4 | Pending
Phase 3 | Payroll & Payslip | Week 5–7 | Pending
Phase 4 | TDS & Compliance Reports | Week 8–9 | Pending
Phase 5 | Loans, Advances & F&F Settlement | Week 10–11 | Pending
Phase 6 | Recruitment & Employee Self-Service | Week 12–13 | Pending

## Phase 1 – Masters
Phase 1 — Masters & Employee Master
Timeline: Week 1–2
Module | Feature | Details | Priority
Department Master | Create departments | Production, Quality, Accounts, Store, HR, etc. | Must Have
Department Master | Edit / deactivate departments | Soft delete with record_status | Must Have
Designation Master | Create designations | Operator, Supervisor, Manager, GM, etc. | Must Have
Designation Master | Grade/Level tagging | Link designation to pay grade | Must Have
Shift Master | Create shifts | Day, Night, General, Rotating | Must Have
Shift Master | Weekly off configuration | Sunday only / Sat-Sun / Alternate Sat | Must Have
Shift Master | Shift timings | Start time, End time, Break duration | Must Have
Leave Type Master | Create leave types | CL, SL, EL, LOP, Maternity, Paternity | Must Have
Leave Type Master | Annual entitlement | Days per year per leave type | Must Have
Leave Type Master | Carry forward rules | EL carry forward with max cap | Must Have
Leave Type Master | Encashable flag | Mark EL as encashable for F&F | Must Have
Holiday Master | Annual holiday list | Tenant-specific, year-wise | Must Have
Holiday Master | Holiday types | National / Festival / Optional / Weekly Off | Must Have
Holiday Master | Paid / Unpaid flag | Mark if holiday is paid or unpaid | Must Have
Holiday Master | Copy previous year | Copy last year's list and update dates | Good to Have
Holiday Master | State-specific holidays | Tamil Nadu, Maharashtra, etc. | Good to Have
Salary Component Master | Create earnings | Basic, HRA, DA, Special Allowance, Conveyance, OT, Bonus | Must Have
Salary Component Master | Create deductions | PF, ESI, PT, TDS, Advance Recovery, Loan EMI | Must Have
Salary Component Master | Formula type | Fixed amount or % of Basic | Must Have
Salary Component Master | Statutory flag | Mark as statutory (PF, ESI, PT, TDS) | Must Have
Salary Component Master | Show on payslip toggle | Admin controls what appears on printed payslip | Must Have
Salary Structure | Create salary structure | Assign components to a grade/structure | Must Have
Salary Structure | Assign to employee | Each employee mapped to one structure | Must Have
Professional Tax Master | State-wise PT slabs | Income range → PT amount | Must Have
Payslip Template Settings | Company branding | Logo, address, colour, signatory name | Must Have
Payslip Template Settings | Show/hide fields | PAN, PF No, ESI No, Bank details, Leave balance | Must Have
Employee Master | Personal details | Name, photo, gender, DOB, blood group | Must Have
Employee Master | Employment details | Employee code, department, designation, join date | Must Have
Employee Master | Statutory details | PAN, Aadhaar, PF number, ESI number, UAN | Must Have
Employee Master | Bank details | Account number, IFSC, bank name | Must Have
Employee Master | Document storage | Offer letter, ID proof, certificates | Must Have
Employee Master | Tax regime selection | Old regime or New regime per employee per FY | Must Have
Employee Master | Reporting manager | Who approves this employee's leaves | Must Have
Employee Master | Shift assignment | Assign shift to employee | Must Have

## Phase 2 – Attendance
Phase 2 — Attendance & Leaves
Timeline: Week 3–4
Module | Feature | Details | Priority
Attendance | Daily attendance marking | Present / Absent / Half Day / LOP / Holiday / Weekly Off | Must Have
Attendance | Bulk attendance entry | Mark attendance for all employees at once | Must Have
Attendance | Auto-mark holidays | Holidays from Holiday Master auto-applied | Must Have
Attendance | Overtime hours entry | Manual OT hours entry per day per employee | Must Have
Attendance | Monthly attendance summary | Days present, absent, LOP, OT hours per employee | Must Have
Attendance | Edit attendance with reason | Corrections allowed before payroll lock | Must Have
Leave Management | Leave application | Employee applies for leave with date range and reason | Must Have
Leave Management | Manager approval workflow | Approve / Reject with comment | Must Have
Leave Management | WhatsApp notification | Notify employee on approval/rejection | Must Have
Leave Management | Leave balance tracking | Real-time balance per leave type per employee | Must Have
Leave Management | Auto LOP on excess absence | If CL/SL exhausted, excess marked as LOP | Must Have
Leave Management | Leave calendar view | Visual calendar showing who is on leave | Good to Have
Leave Management | Carry forward at year end | EL balance carry forward with cap | Must Have
Leave Management | Leave encashment request | Employee requests EL encashment | Good to Have

## Phase 3 – Payroll
Phase 3 — Payroll & Payslip
Timeline: Week 5–7
Module | Feature | Details | Priority
Payroll Processing | Monthly payroll run | Single click to generate payroll for all employees | Must Have
Payroll Processing | Pro-rata salary | Gross = (Monthly CTC ÷ Working days) × Days worked | Must Have
Payroll Processing | LOP deduction | Auto-deducted for excess absences | Must Have
Payroll Processing | OT pay calculation | OT hours × (Basic ÷ 26 ÷ 8) × multiplier | Must Have
Payroll Processing | Shift allowance | Auto-added based on shift worked | Must Have
Payroll Processing | PF calculation | 12% employee + 12% employer, capped at ₹1,800 if Basic > ₹15,000 | Must Have
Payroll Processing | ESI calculation | 0.75% employee + 3.25% employer (only if gross ≤ ₹21,000) | Must Have
Payroll Processing | Professional Tax | Auto-picked from state PT slab table | Must Have
Payroll Processing | TDS deduction | Monthly TDS based on annual projection | Must Have
Payroll Processing | Loan/advance recovery | Auto-deducted EMI each month till cleared | Must Have
Payroll Processing | Net pay calculation | Gross Earnings − Total Deductions = Net Pay | Must Have
Payroll Processing | Net pay in words | Auto-generated (e.g. Rupees Twenty Two Thousand Only) | Must Have
Payroll Processing | Review before finalise | Admin reviews all payroll before locking | Must Have
Payroll Processing | Lock payroll | Locked payroll cannot be edited | Must Have
Payroll Processing | Unlock with reason | Super admin can unlock with audit log | Good to Have
Payslip | Configurable components | Show/hide any earning or deduction per company setting | Must Have
Payslip | Company branding | Logo, address, colours, signatory | Must Have
Payslip | Employee details on payslip | Emp code, department, designation, bank, PAN, PF, ESI | Must Have
Payslip | Attendance summary | Days worked, LOP, leave balance on payslip | Must Have
Payslip | PDF download | One payslip or bulk all employees | Must Have
Payslip | WhatsApp delivery | Send payslip PDF to employee via WhatsApp | Must Have
Payslip | Email delivery | Send payslip PDF to employee via email | Must Have
Salary Register | Monthly salary register | All employees, all components in one report | Must Have
Bank Transfer File | NEFT/RTGS format | Export salary disbursement file for bank upload | Must Have

## Phase 4 – TDS & Compliance
Phase 4 — TDS & Compliance Reports
Timeline: Week 8–9
Module | Feature | Details | Priority
TDS & Tax | Tax regime selection | Old regime or New regime per employee per FY | Must Have
TDS & Tax | Annual tax declaration | Employee declares HRA, 80C, 80D, 80CCD, home loan, LTA | Must Have
TDS & Tax | New regime — standard deduction | ₹75,000 standard deduction only, no other exemptions | Must Have
TDS & Tax | Monthly TDS auto-calculation | Projected annual tax ÷ remaining months | Must Have
TDS & Tax | Mid-year declaration update | Employee can update declaration mid-year | Must Have
TDS & Tax | Year-end reconciliation | Actual proofs vs declared, difference in March salary | Must Have
TDS & Tax | Tax slab tables | Old regime and New regime slabs (FY 2024-25) | Must Have
TDS & Tax | Section 87A rebate | Zero tax if taxable income ≤ ₹7L (new) or ₹5L (old) | Must Have
TDS & Tax | Form 16 Part A | TDS deducted and deposited (from TRACES) | Must Have
TDS & Tax | Form 16 Part B | Salary breakup and deduction details | Must Have
Compliance Reports | PF ECR file | Monthly electronic challan-cum-return for EPFO upload | Must Have
Compliance Reports | ESI contribution report | Monthly ESI contribution for ESIC portal | Must Have
Compliance Reports | Form 24Q data | Quarterly TDS return data export | Must Have
Compliance Reports | PT challan data | State-wise professional tax challan | Must Have
Compliance Reports | Employer PF contribution report | 12% employer share tracking | Must Have
Accounting Integration | Salary journal entry | Auto-posted to accounts on payroll approval | Must Have
Accounting Integration | PF payable account | Employer + employee PF as liability | Must Have
Accounting Integration | ESI payable account | Employer + employee ESI as liability | Must Have
Accounting Integration | TDS payable account | TDS deducted as liability till deposited | Must Have
Accounting Integration | Gratuity provision | Monthly gratuity provision journal entry | Good to Have

## Phase 5 – Loans & F&F
Phase 5 — Loans, Advances & Full & Final Settlement
Timeline: Week 10–11
Module | Feature | Details | Priority
Salary Advance | Advance request | Employee requests advance with amount and reason | Must Have
Salary Advance | Manager approval | Approve or reject with comment | Must Have
Salary Advance | Auto-recovery | Full amount deducted from next salary | Must Have
Loans | Loan request and approval | Amount, number of EMIs, start month | Must Have
Loans | EMI auto-deduction | Monthly EMI deducted from salary automatically | Must Have
Loans | Outstanding balance tracking | Real-time outstanding balance per employee | Must Have
Loans | Auto-stop on clearance | Deduction stops automatically when loan is fully paid | Must Have
Loans | Foreclosure | One-time full recovery option | Good to Have
F&F Settlement | Exit types | Resignation / Termination / Retirement | Must Have
F&F Settlement | Last working day | Set last working day for calculations | Must Have
F&F Settlement | Pending salary | Days worked in last month × daily rate | Must Have
F&F Settlement | Leave encashment | EL balance × daily basic rate | Must Have
F&F Settlement | Gratuity | 15 days × years of service (applicable after 5 years) | Must Have
F&F Settlement | Notice period shortfall | Deduct salary for notice period not served | Must Have
F&F Settlement | Loan / advance recovery | Deduct outstanding loans/advances from F&F | Must Have
F&F Settlement | TDS on F&F | Tax on gratuity beyond exemption limit | Must Have
F&F Settlement | Net F&F amount | Final payable amount after all deductions | Must Have
F&F Settlement | F&F payslip | Printable full & final settlement statement | Must Have
F&F Settlement | Experience letter | Auto-generated from template | Must Have
F&F Settlement | Relieving letter | Auto-generated from template | Must Have

## Phase 6 – Recruitment
Phase 6 — Recruitment & Employee Self-Service
Timeline: Week 12–13
Module | Feature | Details | Priority
Recruitment | Job openings | Create openings with department, designation, vacancies | Must Have
Recruitment | Applicant tracking | Applied → Shortlisted → Interviewed → Offered → Joined | Must Have
Recruitment | Interview scheduling | Date, time, interviewer assignment | Good to Have
Recruitment | Offer letter generation | Auto-generated from template with CTC details | Must Have
Recruitment | Convert to employee | One-click: joined candidate becomes employee record | Must Have
Recruitment | Rejection reason | Track why candidates were rejected | Good to Have
Employee Self-Service | View payslips | Employee views and downloads own payslips | Must Have
Employee Self-Service | View leave balance | Real-time CL, SL, EL balance | Must Have
Employee Self-Service | View attendance | Monthly attendance calendar view | Must Have
Employee Self-Service | Apply for leave | Employee applies directly from app | Must Have
Employee Self-Service | WhatsApp leave apply | Apply for leave via WhatsApp message | Must Have
Employee Self-Service | View loan outstanding | See remaining loan balance | Must Have
Employee Self-Service | Tax declaration submission | Employee submits 80C, HRA, etc. online | Must Have
Employee Self-Service | Download Form 16 | Employee downloads own Form 16 | Must Have
Employee Self-Service | View F&F statement | Exited employees can view F&F details | Good to Have

## Database Tables
HR Module — Database Tables
Table Name | Purpose | Key Columns | Phase
hr_departments | Department master | id, tenant_id, name, record_status | 1
hr_designations | Designation master | id, tenant_id, name, department_id, grade, record_status | 1
hr_shifts | Shift master | id, tenant_id, name, start_time, end_time, weekly_off, record_status | 1
hr_leave_types | Leave type master | id, tenant_id, name, annual_days, carry_forward, encashable, record_status | 1
hr_holidays | Holiday master | id, tenant_id, year, date, name, type, is_paid | 1
hr_salary_components | Earnings & deductions | id, tenant_id, name, type (earning/deduction), formula_type, is_statutory, show_on_payslip | 1
hr_salary_structures | Salary structure template | id, tenant_id, name, components (jsonb) | 1
hr_pt_slabs | Professional Tax slabs | id, tenant_id, state, income_from, income_to, pt_amount | 1
hr_employees | Employee master | id, tenant_id, emp_code, name, department_id, designation_id, shift_id, structure_id, join_date, pan, aadhaar, pf_no, esi_no, uan, bank_account, ifsc, tax_regime | 1
hr_employee_documents | Employee documents | id, tenant_id, employee_id, document_type, file_path, expiry_date | 1
hr_attendance | Daily attendance | id, tenant_id, employee_id, date, status, ot_hours, shift_id | 2
hr_leave_balances | Leave balance per employee | id, tenant_id, employee_id, leave_type_id, year, entitled, used, balance | 2
hr_leave_applications | Leave requests | id, tenant_id, employee_id, leave_type_id, from_date, to_date, days, reason, status, approved_by | 2
hr_payroll_runs | Monthly payroll batch | id, tenant_id, month, year, status (draft/approved/locked), processed_at | 3
hr_payslips | Individual payslips | id, tenant_id, employee_id, payroll_run_id, gross, deductions, net_pay, components (jsonb), status | 3
hr_tax_declarations | Employee tax declarations | id, tenant_id, employee_id, fy, regime, hra, sec_80c, sec_80d, home_loan, nps, lta, other | 4
hr_loans | Employee loans & advances | id, tenant_id, employee_id, type, amount, emi_amount, start_month, outstanding, status | 5
hr_loan_recoveries | Monthly loan deductions | id, tenant_id, loan_id, payslip_id, amount, recovered_on | 5
hr_fnf_settlements | Full & Final settlement | id, tenant_id, employee_id, exit_type, last_working_day, pending_salary, leave_encashment, gratuity, deductions, net_amount, status | 5
hr_job_openings | Recruitment — job openings | id, tenant_id, title, department_id, designation_id, vacancies, status | 6
hr_applicants | Recruitment — candidates | id, tenant_id, job_opening_id, name, phone, email, stage, offer_sent, joined | 6

## Priority Matrix
HR Module — Feature Priority Matrix
Feature | Priority | Reason | Phase
Employee Master | Must Have | Foundation of entire HR module | 1
Department & Designation | Must Have | Required for employee structure | 1
Holiday Master | Must Have | Affects attendance and payroll | 1
Salary Components | Must Have | Core payroll setup | 1
Daily Attendance | Must Have | Drives payroll calculations | 2
Leave Management | Must Have | Mandatory for any HR system | 2
Payroll Processing | Must Have | Primary HR function | 3
Payslip Generation (PDF) | Must Have | Legal requirement in India | 3
WhatsApp Payslip Delivery | Must Have | Key differentiator vs Zoho | 3
PF & ESI Auto-calculation | Must Have | Statutory compliance | 3
TDS – Old & New Regime | Must Have | Mandatory for salaried employees | 4
Form 16 | Must Have | Annual legal requirement | 4
PF ECR File | Must Have | EPFO compliance | 4
Bank Transfer File | Must Have | Salary disbursement | 3
Salary Advance | Must Have | Very common in factories | 5
Loans with EMI Recovery | Must Have | Very common in factories | 5
Full & Final Settlement | Must Have | Every company needs this | 5
Experience & Relieving Letter | Must Have | Standard HR process | 5
Gratuity Calculation | Must Have | Statutory after 5 years | 5
OT Pay Calculation | Must Have | Very common in manufacturing | 3
Leave Calendar View | Good to Have | Useful but not critical | 2
Recruitment Tracking | Good to Have | Nice addition | 6
Employee Self-Service App | Good to Have | Good for large workforce | 6
WhatsApp Leave Application | Good to Have | Differentiator feature | 6
Appraisal / Performance | Future Phase | Can be added later | —
Payroll Unlock with Audit Log | Good to Have | Admin safety net | 3
State-specific Holiday Calendar | Good to Have | Useful for multi-state ops | 1