## Executive Summary
SwachERP × Gold ERP — 15-Day Sprint Cost Estimator
Target: ₹7–9 Lakhs · Timeline: 15 Working Days · 57% of Gold ERP already built in SwachERP
WHY ₹7–9 LAKHS IS ACHIEVABLE IN 15 DAYS
57% Already Built | 77 of 137 Gold ERP features exist in SwachERP. No rebuild needed — just configure and connect.
Only 60 Features New | Scope Phase 1 to the 45 most critical new features. Defer advanced production stages to Phase 2.
2 Senior Devs × 15 Days | Two focused senior full-stack devs working in parallel — most efficient use of 15 days.
Replit = Zero DevOps | No server setup, no Docker, no infra management. Deploy in minutes. Saves 10+ days.
Phase 2 for Advanced | Advanced features (all 15 production stages, bullion trading, chit schemes) billed separately.
TOTAL DAYS | TEAM SIZE | FEATURES (Ph 1) | DEV COST | DOMAIN+INFRA | PROFIT MARGIN | CLIENT QUOTE
15 Days | 4 People | 45 New + 77 Reused | ₹2,70,000 | ₹1,30,000 | ~60% | ₹8,00,000
COST BREAKDOWN | Internal Cost (₹) | % of Cost | Client Billed (₹) | Margin (₹) | Notes
Development (2 Sr Devs × 15 days) | 150000 | 40.28% | 300000 | 150000 | ₹5,000/day × 2 devs × 15 days
Development (1 Jr Dev × 15 days) | 37500 | 10.07% | 75000 | 37500 | ₹2,500/day × 15 days
Domain Expert (10 days) | 40000 | 10.74% | 80000 | 40000 | Jewellery ERP domain consultant
QA Engineer (5 days) | 10000 | 2.686% | 25000 | 15000 | ₹2,000/day × 5 days
Project Management | 18000 | 4.834% | 30000 | 12000 | Part-time PM × 5 days
Replit Deploy + Build Env | 15000 | 4.028% | 25000 | 10000 | 2 months Replit Core + Deploy
Gold Rate API (3 months) | 6000 | 1.611% | 12000 | 6000 | MCX/IBJA live rate feed
WhatsApp Business API | 9000 | 2.417% | 18000 | 9000 | 3 months × ₹3,000
Domain + SSL + Branding | 3000 | 0.8057% | 8000 | 5000 | Domain name + SSL cert
Customization (JW-specific UI) | 50000 | 13.43% | 90000 | 40000 | Estimate PDF, barcode labels, etc.
Buffer / Contingency (10%) | 33850 | 9.091% | 37000 | 3150 | 10% of internal cost
TOTAL | 372350 | 100% | 800000 | 427650 | Gross Margin: 53%

## 15-Day Sprint Plan
15-Day Sprint Plan — Gold ERP Phase 1 (Core)
Dev A = Senior Full-Stack (Backend-heavy) ¦ Dev B = Senior Full-Stack (Frontend-heavy) ¦ Domain Expert on-call Days 1–5 & 13–15
Day | Dev A Task | Dev B Task | Module Delivered | Features Done | Hours | Status
Day 1 | DB schema: jw_items, jw_karigar, jw_metal_rates, jw_estimates | Sidebar nav setup (4 JW modules), business profile switcher | Foundation | DB + Nav ready | 8 | Pending
Day 2 | Metal Rates API integration (MCX/IBJA), rate history table | JW Dashboard: KPI cards, live rate widget, business profile display | Dashboard + Metal Rates | Live gold rate widget | 8 | Pending
Day 3 | Items Master CRUD: HUID, barcode, categories, stone details | Items UI: list, add/edit form, barcode display, category filter | Jewellery Items | Items Master complete | 8 | Pending
Day 4 | Estimates: backend — rate calculation engine (gold+stone+making) | Estimates: frontend — form builder with live rate auto-fill | Estimates (Part 1) | Estimate creation | 8 | Pending
Day 5 | Estimates: PDF generation, WhatsApp share, status workflow | Estimate → Invoice conversion, approval flow | Estimates (Complete) | Full estimate module | 8 | Pending
Day 6 | Repairs: DB schema jw_repairs, stage tracking, billing | Repairs: intake form, stage tracker UI, payment flow | Repairs Management | Repair orders complete | 8 | Pending
Day 7 | Karigar: metal issue/receive, balance tracking, ledger | Karigar: UI — master list, metal issue form, balance dashboard | Karigar Management | Karigar module complete | 8 | Pending
Day 8 | Production Orders: jw_production_orders, 6 core stages (CAD→Casting→Polish→QC→Finalize→Settle) | Production: order creation form, stage pipeline UI | Production (Core 6 stages) | Production orders live | 8 | Pending
Day 9 | Production: material issue to order, wastage tracking, barcode on finalize | Production: stage completion forms, weight in/out, QC pass/fail | Production (Complete) | Production + barcode | 8 | Pending
Day 10 | Hallmarking register (BIS/HUID), link to items, status tracking | Chit Schemes: master, member enrollment, installment tracking | Hallmarking + Chit Schemes | Both modules done | 8 | Pending
Day 11 | Jobwork Orders: karigar assign, stage track, finalize + payment | Customer Buyback: valuation form (weight×rate), transaction log | Jobwork + Buyback | 2 modules complete | 8 | Pending
Day 12 | JW Analytics: sales by category, metal movement, karigar performance | Analytics UI: charts, MIS export (Excel/PDF) | JW Analytics | Analytics dashboard | 8 | Pending
Day 13 | Business profile module gating (Single Store/Wholesaler/Multi Chain/Mfg) | WhatsApp alerts (estimate share, repair updates), notification config | Profiles + WhatsApp | Profile gating done | 8 | Pending
Day 14 | End-to-end testing: all 10 modules, data flow, GST calculations | Bug fixes from testing, responsive mobile layout polish | QA + Bug Fixes | All modules tested | 8 | Pending
Day 15 | Replit production deployment, env vars, domain, final DB migration | UAT with domain expert, training session (admin + ops), handover doc | Go-Live | Production ready | 8 | Pending
Modules Delivered in Phase 1 (15 Days)
✓ JW Dashboard | Live gold rate, KPI cards, business profile
✓ Metal Rates | MCX/IBJA live rate, history, manual override
✓ Jewellery Items Master | HUID, barcode, categories, stone details
✓ Estimates Builder | Live-rate quotes, PDF, WhatsApp share, → Invoice
✓ Repairs Management | Intake, stages, billing, customer updates
✓ Karigar Management | Metal issue/receive, balance, ledger, payment
✓ Production Orders (6 stages) | CAD→Casting→Polish→QC→Finalize→Settlement
✓ Hallmarking Register | BIS/HUID tracking, linked to items
✓ Chit Schemes | Master, enrollment, installments, redemption
✓ Jobwork Orders | Karigar assign, stages, finalize, payment
✓ Customer Buyback | Valuation, weight×rate, transaction log
✓ JW Analytics | Sales, metal movement, karigar performance, MIS export

## Resource Cost
Resource Cost — Lean 15-Day Gold ERP Sprint Team
4-person focused sprint team. Senior devs work in parallel tracks. Domain expert on-call.
Role | Level | Monthly (₹) | Daily Rate (₹) | Days | Internal Cost (₹) | Billed to Client (₹) | Responsibilities
Full-Stack Dev A (Lead) | Senior | 120000 | 5000 | 15 | 75000 | 150000 | Backend: DB schema, APIs, all 10 JW modules server-side, deployment
Full-Stack Dev B | Senior | 90000 | 3600 | 15 | 54000 | 108000 | Frontend: all JW module UIs, responsive layout, charts, PDF templates
Full-Stack Dev C | Junior | 50000 | 2000 | 15 | 30000 | 60000 | Bug fixes, WhatsApp integration, barcode/label printing, test support
Domain Expert | Consultant | 100000 | 4000 | 10 | 40000 | 80000 | Requirements gathering, UAT, training, process validation, go-live support
QA Engineer | Mid | 45000 | 1800 | 5 | 9000 | 25000 | End-to-end testing, bug reporting, UAT coordination, regression tests
Project Manager | Senior | 90000 | 3600 | 5 | 18000 | 36000 | Sprint planning, daily standups, client communication, risk management
TOTAL |  |  |  | 65 | 226000 | 459000 | Gross margin: 51%

## Phase 1 vs Phase 2 Scope
Scope Split — Phase 1 (₹8L / 15 Days) vs Phase 2 (Future)
Phase 1 Feature (IN SCOPE) | Days | Phase 2 Feature (DEFERRED) | Est. Days | Phase 2 Reason
JW Dashboard + KPI cards | 2 | Bullion Trading full module | 12 | Complex rate-cut logic
Live Metal Rates (MCX/IBJA) | 2 | Bullion Invoice & rate cuts | 5 | Needs bullion P1 first
Jewellery Items Master | 3 | Production: stages 7–15 (Filing→Settle) | 8 | Phase 1 has 6 core stages
Estimates Builder (full) | 5 | Multi-currency (USD/AED export) | 5 | Less common requirement
Repairs Management | 4 | RFID tag tracking | 3 | Hardware-dependent
Karigar Management | 5 | Advanced karigar payroll integration | 5 | HR module dependency
Production Orders (6 stages) | 7 | Full 15-stage production pipeline | 8 | Phase 1 = 6 stages
Hallmarking Register | 2 | Chit scheme redemption bonus engine | 4 | Complex rules per scheme
Chit Schemes (basic) | 3 | Loyalty & rewards program | 4 | POS integration needed
Jobwork Orders | 4 | Wholesale order booking (B2B portal) | 6 | B2B feature
Customer Buyback | 2 | Physical inventory count / reconciliation | 3 | Ops process dependent
JW Analytics (core) | 3 | Advanced MIS (pivot reports) | 4 | Custom report builder
Business profile gating | 2 | Multi-branch stock consolidation | 6 | Multi-location feature
WhatsApp integration (alerts) | 1 | API Hub for third-party integrations | 5 | Enterprise feature
Deployment + go-live | 2 | Feedback & survey module (CRM) | 3 | Nice-to-have
QA + Bug fixes | 5 | On-premise license key system | 4 | Only if on-prem client
Training + documentation | 2 | GSTR-1 / GSTR-3B JW-specific reports | 3 | Tax consultant needed
PHASE 1 TOTAL | 54 | PHASE 2 TOTAL | 88 | Phase 2 = ~88 more days
PHASE 2 PRICING (Separate Quotation)
Phase 2 — Basic (Bullion + 15-stage Production) |  | 35–40 days | ₹3,50,000–₹4,50,000
Phase 2 — Standard (+ Multi-branch + B2B portal) |  | 50–60 days | ₹5,00,000–₹6,50,000
Phase 2 — Full (All 137 features complete) |  | 80–90 days | ₹8,00,000–₹10,00,000
Phase 1 + Phase 2 Full (Total project) |  | 95–105 days | ₹14,00,000–₹18,00,000

## Infrastructure & Total
Infrastructure Cost + Grand Total Cost Summary
Infrastructure Item | One-Time (₹) | Monthly (₹) | 3-Month Total (₹) | Annual (₹) | Notes
Replit Core (Build) | 0 | 2900 | 8700 | 34800 | Dev environment — $35/mo
Replit Deploy (Production) | 0 | 2500 | 7500 | 30000 | Production hosting — $30/mo
Neon PostgreSQL | 0 | 0 | 0 | 0 | Free tier sufficient for Phase 1
Domain Name (.com) | 1200 | 0 | 1200 | 1200 | Namecheap/GoDaddy — ₹1,200/yr
SSL Certificate | 0 | 0 | 0 | 0 | Free via Let's Encrypt on Replit
Gold Rate API (MCX/IBJA) | 0 | 2000 | 6000 | 24000 | Live gold/silver rate feed
WhatsApp Cloud API | 0 | 3000 | 9000 | 36000 | Meta Business API
Razorpay Gateway | 0 | 0 | 0 | 0 | 2% per txn — no monthly fee
Barcode Printer | 8000 | 0 | 8000 | 8000 | One-time label printer setup
Branding (logo/colors) | 3000 | 0 | 3000 | 3000 | Gold ERP custom branding
SendGrid Email | 0 | 820 | 2460 | 9840 | Email alerts — $10/mo
Backup (Cloudflare R2) | 0 | 400 | 1200 | 4800 | $5/mo cloud backup
TOTAL INFRA (3-Month Build Phase) | 12200 | 11620 | 47060 | 151640
GRAND TOTAL — CLIENT QUOTE
Development Cost (2 Sr + 1 Jr Dev × 15 days) |  |  | 159000
Domain Expert (10 days) |  |  | 40000
QA + Project Management |  |  | 27000
Infrastructure (3-month build phase) |  |  | 47060
Customization (JW-specific) |  |  | 50000
Training & Documentation |  |  | 12000
Buffer / Contingency (10%) |  |  | 33406
Subtotal (Internal Cost) |  |  | 368466
Profit Margin (~54%) |  |  | 431534
CLIENT QUOTE — PHASE 1 (15 Days) |  |  | 800000 |  | Rounded to ₹8,00,000
ACCEPTABLE QUOTE RANGE
Minimum Quote (tight margin ~48%) |  |  | 700000 | If client is price-sensitive or long-term partner
Target Quote (recommended ~54%) |  |  | 800000 | Sweet spot — fair for both sides
Maximum Quote (premium ~60%) |  |  | 900000 | If client has no competition / urgent delivery