## Executive Summary
SwachERP — Complete Build Plan ¦ 19 Phases ¦ 30 Days ¦ Budget ≤ ₹10 Lakhs
Gold & Jewellery ERP + Industry-Agnostic Platform · Client Proposal · May 2026
| TOTAL BUDGET |  | TIMELINE |  | TEAM SIZE
| ₹ 10,00,000 |  | 30 Days |  | 5 Members
| Fixed-price, all-inclusive |  | June 2026 – Go Live |  | 2 Sr Dev + 2 Dev + QA
| TOTAL PHASES |  | FEATURES |  | MARGIN
| 19 Phases |  | 137+ Features |  | ~45%
| Gold ERP + Platform + SaaS |  | All modules, no compromise |  | Gross margin on ₹10L quote
19-PHASE DELIVERY OVERVIEW
# | Phase Name | Category | Days | Start | End
1 | Core ERP Platform & Multi-tenancy | Platform | 2 days | Day 1 | Day 2
2 | Authentication, RBAC & Permissions | Platform | 1 days | Day 2 | Day 3
3 | Chart of Accounts & Double-Entry | Finance | 2 days | Day 3 | Day 5
4 | GST Invoicing & E-Invoice | Finance | 2 days | Day 4 | Day 6
5 | Purchase Orders & GRN | Procurement | 2 days | Day 5 | Day 7
6 | Inventory & Multi-Warehouse | Inventory | 2 days | Day 6 | Day 8
7 | HR, Payroll & Attendance | HR | 2 days | Day 7 | Day 9
8 | CRM & Customer Portal | CRM | 1 days | Day 8 | Day 9
9 | Metal Rate Engine (IBJA/MCX live) | Gold ERP | 2 days | Day 9 | Day 11
10 | Jewellery Item Master & Pricing | Gold ERP | 2 days | Day 10 | Day 12
11 | Karigar Management & Job Orders | Gold ERP | 2 days | Day 11 | Day 13
12 | Retail Billing & Making Charges | Gold ERP | 2 days | Day 12 | Day 14
13 | Bullion Trading & Scrap | Gold ERP | 2 days | Day 13 | Day 15
14 | Gold Savings Chit Schemes | Gold ERP | 2 days | Day 14 | Day 16
15 | Repair Orders & Design Catalogue | Gold ERP | 2 days | Day 15 | Day 17
16 | Hallmarking & BIS Compliance | Gold ERP | 2 days | Day 16 | Day 18
17 | WhatsApp 2-Way Integration | Integrations | 2 days | Day 17 | Day 19
18 | MIS Reports & Gold Analytics | Analytics | 2 days | Day 19 | Day 21
19 | SaaS Licensing, AMC & Go-Live | Platform | 3 days | Day 21 | Day 24
PARALLEL DEVELOPMENT: Phases 1–8 (Platform) run concurrently with Phases 9–16 (Gold ERP) using 2 dedicated tracks — Timeline collapses to 30 days

## 30-Day Gantt
SwachERP — 30-Day Sprint Gantt Chart ¦ Parallel Track Development
Track A: Gold ERP Modules · Track B: Platform & Integrations · Start Day = Day 1
# | Phase Name | Track | Days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
|  |  |  | W1 | [6 empty] | W2 | [6 empty] | W3 | [6 empty] | W4 | [6 empty] | W5
1 | Metal Rate Engine (IBJA / MCX live feed) | Track A | 3
2 | Jewellery Item Master & Pricing Engine | Track A | 3
3 | Karigar Mgmt, Advances & Job Orders | Track A | 3
4 | Retail Billing, Making Charges & Wastage | Track A | 3
5 | Bullion Trading & Scrap Buy/Sell | Track A | 3
6 | Gold Savings Chit / Scheme Management | Track A | 2
7 | Repair Orders & Design Catalogue | Track A | 2
8 | Hallmarking & BIS Compliance | Track A | 2
9 | Gold ERP Analytics & MIS Reports | Track A | 2
10 | Multi-Branch Gold ERP + Consolidation | Track A | 3
11 | Core ERP Platform & Multi-tenancy | Track B | 2
12 | Authentication, RBAC & Role Permissions | Track B | 2
13 | GST Invoicing, E-Invoice & GSTR Reports | Track B | 3
14 | Purchase Orders, GRN & 3-Way Matching | Track B | 3
15 | Inventory, Warehouses & Stock Transfers | Track B | 3
16 | HR, Payroll, Attendance & Leaves | Track B | 3
17 | CRM, Customer Portal & Lead Pipeline | Track B | 2
18 | WhatsApp 2-Way + Notification Engine | Track B | 3
19 | SaaS Licensing, AMC, Module Marketplace | Track B | 3
20 | Integration Testing & QA Sign-off | QA | 4
21 | UAT, Training & Go-Live Deployment | QA | 2
LEGEND: |  |  |  | Track A: Gold ERP |  |  | Track B: Platform |  |  | QA & Go-Live |  |  | Weekend

## Resource & Cost
Resource & Cost Breakdown — 30-Day Project
All costs in INR (₹) · Fixed price model · No hidden charges
TEAM COST (30 DAYS)
# | Role | Seniority | Monthly Rate | 30-Day Cost | Allocation | Effective Cost
1 | Tech Lead / Architect | Senior | 150000 | 150000 | 100% | 150000
2 | Full Stack Dev A (Gold ERP) | Senior | 100000 | 100000 | 100% | 100000
3 | Full Stack Dev B (Platform) | Mid | 80000 | 80000 | 100% | 80000
4 | Frontend / UI Dev | Mid | 75000 | 75000 | 100% | 75000
5 | QA Engineer | Junior | 55000 | 55000 | 100% | 55000
TOTAL TEAM COST | [5 empty] | 460000
INFRASTRUCTURE & TOOLS (30 DAYS)
# | Item | Vendor | Unit Cost | Units | Total | Notes
1 | Neon PostgreSQL (Pro) | Neon.tech | 3500 | 1 | 3500 | Serverless, auto-scale
2 | Replit Hacker / Hosting | Replit | 2000 | 1 | 2000 | Dev + staging environment
3 | WhatsApp Business API | Meta Cloud | 2000 | 1 | 2000 | 1000 msgs/month included
4 | Colloki Flow API | Colloki | 1500 | 1 | 1500 | WhatsApp 2-way automation
5 | SendGrid Email | Twilio | 500 | 1 | 500 | Transactional email
6 | Razorpay Payment GW | Razorpay | 500 | 1 | 500 | For SaaS billing
7 | Domain + SSL | GoDaddy/CF | 1000 | 1 | 1000 | swacherp.com SSL
8 | SMS Gateway | Fast2SMS | 500 | 1 | 500 | OTP + alerts
9 | MCX / IBJA Rate Feed | Commodity API | 2000 | 1 | 2000 | Live gold rates
10 | Miscellaneous / Buffer | - | 2000 | 1 | 2000 | Unexpected costs
TOTAL INFRASTRUCTURE COST | [5 empty] | 16500
BUDGET SUMMARY
Team Cost (5 members × 30 days) | [5 empty] | 460000
Infrastructure & Tools | [5 empty] | 16500
Contingency / Buffer (5%) | [5 empty] | 23825
TOTAL INTERNAL COST | [5 empty] | 500325
CLIENT QUOTE (Fixed Price) | [5 empty] | 1000000
Gross Margin | [5 empty] | 499675
Margin % | [5 empty] | ~50%

## Phase-Wise Scope
Phase-Wise Feature Scope — All 19 Phases
Detailed breakdown of deliverables per phase · DB tables · APIs · UI Screens
| Ph# | Deliverable / Feature | Owner Track | DB Tables | APIs | UI Screens
PLATFORM PHASES (Track B — Dev B + Frontend Dev)
Phase 1: Core ERP Platform & Multi-tenancy
| 1 | Multi-tenant data isolation (AsyncLocalStorage) | Track B | tenants, subscriptions | 6 | 2
| 1 | Session management & secure cookies | Track B | sessions | 3 | 1
| 1 | Plan gating middleware (feature flags) | Track B | subscription_plans | 4 | 1
| 1 | Company settings & branding | Track B | company_settings | 5 | 2
Phase 2: Authentication & RBAC
| 2 | Email + username login (scrypt hashing) | Track B | users | 2 | 2
| 2 | Role-based access control (can_view/create/edit) | Track B | roles, role_permissions | 5 | 2
| 2 | Employee invite & onboarding flow | Track B | users | 3 | 2
Phase 3: GST Invoicing & Finance
| 3 | Double-entry journal engine | Track B | journal_entries | 8 | 1
| 3 | GST tax invoice (B2B/B2C) with IRN/QR | Track B | invoices | 6 | 3
| 3 | GSTR-1 / GSTR-3B reports & JSON export | Track B | gst_reports | 3 | 2
| 3 | Chart of accounts (COA) management | Track B | chart_of_accounts | 4 | 2
Phase 4: Purchase & GRN
| 4 | Purchase requisitions → PO → GRN flow | Track B | purchase_orders, grn | 8 | 4
| 4 | Vendor management & credit limits | Track B | vendors | 5 | 2
| 4 | 3-way matching (PO ↔ GRN ↔ Invoice) | Track B | matching_log | 3 | 1
Phase 5: Inventory & Warehouses
| 5 | Multi-location warehouses & stock transfer | Track B | warehouses, stock_transfers | 6 | 3
| 5 | UOM conversions & serial/lot tracking | Track B | uom, serial_lot | 4 | 2
| 5 | Reorder alerts & stock reports | Track B | products | 3 | 2
Phase 6: HR & Payroll
| 6 | Employee master & departments | Track B | employees | 4 | 2
| 6 | Attendance, leaves & overtime | Track B | attendance, leaves | 6 | 3
| 6 | Payroll computation & payslips | Track B | payroll | 5 | 2
Phase 7: CRM
| 7 | Lead management & pipeline | Track B | leads | 4 | 2
| 7 | Customer follow-up & activity log | Track B | crm_activities | 3 | 2
Phase 8: WhatsApp & Notifications
| 8 | Meta Cloud API 2-way WhatsApp | Track B | whatsapp_messages | 6 | 2
| 8 | Automated alerts (invoice, order, scheme) | Track B | notification_templates | 4 | 2
GOLD ERP PHASES (Track A — Tech Lead + Dev A)
Phase 9: Metal Rate Engine
| 9 | Live IBJA / MCX gold & silver rate feed | Track A | metal_rates | 4 | 2
| 9 | Rate history, alerts & date-wise purity rates | Track A | metal_rate_history | 3 | 2
Phase 10: Jewellery Item Master
| 10 | Metal/stone/making charge price engine | Track A | jw_items, jw_purity | 6 | 3
| 10 | Wastage %, melting %, karigar rate config | Track A | jw_pricing_config | 4 | 2
Phase 11: Karigar Management
| 11 | Karigar master, advances & job orders | Track A | jw_karigars, jw_job_orders | 7 | 3
| 11 | Weight issue/receive & purity conversion | Track A | jw_weight_ledger | 4 | 2
Phase 12: Retail Billing
| 12 | GST jewellery bill with making charges | Track A | jw_sales | 6 | 3
| 12 | Old gold exchange & melt value calculator | Track A | jw_exchange | 4 | 2
Phase 13: Bullion Trading
| 13 | Gold bar/coin buy-sell transactions | Track A | jw_bullion | 5 | 2
| 13 | Scrap gold purchase & refinery tracking | Track A | jw_scrap | 3 | 2
Phase 14: Gold Savings Chit Schemes
| 14 | Monthly scheme enrolment & instalment tracking | Track A | jw_chit_schemes, jw_chit_members | 6 | 3
| 14 | Redemption — jewellery or cash options | Track A | jw_redemptions | 3 | 2
Phase 15: Repair & Design
| 15 | Repair order with before/after photos | Track A | jw_repairs | 5 | 3
| 15 | Design catalogue with image upload & tags | Track A | jw_designs | 4 | 2
Phase 16: Hallmarking & BIS
| 16 | HUID generation & BIS lot submission | Track A | jw_hallmarking | 5 | 2
| 16 | Assay centre integration & purity cert | Track A | jw_assay | 3 | 2
Phase 17: Analytics & MIS
| 17 | Gold ERP dashboard — stock, sales, karigar KPIs | Track A | analytics_views | 5 | 3
| 17 | P&L by branch, category, karigar | Track A | financial_reports | 4 | 2
Phase 18: Module Marketplace & SaaS Billing
| 18 | Per-module pricing & selection UI | Track B | subscriptions | 5 | 3
| 18 | Razorpay recurring billing integration | Track B | billing_events | 4 | 2
Phase 19: SaaS Licensing, AMC & Go-Live
| 19 | License key generation (SaaS + On-Premise) | Track B | license_keys | 5 | 2
| 19 | AMC tracking, renewal alerts | Track B | amc_schedule | 3 | 2
| 19 | Production deployment, DNS, SSL, monitoring | Track B | - | 2 | 1

## Payment Milestones
Payment Milestones — ₹10,00,000 Fixed Price
3 milestone payments · Linked to deliverable sign-off · No payment without demo
| M# | Milestone Name | Deliverables | Due Date | Amount | % of Total
1 | MILESTONE 1: Project Kick-off & Advance |  | Day 0 (Signing) |  | ₹300,000 | 30%
Signed agreement + requirement lock Environment setup + DB schema Project plan approval
2 | MILESTONE 2: Mid-Sprint Delivery (Day 15) |  | Day 15 |  | ₹400,000 | 40%
Phases 1–10 demo (Gold ERP core + Platform base) Metal rates + Karigar + Billing live All API endpoints tested
3 | MILESTONE 3: Final Delivery & Go-Live |  | Day 30 |  | ₹300,000 | 30%
All 19 phases complete + QA sign-off UAT by client team Deployment + training + handover
TOTAL PROJECT VALUE |  |  |  |  | ₹10,00,000 | 100%
PAYMENT TERMS & CONDITIONS
1. Payment via NEFT/RTGS to company account. UPI accepted for amounts ≤ ₹1L.
2. Each milestone payment is due within 3 business days of deliverable demo sign-off.
3. Source code escrow provided after Milestone 3 clearance.
4. Post go-live support: 30 days free bug fixes. Extended support via AMC @ ₹60,000/year.
5. Ownership of code transfers to client upon full payment.

## Risk & Assumptions
Risk Register & Assumptions
All risks mitigated through parallel dev, daily standups & fixed-price contract
KEY ASSUMPTIONS
| # | Assumption
| 1 | Client provides logo, branding colors, and GSTIN details within Day 1
| 2 | MCX/IBJA API access credentials provided by client (or we use public scrape fallback)
| 3 | Existing SwachERP codebase is the base — NO rewrite from scratch
| 4 | Client team (1 person) available for daily 30-min standup during build
| 5 | UAT feedback cycle capped at 3 rounds; no scope creep without change order
| 6 | On-premise delivery = Docker container + PostgreSQL dump + license key
| 7 | WhatsApp Business API approved account provided by client OR we help set up
| 8 | Payment gateway (Razorpay) account already exists with client
RISK REGISTER
| # | Risk | Probability | Impact | Mitigation | Owner
| 1 | Scope creep from client change requests | Medium | High | Change order process; signed scope doc | PM
| 2 | MCX API rate limits or downtime | Low | Medium | Cache rates every 5 min; fallback to IBJA scrape | Dev A
| 3 | WhatsApp API approval delay (Meta) | Medium | Medium | Start approval Day 1; use SMS fallback if delayed | Dev B
| 4 | Team member unavailability / sick leave | Low | High | Cross-trained; Tech Lead can cover any module | TL
| 5 | Client delays in UAT sign-off | Medium | Medium | Auto-escalation after 48hrs; capped 3 rounds | PM
| 6 | Razorpay / payment gateway integration issues | Low | Low | Well-documented API; existing codebase has Razorpay | Dev B
| 7 | Database performance at scale (multi-tenant) | Low | High | Neon serverless auto-scales; connection pooling enabled | TL