## 📊 Summary
Gold / Jewellery ERP — Final Build Plan for SwachERP
Based on SIONIQ ERP PDF (Manufacturers / Wholesalers / Retailers / Bullion Traders) mapped against SwachERP existing 143 screens
✅ REUSE | 🔧 EXTEND | 🆕 BUILD
SwachERP already has this screen — use as-is or tiny config change. Zero build effort. | SwachERP has the base — add jewellery-specific fields, logic, or UI. Medium effort. | Completely new screen — does not exist in SwachERP at all. Full build required.
Total screens in Gold ERP | ✅ Reuse (no build) | 🔧 Extend existing | 🆕 Build from scratch | Sub-modules
108 | 9 | 30 | 69 | 11
Total APIs | 🆕 Build APIs | 🔧 Extend APIs | Total Integrations | 🆕 New Integrations
116 | 100 | 16 | 18 | 11 | Key missing feature
Production | 0 | 4 | 14 | 18 | 14-stage production flow, Ghat/Casting/Settlement — completely absent from SwachERP
Wholesale | 4 | 6 | 5 | 15 | Bullion transactions, Line-wise inventory, Rate-cut invoicing
Retail | 1 | 6 | 13 | 20 | Gold Chit Schemes, Estimation, Customer approval, Buy-back, Physical inventory control
Bullion Trade | 3 | 1 | 4 | 8 | Bullion booking/inward, Rate cuts, Vault physical control, Movement dashboard
Gold Chit Schemes | 0 | 0 | 7 | 7 | Entire module missing — scheme setup, enrollment, collection, maturity, redemption
E-Catalog | 0 | 1 | 4 | 5 | B2B digital catalogue with secure sharing, 360° view, content protection
OMS | 1 | 2 | 3 | 6 | Customer-facing order portal with live availability and tracking
E-Commerce | 0 | 2 | 5 | 7 | Jewellery store with live gold rate-based pricing — unique requirement
RFID | 0 | 1 | 6 | 7 | Real-time inventory tagging, anti-theft, bulk scanning — hardware + software
Business Analytics | 0 | 6 | 4 | 10 | Making charge trends, weight/purity loss P&L, item-wise tag insights
Finance (Jewellery) | 0 | 1 | 4 | 5 | Metal-based parallel accounting (gm alongside ₹) — fundamental for gold business

## 📋 Full Build Plan
Sub-Module | Status | # | Screen Name | Priority | Effort | UI Fields / Columns | SwachERP Reference
Production | 🔧 EXTEND | 1 | Production Planning | High | Medium | Work Order No (auto), Design Ref, Item Type (Ring/Necklace/Bangle/etc.), Metal, Purity, Quantity (pieces), Target weight per piece (gm), Total gold required (gm), Raw material check (Green=available/Red=short), Assigned karigar / department, Planned start date, Planned end date, Priority (Urgent/Normal), Linked customer order, Current stage (live), Status (Planned/In progress/Completed/Cancelled), Notes | Extend: Production Entries + add jewellery stages/weight tracking
| 🆕 BUILD | 2 | Master Design Library | High | Medium | Design Code (auto), Design Name, Category (Ring/Necklace/Bangle/Earring/Pendant/Bracelet/Set), Sub-category, Metal (Gold/Silver/Platinum), Purity, Style (Plain/Filigree/Casting/Handmade/Antique/Kundan/Meenakari/Diamond/CZ), Sketch image upload (multiple), CAD file attachment, Standard weight range (min–max gm), Stone details (type/shape/size/count), Making charges (₹/gm or ₹/piece), Selling price formula, Active (Y/N), Created by, Version history | New — no equivalent in SwachERP
| 🆕 BUILD | 3 | Sketch Process | High | Small | Job ID, Design Code (linked), Sketch artist name, Sketch date, Customer design brief (text + reference images uploaded), Sketch version (v1/v2/v3), Sketch images (upload multiple), Customer approval status (Pending/Approved/Revision requested), Revision notes, Approved by, Approved on, Proceed to CAD (button) | New — no equivalent in SwachERP
| 🆕 BUILD | 4 | CAD Process | High | Medium | Job ID, Design Code, CAD operator name, Software used (RhinoGold/Matrix/JewelCAD/3Design), CAD file upload (.3dm/.stl/.obj), CAD version, Weight estimate from CAD (gm), Metal volume (cc), Render images (upload multiple), Customer approval status, Revision notes, Stone placement verification (Y/N), Approved by, Approved on, Send to CAM (button), Estimated production cost (auto from weight × rate) | New — no equivalent in SwachERP
| 🔧 EXTEND | 5 | Design Approvals | Medium | Small | Approval ID, Job ID, Design Code, Stage (Sketch/CAD/Sample), Submitted by, Submitted on, Submitted to (customer/internal), Customer name, Approval method (In-person/WhatsApp/Email/Portal), Status (Pending/Approved/Revision/Rejected), Revision count, Comments, Approved by, Approved on, Attach approved file | Extend: Approval Workflows — add jewellery design context
| 🆕 BUILD | 6 | CAM Process | High | Medium | Job ID, CAM operator, CAM software (SprutCAM/Fusion 360/Custom), Milling/printing machine, Material for prototype (Wax/Resin/Metal), CAM file upload, Estimated time (hrs), Actual time (hrs), Output: prototype weight (gm), Prototype images, Quality check on prototype (Y/N), Issues noted, Proceed to tree setup (button) | New — manufacturing-specific
| 🆕 BUILD | 7 | Tree Setup (Casting Tree) | High | Medium | Tree ID (auto), Job ID, Metal, Purity, Sprue/tree wax weight (gm), Items attached to tree: (Design Code ¦ Qty pieces ¦ Each weight gm ¦ Total weight gm), Total wax tree weight (gm), Gold required for casting (calculated: weight × density × purity factor), Casting alloy additions (if any), Tree photo upload, Approved by, Date, Casting operator assigned | New — jewellery casting specific
| 🆕 BUILD | 8 | Ghat Process (Weighing & Assaying) | High | Small | Ghat Entry ID, Date, Job ID, Stage (Pre-casting / Post-casting / Post-polish / Final), Operator name, Item description, Gross weight (gm), Stone weight deduction (gm), Net metal weight (gm), Purity tested (touchstone/XRF/acid test), Purity % result, Expected purity %, Variance (%), Alert if variance >0.5%, Alloy composition (if tested), Weighing scale ID / calibration date, Witnessed by | New — critical for gold accuracy
| 🆕 BUILD | 9 | Material Management (per Job) | High | Small | Job ID, Date, Material type (Gold / Silver / Solder / Alloy / Chemicals / Consumables), Material issued (gm / qty), Issued from stock (location), Issued by, Issued to (karigar/department), Purpose (Casting/Repair/Plating/Polishing), Material returned (gm / qty), Net consumed (gm auto), Variance vs BOM (gm), Variance reason, Stock balance updated (Y/N) | Extend: Raw Material Issuance — add weight/purity fields
| 🆕 BUILD | 10 | Casting Process | High | Medium | Casting ID, Date, Job ID / Tree ID linked, Furnace / casting machine, Operator, Metal poured (gm), Alloy added (gm), Total melt weight (gm), Casting method (Vacuum / Centrifugal / Gravity), Temperature (°C), Casting time (mins), Quench method (Water/Air), Raw casting weight (gm), Casting tree removed (Y/N), Sprue cut weight (gm — returned to stock), Net casting weight (gm), Visual inspection (Pass/Fail), Issues (Porosity / Shrinkage / Incomplete fill / Other), Re-cast required (Y/N) | New — jewellery manufacturing specific
| 🆕 BUILD | 11 | Filing & Buffing | Medium | Small | Job ID, Operator name, Date, Input weight (gm — from casting), Filing tools used, Buffing wheel type, Filing dust collected (gm), Buffing dust collected (gm), Total wastage collected (gm), Output weight (gm after filing), Visual check (surface finish — Pass/Fail), Issues noted, Time taken (mins), Move to: Fitting / Stone setting / Polish | New — post-casting stage
| 🆕 BUILD | 12 | Fitting Process | Medium | Small | Job ID, Fitting operator, Date, Input weight (gm), Items to fit: (Component ¦ Type: Clasp/Hook/Ear-pin/Ring shank/Bail ¦ Weight gm ¦ Soldered Y/N), Solder used (gm — goes to wastage), Post-fitting weight (gm), Strength test (Pass/Fail), Visual check (Pass/Fail), Issues, Time taken (mins), Move to: Stone setting / Polish | New — assembly stage
| 🆕 BUILD | 13 | Polish Process | Medium | Small | Job ID, Polish operator, Date, Input weight (gm), Polish type (Mechanical/Electrolytic/Hand), Polishing compound used (type + gm), Rhodium plating (Y/N), Rhodium weight (gm — if plated), Polish dust / slurry collected (gm — to wastage), Output weight (gm), Finish quality (Mirror/Matte/Satin/Antique), Visual check (Pass/Fail), Issues, Time taken (mins), Move to QC | New — finishing stage
| 🔧 EXTEND | 14 | Quality Check (Jewellery) | High | Small | QC Entry ID, Job ID, QC inspector, Date, Item: Design Code, Metal, Purity, Weight (gm), Checks: (Purity verified Y/N ¦ Finish quality Pass/Fail ¦ Stone set securely Y/N ¦ Dimensions as per design Y/N ¦ HUID verified Y/N ¦ No cracks/porosity Y/N ¦ Clasp/closure function Y/N ¦ Customer design match Y/N), Overall Result (Pass/Fail/Rework), Rework instructions, Rework karigar assigned, Re-QC date, Final approval (Y/N), Move to finalize | Extend: Quality/Returns — add jewellery-specific checklist items
| 🆕 BUILD | 15 | Job Finalize & Barcode | High | Small | Job ID, Finalize date, Design Code, Metal, Purity, Final weight (gm), Stone details (if any), HUID No (BIS hallmark — enter or scan), Barcode / Tag No (auto-generated), Tag type (RFID/Barcode), Tag printed (Y/N), Print tag button, Photo of finished item (upload), Certificate of authenticity (auto-generate), Move to finished goods stock (button), Linked to customer order (Y/N), Ready for dispatch (Y/N) | New — critical link between production and inventory
| 🆕 BUILD | 16 | Settlement | High | Medium | Settlement ID, Job ID, Design Code, Customer (if made-to-order), Settlement date, Gold issued (gm), Gold returned in piece (gm), Wastage collected (gm: filing dust + polish dust + casting sprue), Total accounted gold (gm auto), Unaccounted gold (issued − returned − wastage — should be 0), Karigar making charges (₹), Deductions (excess wastage × gold rate), Net payable to karigar (₹), Settlement mode (Cash/Bank), Settled (Y/N), Settlement date, Approved by | New — critical job closure screen
| 🔧 EXTEND | 17 | Worker Material Management | Medium | Small | Worker/Karigar Name, Date, Gold in hand (current — gm), Pending jobs (count), Material issued today: (Job ID ¦ Material ¦ Weight gm), Material returned today: (Job ID ¦ Material ¦ Weight gm), Accumulated wastage collected (gm), Net gold balance with worker (gm), Alert if gold in hand >X gm for >Y days, Tools issued (list), Tool condition, Payment advance given (₹) | Extend: Raw Material Issuance — add karigar-wise tracking
| 🆕 BUILD | 18 | Jobwork Register (Karigar) | High | Medium | Job Work ID, Issue date, Karigar name, Trade (Goldsmith/Stone setter/Polisher/Fitter/Engraver), Design Code, Production Order No, Metal issued (gm), Purity, Stones issued (type/qty/carats), Findings issued, Expected return date, Actual return date, Metal returned in piece (gm), Stones returned (Y/N), Allowed wastage % (by trade), Allowed wastage gm (auto), Actual wastage gm (issued − returned), Excess wastage gm (actual − allowed), Excess wastage deduction (₹ = excess × gold rate), Making charges (₹), Net payable, Payment status | New — detailed karigar accountability
Wholesale | 🔧 EXTEND | 1 | Order Booking (Wholesale) | High | Small | Order No (auto), Order date, Customer (retailer/wholesaler), Customer GST, Design Code / Catalogue reference, Item description, Metal, Purity, Qty (pieces), Approx weight per piece (gm), Making charges agreed (₹/gm), Stone charges (if any), Advance paid (₹), Payment terms, Delivery date, Special instructions, Sketch / reference image attached, Production order auto-created (Y/N), Order status (Booked/In production/Ready/Dispatched) | Extend: Sales Orders — add gold-specific fields
| 🆕 BUILD | 2 | Jobwork Processing (Wholesale) | High | Medium | Jobwork ID, Customer name, Date received, Customer gold received (gm, purity — customer sends own gold), Design Code, Qty pieces, Making charges agreed (₹/gm or ₹/piece), Stone setting charges, Timeline, Gold issued to karigar (from customer account), Production tracking (same as production flow), Finished pieces (gm), Customer gold balance (gm auto), Invoice: making charges only (not gold value), Customer approval required (Y/N), Ready for delivery | New — key wholesale workflow
| 🔧 EXTEND | 3 | Inventory Inward (Wholesale) | High | Small | GRN No (auto), Date, Supplier, Invoice No, Item: Design Code, Metal, Purity, Gross weight (gm), Stone weight (gm), Net gold weight (gm), HUID No, Barcode No, Rate (₹/gm), Making charges (₹), Stone value (₹), Total value (₹), QC done (Y/N), Storage location, Certificate attached, Tag printed (Y/N) | Extend: GRN — add weight/purity/HUID fields
| 🔧 EXTEND | 4 | Barcode & Inventory (Wholesale) | High | Small | Item Tag No / Barcode, Design Code, Description, Metal, Purity, Gross weight (gm), Net gold weight (gm), Stone details, HUID No, Location (showcase/vault/safe), Status (Available/On approval/Sold/On repair/In transit), Gold value (auto: net weight × today's rate), Making charges, Total value, Customer holding (if on approval), Days in stock, Movement history | Extend: Serial/Lot Register — add jewellery tag fields
| 🆕 BUILD | 5 | Remodeling & Repair Process | Medium | Medium | Repair/Remodel ID, Date received, Customer name, Item description, Metal, Purity, Weight received (gm), Issue reported (Broken clasp/Resizing/Stone reset/Polish/Full remodel), Customer instructions, Photo on receipt (upload), Additional gold required (gm), Additional gold source (Customer provides/We supply), Making charges (₹), Estimated delivery date, Karigar assigned, Status (Received/In work/Ready/Delivered), Final weight (gm), Final photo, Customer sign-off | New — common jewellery service
| 🆕 BUILD | 6 | Bullion Transactions (Wholesale) | High | Medium | Transaction ID, Date, Transaction type (Purchase/Sale/Exchange/Rate cut), Party name, Metal (Gold/Silver/Platinum), Purity (999/995/916/875/etc.), Form (Bar/Coin/Granule/Scrap), Weight (gm / troy oz / kg), Rate agreed (₹/gm), Agreed rate date, Rate source (MCX/IBJA/Negotiated), Amount (₹ auto), Rate cut (₹ — discount for impurity), Net amount, Payment mode, Tax (GST — 3% on bullion), e-Way bill required (Y/N), Assay certificate attached | New — core for bullion/wholesale
| ✅ REUSE | 7 | Vendor & Supplier Process | Low | Small | Use existing SwachERP Vendors screen — add fields: Metal categories supplied (Gold/Silver/Stones/Findings), Assay lab preferred, Credit terms for bullion, GST No for bullion trading | Reuse: Vendors screen with minor additions
| 🔧 EXTEND | 8 | Inventory & Distribution Transfers | Medium | Small | Transfer ID, Date, From branch/location, To branch/location, Items: (Tag No ¦ Design Code ¦ Metal ¦ Purity ¦ Weight gm ¦ Value ₹), Total weight transferred (gm), Total value (₹), Transfer type (Sale/Stock movement/Approval/Return), Transit insurance (Y/N), Insured value, Vehicle/courier, Driver, E-way bill No, Received by, Received on, Discrepancy (Y/N), Discrepancy weight (gm) | Extend: Stock Transfers — add weight/value/insurance
| 🔧 EXTEND | 9 | Quotation Engine | Medium | Small | Quotation No, Date, Valid till, Customer, Item: Design Code, Metal, Purity, Weight (gm), Today's gold rate (auto from MCX), Gold value (auto: weight × rate), Making charges (₹/gm or ₹/piece), Stone charges, Wastage % (add-on), Hallmarking charges, Packaging, GST (3% on gold value), Total quotation value (₹), Margin % (internal view only), Convert to order (button), Download PDF, Share on WhatsApp | Extend: Price Lists — add gold rate-based calculation
| ✅ REUSE | 10 | Customer Ledger | Low | Small | Use existing SwachERP Ledger View — add: Gold account balance (gm) column alongside ₹ balance | Reuse: Ledger View with gold weight column
| ✅ REUSE | 11 | Receivables & Payables Tracking | Low | Small | Use existing SwachERP Aging Report + Pending Payments as-is | Reuse: Aging Report
| 🆕 BUILD | 12 | Line-wise Sales & Inventory | Medium | Medium | Line / Product category (22K Plain / 18K Diamond / Silver / etc.), Opening stock (pieces + gm), Inward (pieces + gm), Sales (pieces + gm), Returns (pieces + gm), Closing stock (pieces + gm), Closing gold value (₹ auto at today's rate), Stock aging (0–30 / 31–60 / 60–90 / 90+ days), Fast-moving designs (top 10 by pieces), Slow-moving (>60 days unsold), Reorder suggestion, Filter by branch / date | New — jewellery-specific stock analytics
| 🔧 EXTEND | 13 | Sales & Dispatch Process | High | Small | Invoice No, Date, Customer, Items: (Tag No ¦ Design Code ¦ Metal ¦ Purity ¦ Gross wt gm ¦ Net gold wt gm ¦ HUID ¦ Making charges ¦ Gold value ¦ Total), Total weight (gm), Total invoice value (₹), GST breakup (3% on gold / 5% on making), E-way bill No, Delivery challan No, Transit insurance (Y/N), Insured value (₹), Vehicle No / courier, Customer signature on receipt, Payment received (Y/N) | Extend: Dispatch Tracking + GST Invoice — add weight/purity/HUID
| 🆕 BUILD | 14 | Quality Testing & Hallmarking | High | Medium | Batch ID, Date, Items submitted: (Tag No ¦ Design Code ¦ Metal ¦ Claimed purity ¦ Weight gm), Submitted to hallmarking centre, BIS licence No of centre, Date submitted, Testing method (XRF/Acid/Cupellation), Tested purity (result), HUID assigned (per piece), Date received back, Rejected pieces (reason), Hallmark certificate upload, Update item tag (auto-links HUID to barcode/RFID), Cost (₹/piece × qty), Batch summary report | New — mandatory for all jewellers
| ✅ REUSE | 15 | Approval Workflow | Low | Small | Use existing SwachERP Approval Workflows — configure for jewellery: high-value sales >₹X, bullion transactions, returns | Reuse: Approval Workflows
Retail | 🔧 EXTEND | 1 | Inventory Inward (Retail) | High | Small | Same as Wholesale Inventory Inward — with additional: Branch/store received at, Source (Own manufacture/External supplier/HO transfer), Showcase placement (Showcase No / Tray No), Customer-facing tag updated (Y/N) | Extend: GRN — add branch/showcase placement
| 🔧 EXTEND | 2 | Barcode & Inventory (Retail) | High | Small | Same as Wholesale Barcode & Inventory — add: Showcase No, Tray No, Customer-visible display price (gold value + making), Walk-in customer enquiry count (if RFID), Days on display | Extend: Serial/Lot Register
| 🆕 BUILD | 3 | Quality Testing & Hallmarking (Retail) | High | Small | Same as Wholesale Quality Testing & Hallmarking — built once, used by both | New — same screen reused across Wholesale and Retail
| 🆕 BUILD | 4 | Bullion Transactions (Retail) | Medium | Small | Same as Wholesale Bullion Transactions — Customer old gold purchase (rate cut applied), Bullion sale to customer (coins/bars), Exchange transaction | New — same screen, retail context
| 🔧 EXTEND | 5 | Inventory Transfer & Distribution | Medium | Small | Same as Wholesale Inventory Transfers — add: Triggered by HO / self-initiated, Approval required for transfers >X gm | Extend: Stock Transfers
| 🆕 BUILD | 6 | Promotions & Rewards Setup | Medium | Small | Promotion ID, Name, Type (Making charge waiver / Flat discount / Gift on purchase / Gold coin on purchase / Double points), Applicable categories (All/22K/18K/Silver/Diamond/etc.), Min purchase value / weight, Discount value or %, Valid from/to, Applicable branches (All/specific), Customer segment (All/Gold member/Platinum), Stackable with loyalty points (Y/N), Terms & conditions, Active toggle, Usage count, Budget allocated (₹) | New — jewellery retail promotions
| 🆕 BUILD | 7 | Refining Process (Retail) | Medium | Medium | Refinery Entry ID, Source (Customer old gold / Workshop wastage / Returned goods), Customer name (if customer gold), Item description, Gross weight received (gm), Assay result (purity %), Net fine gold (gm), Refinery name, Date sent, Date received, Refined gold (gm), Recovery % (received/sent), Loss (gm), Loss within acceptable % (Y/N), Refined gold credited: Customer account / Own stock, Payment to/from customer (₹ if applicable), Certificate upload | New — retail refining/exchange
| 🆕 BUILD | 8 | Order & Jobwork Process (Retail) | High | Medium | Order ID, Customer name, Mobile, Date, Order type (New design/Remodel/Repair/Stone change/Resizing), Design reference (catalogue/custom sketch), Metal, Purity, Approx weight (gm), Making charges quote (₹), Stone requirements, Advance collected (₹), Balance due, Customer gold provided (gm — if customer sends own gold), Expected delivery date, Assigned to: own workshop/external karigar, Status (Booked/In work/Ready/Delivered/Cancelled), Customer notified (Y/N) | New — customer order management for retail
| 🆕 BUILD | 9 | Repairs & Remodeling (Retail) | Medium | Medium | Repair ID, Date received, Customer name, Mobile, Item: description/photo, Metal, Purity, Weight received (gm), Reported problem (Broken/Loose stone/Resize/Polish/Replating/Full remodel), Estimate given (₹), Customer approval (Y/N), Additional gold needed (gm), Gold source (Customer/Shop), Karigar assigned, Work done description, Additional charges (₹), Final weight (gm), Ready date, Customer sign-off, Delivery photo | New — essential retail service
| ✅ REUSE | 10 | Vendor & Supplier Process (Retail) | Low | Small | Reuse SwachERP Vendors screen as-is | Reuse: Vendors
| 🆕 BUILD | 11 | Customer Approval Management | Medium | Small | Approval ID, Customer name, Mobile, Date items given on approval, Items: (Tag No ¦ Design Code ¦ Weight gm ¦ Value ₹), Total value on approval (₹), Security deposit collected (Y/N), Deposit amount, Expected return date, Actual return (Y/N), Return date, Items returned: (Tag No ¦ Condition — Good/Damaged), Items purchased (convert to sale), Items not returned (follow-up flag), Overdue alert (>N days), Follow-up call log | New — jewellery retail specific — customers take items home to decide
| 🆕 BUILD | 12 | Order & Repair Booking | High | Small | Booking ID, Date, Customer, Mobile, Type (New order/Repair/Remodel/Resize/Stone setting), Quick capture: Voice memo / WhatsApp screenshot attach, Urgency (Normal/Urgent/VIP), Advance collected (₹), Receipt issued (Y/N), Assigned to technician, Expected ready date, Status (Booked/WIP/Ready/Collected), Customer reminder sent (WhatsApp/SMS), Counter staff name | New — quick booking counter screen
| 🔧 EXTEND | 13 | POS Management (Jewellery) | High | Large | Customer lookup (by name/mobile/loyalty ID), Customer profile: tier/points/outstanding, Item scan (barcode/RFID), Item: Tag No, Design Code, Metal, Purity, Gross weight, Net gold weight, HUID, Gold value (auto: weight × today's rate), Making charges, Stone charges, GST (auto), Total MRP, Multiple items in cart, Exchange old gold (weight/purity/value credited), Advance adjustment, Loyalty points redeem, Discount (if promotion active), Payment mode (Cash/Card/UPI/EMI/Part payment), Bill print, e-Invoice, Send bill on WhatsApp, Customer digital signature, Warranty card print | Extend: POS Terminal — complete jewellery billing overhaul
| 🆕 BUILD | 14 | Estimation (Quotation at Counter) | High | Small | Customer name (optional), Date, Design reference (catalogue/custom), Metal, Purity, Approx weight (gm), Today's gold rate (auto), Gold value (auto), Making charges (₹/gm — configurable), Stone charges, Wastage % (add-on), Hallmarking charges, GST (auto), Total estimate (₹), Valid for N hours (gold rate-linked), PDF download, Share on WhatsApp, Convert to order (button), Counter staff name | New — essential retail front desk tool
| 🆕 BUILD | 15 | Loyalty & Rewards Program | Medium | Medium | Programme tiers: (Silver/Gold/Platinum — auto-upgrade threshold ₹), Points earning: (₹ spent = X points, excluding gold value / on making charges only / on full value — configurable), Points redemption value (1 point = ₹X towards making charges), Tier benefits per level (priority service / free repair / gifting), Customer loyalty card (digital), Points expiry (N months), Birthday/anniversary bonus points, Redemption at POS (auto-deduct), Programme analytics (enrolled / active / points liability ₹) | New — essential for jewellery retail retention
| 🆕 BUILD | 16 | Gold Chit Schemes | High | Large | Scheme ID, Scheme Name, Duration (months: 11/15/22/30), Monthly instalment (₹), Total instalment value (₹), Bonus: (1 month free / Discount on making / Gift), Start date, End date, Member: Name, Mobile, Aadhaar, Bank account, Photo, Monthly collection register: (Month ¦ Due date ¦ Amount ¦ Collected date ¦ Mode ¦ Receipt No ¦ Status: Paid/Pending/Late), Total collected (₹), Total due (₹), Defaulter flag (>1 month pending), Maturity date, Maturity value (₹ + bonus), Redemption: Cash / Gold purchase / Making charge credit, Scheme analytics: Active/Matured/Defaulted/Foreclosed count | New — critical product, missing entirely from SwachERP
| 🔧 EXTEND | 17 | Credit & Debit Management | Medium | Small | Customer name, Credit limit (₹), Outstanding balance (₹), Overdue amount, Overdue days, Transaction history: (Date ¦ Invoice / Receipt ¦ Dr ¦ Cr ¦ Balance), Gold account balance (gm — if applicable), Credit limit alert, Block sales if overdue >N days (configurable), Statement download, Send statement on WhatsApp | Extend: Customer Advances + Credit Notes — add gold account
| 🆕 BUILD | 18 | Physical Inventory Control | High | Medium | Stock audit ID, Date, Branch/Location, Audit type (Full/Partial/Spot check), Auditor name, Stock as per system: (Tag No ¦ Design Code ¦ Metal ¦ Weight gm ¦ Location), Physical count: (Tag No found Y/N ¦ Actual weight gm ¦ Condition), Discrepancies: (Extra / Missing / Weight mismatch), Total system weight (gm), Total physical weight (gm), Discrepancy weight (gm), Discrepancy value (₹), Shrinkage % (alert if >0.1%), Approval by manager, Action taken (Adjust/Investigate), Next audit date scheduled | New — critical for theft prevention and accuracy
| 🔧 EXTEND | 19 | MIS & Sales Analytics (Retail) | Medium | Small | Date range, Branch, Sales by metal (22K/18K/Silver/Diamond), Revenue: gold value vs making charges split, Avg transaction value (₹), Pieces sold, Weight sold (gm), Making charges revenue (₹ — key margin metric), Gold scheme collections (₹), Repair/jobwork revenue (₹), Old gold purchases (gm + ₹), Exchange transactions, Top selling designs (by pieces/value), Slow movers (>60 days on display), Staff-wise sales performance, Customer acquisition vs repeat | Extend: MIS screens — add jewellery metrics
| 🆕 BUILD | 20 | Customer Buy-back Management | Medium | Small | Buy-back ID, Date, Customer name, Mobile, Item: Description, Metal, Purity, Gross weight (gm), Stone weight (gm), Net gold weight (gm), Our original invoice (linked if purchased from us), Original making charges paid, Buy-back rate (% of today's gold rate — configurable, e.g. 95%), Buy-back value (₹ auto: net weight × rate%), Deductions (damage/stone missing/etc.), Net offered to customer (₹), Customer acceptance (Y/N), Payment mode (Cash/Credit to account/Adjust against new purchase), Stock updated (Y/N), Refinery or resale flag | New — builds customer trust, industry standard
Bullion Trade | 🆕 BUILD | 1 | Bullion Booking & Inward Process | High | Medium | Booking ID, Date, Party type (Supplier/Bank/Bullion dealer), Party name, Metal (Gold/Silver/Platinum/Palladium), Form (Bar/Coin/Granule/Wire/Sheet), Fineness (999.9/999/995/916), Weight unit (gm/troy oz/kg), Quantity, Weight (gm), Rate agreed (₹/gm or USD/troy oz), Exchange rate (if USD), Amount (₹ auto), Delivery type (Physical/Allocated/Unallocated), Expected delivery date, Actual delivery date, Received weight (gm), Weight discrepancy, Assay certificate No, Certificate upload, Payment terms (Advance/Credit/RTGS), GST (3%), TDS if applicable | New — bullion-specific procurement
| 🆕 BUILD | 2 | Bullion Invoice & Rate Cuts | High | Medium | Invoice No, Date, Customer/Party, Metal, Form, Fineness, Weight invoiced (gm), Gross rate (₹/gm), Rate cut 1 (impurity deduction — ₹/gm or %), Rate cut 2 (wastage allowance — %), Rate cut 3 (refining charges — ₹/gm), Net rate after all cuts (₹/gm auto), Net amount (₹ auto), GST (3% on bullion — auto), Total invoice (₹), Payment received (Y/N), Due date, e-Way bill (for physical delivery), Download invoice PDF | New — rate cuts are unique to bullion trade
| ✅ REUSE | 3 | Receipts & Payments (Bullion) | Low | Small | Use SwachERP Invoice Payments screen — configure for bullion: enable weight field, 3% GST preset | Reuse: Invoice Payments
| 🔧 EXTEND | 4 | Logistics In / Out (Bullion) | High | Small | Movement ID, Date, Movement type (Inward/Outward), Party, Metal, Form, Weight (gm), Seal No / Box No, Armoured van / carrier name, Driver, Insurance policy No, Insured value (₹), e-Way bill No, Customs declaration (for import/export), Received by, Received at (vault/branch/refinery), Security seal intact (Y/N), GPS tracking ref (if applicable), Signature | Extend: Dispatch Tracking — add insurance/seal/customs fields
| 🆕 BUILD | 5 | Physical Inventory Control (Bullion Vault) | High | Medium | Vault audit ID, Date, Location (Vault A/B/Safe/Showroom), Auditors (min 2 required), Items: (Serial/Bar No ¦ Metal ¦ Fineness ¦ Weight gm ¦ Certificate No ¦ Verified Y/N ¦ Physical weight gm ¦ Variance gm), Total system weight (gm), Total physical weight (gm), Discrepancy (gm), Discrepancy value (₹), Seal check (intact Y/N), Tamper evidence, Photography (upload), Sign-off: 2 auditors + manager, Frequency (Daily/Weekly/Monthly), Alert if discrepancy >0.01 gm | New — vault-level accuracy critical
| ✅ REUSE | 6 | Vendor & Supplier Process (Bullion) | Low | Small | Use SwachERP Vendors — add: Bullion dealer licence No, RBI registered (Y/N), Assay lab | Reuse: Vendors
| ✅ REUSE | 7 | Customer Ledger (Bullion) | Low | Small | Use SwachERP Ledger View — add weight column alongside ₹ | Reuse: Ledger View
| 🆕 BUILD | 8 | Bullion Movement Tracking Dashboard | High | Medium | Live dashboard, Period filter, Total gold in (gm + ₹), Total gold out (gm + ₹), Current vault balance (gm + ₹ at today's rate), By location (Vault/Showroom/In transit/With karigar), By metal and form, Movement timeline (chart), Open bookings (delivery pending), In-transit consignments (map view if GPS), Rate exposure (total gold × today rate − purchase cost = unrealised P&L), Alerts: transit >24hrs, vault discrepancy, large movement pending approval | New — command centre for bullion
Gold Chit Schemes | 🆕 BUILD | 1 | Scheme Setup & Configuration | High | Small | Scheme ID, Scheme Name, Type (Fixed instalment/Gold weight accumulation), Duration (months), Monthly instalment (₹ or gm), Joining fee (₹), Bonus type (Free month/Making discount %/Gift/Gold coin), Bonus value, Max members per scheme batch, Start date, Auto-close date, Payment modes accepted (Cash/UPI/Bank), Late payment grace period (days), Late fee (₹ or %), Foreclosure penalty (%), Terms & conditions, Active (Y/N) | New — Gold Chit is unique to Indian jewellers
| 🆕 BUILD | 2 | Member Enrollment | High | Small | Enrollment ID, Scheme selected, Member Name, Mobile, Email, Aadhaar No, Photo, Address, Nominee name, Nominee relation, Bank account (for refunds), Monthly instalment amount (₹), First instalment date, Installment day of month (1st/5th/10th/etc.), Member agreement signed (Y/N), Agreement upload, Enrollment date, Staff who enrolled, Branch, Member ID / Scheme card No (auto), Welcome message sent (WhatsApp/SMS) | New
| 🆕 BUILD | 3 | Monthly Collection Register | High | Small | Scheme Name, Collection month, Members list: (Member ID ¦ Name ¦ Mobile ¦ Instalment amount ¦ Due date ¦ Paid date ¦ Mode: Cash/UPI/NEFT ¦ Receipt No ¦ Status: Paid/Pending/Late/Waived), Total collected (₹), Total pending (₹), Collection % (paid/total members), Defaulters count, Send reminder button (bulk WhatsApp/SMS), Daily collection summary by staff, Export to Excel | New
| 🆕 BUILD | 4 | Scheme Maturity Management | High | Small | Member ID, Name, Scheme, Start date, End date (maturity), Total instalments (count + ₹), Bonus (₹ or making discount %), Total maturity value (₹), Status (Approaching maturity / Matured / Redeemed), Reminder sent at: 60 days / 30 days / 10 days before maturity, Redemption options offered (Gold purchase / Cash / Extended scheme), Member response, Redemption processed (Y/N) | New
| 🆕 BUILD | 5 | Redemption (Gold / Cash / Purchase) | High | Small | Redemption ID, Member ID, Name, Scheme, Maturity amount (₹), Bonus (₹ or making credit ₹), Total redeemable (₹), Redemption type: Cash payout / Gold purchase (making charge credit applied) / Extend to new scheme, If gold purchase: Item selected (Tag No), Item value (₹), Making charges (after bonus discount), Gold rate on redemption date, Balance payable by customer (if any) or refund, Receipt issued, TDS deducted (if cash >₹10,000), Settlement complete (Y/N) | New
| 🆕 BUILD | 6 | Defaulter Management | Medium | Small | Defaulter ID, Member Name, Mobile, Scheme, Months paid, Months defaulted, Default amount (₹), Last paid date, Days since last payment, Action taken: (Date ¦ Action: Call/WhatsApp/Visit ¦ Response ¦ Next follow-up date), Foreclosure option offered (Y/N), Foreclosure value (paid amount − penalty), Legal notice issued (Y/N), Write-off flag (Y/N), Resolved (Y/N), Resolution type (Paid/Foreclosed/Written off) | New
| 🆕 BUILD | 7 | Scheme Reports & Analytics | Medium | Small | Period, Scheme-wise summary: (Scheme Name ¦ Active members ¦ Total collected ₹ ¦ Maturing this month ¦ Redeemed ¦ Defaulters), Cash flow from schemes (monthly bar chart), Upcoming maturities (next 3 months with ₹ value), Redemption trend (gold purchase % vs cash %), Scheme ROI for business (gold sold via scheme vs regular), Branch-wise collection, Staff-wise enrollment targets vs actual, Export to Excel / PDF | New
E-Catalog | 🆕 BUILD | 1 | Digital Catalogue Setup & Branding | Medium | Small | Catalogue ID, Catalogue name, Business name, Logo upload, Brand colours (primary/secondary hex), Catalogue URL / share link (auto-generated), Access type (Public link / Password protected / Time-based), Password (if protected), Expiry date/time (for time-based), Watermark text (e.g. 'Confidential — XYZ Jewellers'), Custom footer text, Default currency, Language (EN/Telugu/Hindi/Tamil), Active (Y/N) | New — B2B digital catalogue for jewellery
| 🔧 EXTEND | 2 | Category & Product Management | Medium | Small | Category: Name, parent category, display order, cover image; Product: Design Code, Name, Category, Metal, Purity, Weight range (min–max gm), Images (upload multiple — min 4 angles), 360° video upload, Stone details, Available in sizes (Ring sizes/Bangle sizes), Price display: Hide price / Show MRP / Show making charges only / Show range, Stock availability: Show/Hide/Show as Available if >0, Tags/labels (New arrival/Bestseller/Limited edition/On offer) | Extend: Product Categories + Products — add jewellery catalogue fields
| 🆕 BUILD | 3 | Customer Catalogue Sharing Portal | Medium | Medium | Share link generation (unique per customer or general), Customer receives: Branded catalogue view, Category browsing, Quick item lookup (search by name/code/purity), Multi-image view with interactive zoom, 360° product view, One-tap image sharing (WhatsApp/Email), Add to enquiry list, Submit enquiry (items + quantities + notes), Content protection: disable screenshot (where technically possible), Watermark on images, Secure access with OTP, Session time limit, View analytics: which customer viewed what for how long | New — critical B2B tool
| 🆕 BUILD | 4 | Shelf Stock Monitoring (Track & Refill) | Medium | Small | Product: Design Code, Category, Current stock (pieces + gm), Min display stock (configurable), Max display stock, Alert if stock < min (auto WhatsApp to manager), Refill required (Y/N), Last restocked date, Source (Own manufacture / Supplier / Transfer from HO), Reorder trigger, Fast-moving items (refill frequently), Dead stock (no enquiry in >30 days), Catalogue visibility auto-hidden if stock = 0 (configurable) | New
| 🆕 BUILD | 5 | Catalogue Analytics | Medium | Small | Period filter, Catalogue views (total), Unique viewers, Most viewed categories, Most viewed items (Top 20 by views), Most shared items, Enquiries received (count + items), Conversion rate (enquiry to order %), Customer-wise engagement: (Customer ¦ Views ¦ Time spent ¦ Items viewed ¦ Enquiries raised), Catalogue sent vs opened vs acted, Export report | New
OMS | 🆕 BUILD | 1 | Online Order Booking Portal | High | Large | Customer login (mobile OTP), Customer profile, Browse: Category → Metal → Purity → Designs, Filter: price range / weight range / purity / style, Product page: multiple images, 360° view, weight, making charges, today's gold rate, estimated total price (live-updated), Customisation notes (size/colour/stone preference), Add to cart, Cart summary, Order notes (free text), Advance payment (online gateway), Order confirmation (SMS/WhatsApp/Email), Mobile + desktop responsive | New — customer-facing jewellery ordering
| 🆕 BUILD | 2 | Live Product Availability Display | High | Small | Real-time stock sync from ERP, Display: In stock / Made to order (N days) / Not available, Stock depletes in cart if others book same item, Pre-order option (Y/N — configurable per item), Notify me when available (WhatsApp/SMS opt-in), ETA for made-to-order items (from production planning auto-calculated) | New
| 🆕 BUILD | 3 | Order Tracking Dashboard (Customer) | High | Small | Customer login, My orders: (Order ID ¦ Date ¦ Items ¦ Status ¦ Est delivery ¦ Actions), Order status timeline: Booked → Design confirmed → In production → Quality check → Ready → Dispatched → Delivered, WhatsApp notification at each stage, Live location tracking (if courier integrated), Estimated delivery date (updated dynamically), Raise issue button (if problem with order), Download invoice | New — customer transparency
| 🔧 EXTEND | 4 | Order History with Status | Medium | Small | Extend SwachERP Sales Orders — add: Customer portal visible (Y/N), Production stage (live), WhatsApp notification log, Customer review/rating after delivery | Extend: Sales Orders
| ✅ REUSE | 5 | Customer Ledger (OMS) | Low | Small | Reuse SwachERP Ledger View for customer order advances and payments | Reuse: Ledger View
| 🔧 EXTEND | 6 | SMS / WhatsApp Alerts (OMS) | Medium | Small | Extend SwachERP's central WhatsApp service — add OMS triggers: Order placed / Production started / Ready for pickup / Dispatched / Delivered / Payment due / Scheme instalment due | Extend: WhatsApp central service
E-Commerce | 🆕 BUILD | 1 | Jewellery Online Store Setup | High | Large | Store name, Domain/subdomain, Logo + branding, Store currency (INR/USD/AED/etc.), Default language + multi-language toggle, Gold rate source (MCX/IBJA/Manual), Rate update frequency (Every 15 min / Hourly / Manual), Making charges display: Included in price / Shown separately, Price validity message ('Price valid for next 30 minutes — gold rate linked'), Shipping zones + rates, COD available (Y/N), Return policy text, Terms & conditions, SEO meta fields, Google Analytics integration, WhatsApp chat widget | New — jewellery e-commerce is unique due to live gold pricing
| 🆕 BUILD | 2 | Product Catalog with Metal Rate Pricing | High | Medium | Design Code, Product name, Category, Metal, Purity, Weight (gm), Making charges (₹/gm — stored), Stone charges (₹ — stored), Today's gold rate (live), Auto-calculated selling price (weight × rate + making + stone + GST), Price updates live as gold rate changes, Image gallery (multiple angles), 360° view, Weight range display, Customisation available (Y/N), Stock: In stock / Made to order, Certification: BIS hallmarked / IGI certified / GIA certified | New — core differentiator for jewellery e-commerce
| 🆕 BUILD | 3 | Live Gold Rate Price Calculator | High | Small | Visible widget on all product pages and homepage, Inputs: Metal (Gold/Silver), Purity (24K/22K/18K/Silver 925), Weight (gm) — editable, Making charges %, Output: Gold value (₹), Making charges (₹), GST (₹), Total estimate (₹), Rate source and timestamp shown ('MCX rate as of HH:MM'), 'Rate valid for N minutes' countdown, 'Get exact quote' button (links to enquiry/order form), Embeddable on WhatsApp link | New — mandatory for jewellery e-commerce trust
| 🆕 BUILD | 4 | Cart, Checkout & Quote Request | High | Medium | Cart: Items (image, name, weight, live price — updates every refresh), Remove item, Update quantity, Apply coupon/offer, Estimated total (live-updated with gold rate), Quote request option (instead of direct buy — generates PDF quotation), Checkout: Delivery address, Shipping method, Payment: Razorpay/PayU/COD/Bank transfer/Gold scheme balance, Order summary with rate lock timestamp, Place order confirmation, EMI option display (if enabled) | New
| 🆕 BUILD | 5 | Customer Registration & Wishlist | Medium | Small | Registration: Name, Mobile (OTP), Email, Birthday/Anniversary (for reminders), City, Preferred metal/purity, Newsletter opt-in, Login: Mobile OTP / Google / Email+password, Wishlist: Add/remove items, WhatsApp share wishlist (for gifting), Price drop alert (if gold rate falls, notify wishlist items are cheaper), Saved cart, Order history, My account dashboard, Gold rate history chart, Loyalty points balance | New
| 🔧 EXTEND | 6 | Offer & Coupon Management | Medium | Small | Extend: existing CRM/Promotions — add e-commerce coupon codes: FLAT discount / % on making charges / Free shipping / Gift on order above ₹X, Coupon: single-use / multi-use / customer-specific, Track redemption, Expiry date | Extend: Promotions & Rewards Setup
| 🔧 EXTEND | 7 | ERP Sync Dashboard | Medium | Small | Orders from e-commerce → auto-create in SwachERP Sales Orders, Stock from SwachERP → auto-update e-commerce availability, Customer data synced, Payment reconciliation, Sync status: (Last sync ¦ Orders synced ¦ Stock updates ¦ Errors), Manual sync trigger | Extend: Existing channel sync concept
RFID | 🆕 BUILD | 1 | RFID Tagging & Encoding Station | High | Large | Tag ID (auto-encoded), EPC code (assigned), Item linked: Design Code, Tag No/Barcode, Metal, Purity, Weight gm, HUID, Encoding station (printer/encoder device), Tag type (UHF RFID / HF NFC), Tag placement (on item / on tag card), Encoding date, Encoded by, Verification scan (confirm tag reads correctly), Failed encoding log, Tags encoded today (count), Batch encode (multiple items), Link to inventory auto (Y/N) | New — hardware integration required: RFID encoder
| 🆕 BUILD | 2 | Bulk Inventory Scanning | High | Large | Scan session ID, Date, Location (Showroom/Vault/Safe/Showcase No), Scanner device ID, Scan start time, Scan end time, Items detected: (Tag ID ¦ Design Code ¦ Description ¦ Metal ¦ Weight gm ¦ Status: Found/Missing/Extra), Total expected (system), Total scanned (physical), Matched (count + gm), Missing (count + gm + value ₹), Extra (count — investigate), Discrepancy report, Auto-alert if missing items >0, Export scan report, History of scan sessions | New — hardware integration: handheld RFID scanner
| 🔧 EXTEND | 3 | Inward & Outward Movement Tracking (RFID) | High | Medium | RFID gate reader at entry/exit, Auto-detect items passing gate, Movement entry: Date/time, Direction (In/Out), Items: (Tag ID ¦ Design Code ¦ Weight gm), Associated GRN/Invoice/Transfer, Authorised movement (Y/N), Unauthorised alert (item leaving without invoice/transfer), Dashboard: items in showroom vs vault vs safe vs in transit | Extend: Stock Transfers — add RFID gate auto-detection
| 🆕 BUILD | 4 | Packing & Dispatch Validation (RFID) | High | Medium | Dispatch ID, Customer/Invoice linked, Expected items to pack: (Tag ID ¦ Design Code ¦ Weight gm), Scan items into package (RFID scan one by one or bulk), Validation: All expected items scanned? (Green=Yes / Red=Missing), Extra items detected (alert), Total weight packed (auto sum gm), Package sealed, Seal No recorded, Final scan count matches invoice (Y/N), Dispatch authorised, Exception override (requires manager password), Packing photos | New — eliminates dispatch errors
| 🆕 BUILD | 5 | Anti-Theft & Security Alerts | High | Large | Alert types: (Unauthorised exit — item leaving without invoice ¦ Ghost item — tag not in system ¦ Missing item — was in location, now not found ¦ Tampered tag — tag damaged/removed ¦ Unusual movement — item moved outside business hours), Alert log: (Date/time ¦ Alert type ¦ Item: Tag ID/Code/Description/Weight ¦ Location ¦ Triggered by ¦ Acknowledged by ¦ Action taken ¦ Resolved Y/N), Real-time push alert (app/SMS to manager), CCTV timestamp reference (if integrated), False alarm tracking | New — requires RFID gate readers and server integration
| 🆕 BUILD | 6 | Live RFID Dashboard & Reports | High | Medium | Live stock map: items by location (Showroom: Showcase 1–10, Vault, Safe, Counter), Item heatmap: which showcases have most/least stock, Real-time weight in each location (gm), Value by location (₹ at today's rate), Last full scan date per location, Alerts active count, Scan accuracy % (scanned vs system), Items not scanned in >N days, Reports: Daily movement log, Weekly discrepancy, Missing items history, RFID utilisation (% of stock tagged), Export CSV | New
| 🆕 BUILD | 7 | Mobile & Handheld RFID Scanner App | High | Large | Login with employee ID + PIN, Select mode: Spot check / Full audit / Packing scan / Single item lookup, Point and scan (camera + RFID reader), Scanned item details (name, weight, location, status — instant display), Flag item (missing/damaged/misplaced), Add note, Multi-scan session (accumulate list), Submit session (syncs to ERP), Works offline (queues and syncs), Battery-efficient scanning mode, Print label (if Bluetooth printer connected) | New — requires mobile app + RFID hardware
Business Analytics | 🔧 EXTEND | 1 | Live Stock Value Dashboard | High | Small | Total pieces in stock (count), Total gross weight (gm), Total net gold weight (gm), Today's gold rate (live), Live stock value (₹ = net gold weight × rate), Making charges embedded in stock (₹), Total stock value (gold + making), By metal/purity breakdown, By category breakdown, Stock value trend (30-day chart), Compare with yesterday/last week/last month, Branch-wise stock value, Alert if stock value crosses threshold | Extend: MIS Inventory — add weight/value live calculations
| 🆕 BUILD | 2 | Making Charge & Wastage Trends | High | Small | Period, Making charges collected (₹) — by category/metal, Making charge % of total revenue, Wastage generated (gm) by karigar/department, Wastage as % of gold issued, Refinery recovery % (refined gold returned/wastage sent), Month-on-month wastage trend, Karigar-wise wastage ranking (best to worst), Alert if karigar wastage >X% above average, Cost per gram of making by design category, Margin on making charges | New — key profitability metric for jewellers
| 🆕 BUILD | 3 | Item-wise & Tag-wise Insights | Medium | Small | Each item (tag): days in stock, views/enquiries (if RFID/catalogue), sold/unsold, rate of return (repurchased by customers), Bestsellers (by pieces/weight/revenue — last 30/90/365 days), Slow movers (>60 days unsold — with value at risk), Category performance (turnover ratio: sold/average stock), Design lifecycle (from production to sale — avg days), Re-order suggestions (designs selling fast, low stock) | New
| 🆕 BUILD | 4 | Weight & Purity Loss Reports | High | Small | Gold issued to karigar (gm), Gold returned in pieces (gm), Wastage collected (gm), Refinery send (gm), Refinery received (gm), Net loss (gm = issued − returned − collected + not yet recovered), Loss % (alert if >2%), Purity variance: issued purity vs received purity, Value of loss (₹ at market rate), Loss by karigar (accountability), Loss by process stage (casting/filing/polish), Month-on-month loss trend, Acceptable loss benchmark (configurable) | New — critical for gold business profitability
| 🔧 EXTEND | 5 | Job Work & Production Analytics | Medium | Small | Extend: Variance Analytics — add: Job completion rate (on-time %), Avg production days by design type, Karigar efficiency (pieces/gm output per day), Rework rate (QC failures %), Wastage per production order, Most efficient karigar (by output/wastage ratio), Production cost vs selling price margin | Extend: Variance Analytics
| 🔧 EXTEND | 6 | Customer Behaviour Analytics | Medium | Small | Extend: MIS Sales — add: Avg purchase frequency (orders/year), Avg order value (₹), Metal preference (% customers by 22K/18K/Silver/Diamond), Occasion-based buying (festival/wedding/birthday), Gold scheme participation %, Repair vs new purchase ratio, Lapsed customers (no purchase in >6 months), Top 100 customers by revenue | Extend: MIS Sales
| 🔧 EXTEND | 7 | Sales Performance Analytics | Medium | Small | Extend: MIS Sales — add: Revenue split: gold value vs making charges vs stone charges, Gross margin % (making charges/total revenue), Sales by counter staff, Peak hours/days (hourly heatmap), Walk-in to sale conversion %, Scheme-led sales %, Festival season performance comparison | Extend: MIS Sales
| 🔧 EXTEND | 8 | Billing & Margin Reports | Medium | Small | Extend: Financial Analytics — add: Making charges margin by category, Stone charges margin, Bullion trade margin (sell rate − buy rate), Total gold traded (gm/period), Avg buying rate vs avg selling rate (margin ₹/gm), Revenue per square foot (retail), Cost of unsold inventory (opportunity cost) | Extend: Financial Analytics
| 🔧 EXTEND | 9 | Purchase & Vendor Insights | Low | Small | Extend: Vendor Analytics — add: Gold purchased (gm by supplier), Avg purchase rate vs MCX rate (premium/discount %), Supplier quality score (rejection rate %), Lead time reliability, Payment terms compliance, Top 5 suppliers by volume | Extend: Vendor Analytics
| 🆕 BUILD | 10 | Movement & Transfer Tracking | Medium | Small | Period, Branch-wise stock movement: (Sent gm ¦ Received gm ¦ Net change gm), Transfer efficiency (arrived complete Y/N), Items in transit currently (count + gm + value), Lost/damaged in transit (history), Karigar-wise material movement (issued/returned tracking), Refinery movement log (sent/received timeline), e-Way bill compliance (% transactions with e-way bill generated), Insurance coverage on movements | New
Finance (Jewellery) | 🆕 BUILD | 1 | Metal-Based Accounting (Gold/Silver/Platinum) | High | Large | Parallel weight ledger alongside ₹ ledger — every transaction records: ₹ amount + metal weight gm + purity, Account types: Gold stock account (gm), Gold purchase account (gm + ₹), Gold sales account (gm + ₹), Karigar payable (gm + ₹), Refinery account (gm), Wastage account (gm), Metal P&L: unrealised gain/loss (current stock weight × (today's rate − avg purchase rate)), Trial balance with weight column, Journal entries with weight field, Day book shows both ₹ and gm | New — most critical and complex build, fundamental for gold accounting
| 🆕 BUILD | 2 | Multi-Branch Gold Stock Consolidation | High | Medium | HO consolidated view: All branches + main vault, Total gold in organisation (gm by purity), Total gold value (₹ at live rate), Unrealised P&L (total stock value − total purchase cost), Branch-wise breakdown: (Branch ¦ Gold in stock gm ¦ With karigar gm ¦ In transit gm ¦ Total gm ¦ Value ₹), Intercompany transfers (gm reconciliation), Daily closing gold position report (regulatory requirement for large dealers), Export to PDF/Excel | New
| 🆕 BUILD | 3 | Metal Rate-Based P&L | High | Medium | Period P&L with jewellery-specific lines: Revenue: Gold sales (₹) ¦ Making charges (₹) ¦ Stone charges (₹) ¦ Repair/jobwork (₹) ¦ Gold scheme income (₹) ¦ Bullion trading margin (₹), COGS: Gold purchase cost (gm × avg rate), Gross margin: Making charges + other non-gold revenue, Inventory holding gain/loss (stock at period-end rate vs purchase rate), Wastage cost (gm × rate), Refinery loss (gm × rate), Metal-adjusted net profit | New — fundamental for gold business profitability understanding
| 🆕 BUILD | 4 | Weight & Purity Loss P&L Impact | High | Small | Period, Total gold issued (gm), Total gold recovered in products (gm), Total wastage sent to refinery (gm), Total refined gold received (gm), Unaccounted loss (gm = issued − products − refinery received), Unaccounted loss value (₹ = gm × gold rate), This goes to: Wastage expense account (P&L debit), Purity downgrade loss: items sold at lower purity than expected — rate difference × weight = loss (₹), Total metal loss impact on P&L (₹), Benchmark: acceptable loss % × total gold processed = benchmark loss | New
| 🔧 EXTEND | 5 | Cash Flow & Fund Flow (Jewellery) | Medium | Small | Extend: Cash Flow Statement — add: Gold scheme collections (₹ inflow), Gold purchases — cash outflow, Bullion trading cash flow, Karigar payments — cash outflow, Refinery payments/receipts, Large cash transactions flagged (>₹2L — Income Tax reporting required), Gold loan disbursement/collection (if gold loans offered) | Extend: Cash Flow Statement — add jewellery cash flow lines

## 🆕 Build List (Developer View)
Sub-Module | # | Screen Name | Priority | Effort | UI Fields / Columns
Production | 1 | [EXTEND] Production Planning | High | Medium | Work Order No (auto), Design Ref, Item Type (Ring/Necklace/Bangle/etc.), Metal, Purity, Quantity (pieces), Target weight per piece (gm), Total gold required (gm), Raw material check (Green=available/Red=short), Assigned karigar / department, Planned start date, Planned end date, Priority (Urgent/Normal), Linked customer order, Current stage (live), Status (Planned/In progress/Completed/Cancelled), Notes
Production | 2 | [BUILD] Master Design Library | High | Medium | Design Code (auto), Design Name, Category (Ring/Necklace/Bangle/Earring/Pendant/Bracelet/Set), Sub-category, Metal (Gold/Silver/Platinum), Purity, Style (Plain/Filigree/Casting/Handmade/Antique/Kundan/Meenakari/Diamond/CZ), Sketch image upload (multiple), CAD file attachment, Standard weight range (min–max gm), Stone details (type/shape/size/count), Making charges (₹/gm or ₹/piece), Selling price formula, Active (Y/N), Created by, Version history
Production | 3 | [BUILD] Sketch Process | High | Small | Job ID, Design Code (linked), Sketch artist name, Sketch date, Customer design brief (text + reference images uploaded), Sketch version (v1/v2/v3), Sketch images (upload multiple), Customer approval status (Pending/Approved/Revision requested), Revision notes, Approved by, Approved on, Proceed to CAD (button)
Production | 4 | [BUILD] CAD Process | High | Medium | Job ID, Design Code, CAD operator name, Software used (RhinoGold/Matrix/JewelCAD/3Design), CAD file upload (.3dm/.stl/.obj), CAD version, Weight estimate from CAD (gm), Metal volume (cc), Render images (upload multiple), Customer approval status, Revision notes, Stone placement verification (Y/N), Approved by, Approved on, Send to CAM (button), Estimated production cost (auto from weight × rate)
Production | 5 | [EXTEND] Design Approvals | Medium | Small | Approval ID, Job ID, Design Code, Stage (Sketch/CAD/Sample), Submitted by, Submitted on, Submitted to (customer/internal), Customer name, Approval method (In-person/WhatsApp/Email/Portal), Status (Pending/Approved/Revision/Rejected), Revision count, Comments, Approved by, Approved on, Attach approved file
Production | 6 | [BUILD] CAM Process | High | Medium | Job ID, CAM operator, CAM software (SprutCAM/Fusion 360/Custom), Milling/printing machine, Material for prototype (Wax/Resin/Metal), CAM file upload, Estimated time (hrs), Actual time (hrs), Output: prototype weight (gm), Prototype images, Quality check on prototype (Y/N), Issues noted, Proceed to tree setup (button)
Production | 7 | [BUILD] Tree Setup (Casting Tree) | High | Medium | Tree ID (auto), Job ID, Metal, Purity, Sprue/tree wax weight (gm), Items attached to tree: (Design Code ¦ Qty pieces ¦ Each weight gm ¦ Total weight gm), Total wax tree weight (gm), Gold required for casting (calculated: weight × density × purity factor), Casting alloy additions (if any), Tree photo upload, Approved by, Date, Casting operator assigned
Production | 8 | [BUILD] Ghat Process (Weighing & Assaying) | High | Small | Ghat Entry ID, Date, Job ID, Stage (Pre-casting / Post-casting / Post-polish / Final), Operator name, Item description, Gross weight (gm), Stone weight deduction (gm), Net metal weight (gm), Purity tested (touchstone/XRF/acid test), Purity % result, Expected purity %, Variance (%), Alert if variance >0.5%, Alloy composition (if tested), Weighing scale ID / calibration date, Witnessed by
Production | 9 | [BUILD] Material Management (per Job) | High | Small | Job ID, Date, Material type (Gold / Silver / Solder / Alloy / Chemicals / Consumables), Material issued (gm / qty), Issued from stock (location), Issued by, Issued to (karigar/department), Purpose (Casting/Repair/Plating/Polishing), Material returned (gm / qty), Net consumed (gm auto), Variance vs BOM (gm), Variance reason, Stock balance updated (Y/N)
Production | 10 | [BUILD] Casting Process | High | Medium | Casting ID, Date, Job ID / Tree ID linked, Furnace / casting machine, Operator, Metal poured (gm), Alloy added (gm), Total melt weight (gm), Casting method (Vacuum / Centrifugal / Gravity), Temperature (°C), Casting time (mins), Quench method (Water/Air), Raw casting weight (gm), Casting tree removed (Y/N), Sprue cut weight (gm — returned to stock), Net casting weight (gm), Visual inspection (Pass/Fail), Issues (Porosity / Shrinkage / Incomplete fill / Other), Re-cast required (Y/N)
Production | 11 | [BUILD] Filing & Buffing | Medium | Small | Job ID, Operator name, Date, Input weight (gm — from casting), Filing tools used, Buffing wheel type, Filing dust collected (gm), Buffing dust collected (gm), Total wastage collected (gm), Output weight (gm after filing), Visual check (surface finish — Pass/Fail), Issues noted, Time taken (mins), Move to: Fitting / Stone setting / Polish
Production | 12 | [BUILD] Fitting Process | Medium | Small | Job ID, Fitting operator, Date, Input weight (gm), Items to fit: (Component ¦ Type: Clasp/Hook/Ear-pin/Ring shank/Bail ¦ Weight gm ¦ Soldered Y/N), Solder used (gm — goes to wastage), Post-fitting weight (gm), Strength test (Pass/Fail), Visual check (Pass/Fail), Issues, Time taken (mins), Move to: Stone setting / Polish
Production | 13 | [BUILD] Polish Process | Medium | Small | Job ID, Polish operator, Date, Input weight (gm), Polish type (Mechanical/Electrolytic/Hand), Polishing compound used (type + gm), Rhodium plating (Y/N), Rhodium weight (gm — if plated), Polish dust / slurry collected (gm — to wastage), Output weight (gm), Finish quality (Mirror/Matte/Satin/Antique), Visual check (Pass/Fail), Issues, Time taken (mins), Move to QC
Production | 14 | [EXTEND] Quality Check (Jewellery) | High | Small | QC Entry ID, Job ID, QC inspector, Date, Item: Design Code, Metal, Purity, Weight (gm), Checks: (Purity verified Y/N ¦ Finish quality Pass/Fail ¦ Stone set securely Y/N ¦ Dimensions as per design Y/N ¦ HUID verified Y/N ¦ No cracks/porosity Y/N ¦ Clasp/closure function Y/N ¦ Customer design match Y/N), Overall Result (Pass/Fail/Rework), Rework instructions, Rework karigar assigned, Re-QC date, Final approval (Y/N), Move to finalize
Production | 15 | [BUILD] Job Finalize & Barcode | High | Small | Job ID, Finalize date, Design Code, Metal, Purity, Final weight (gm), Stone details (if any), HUID No (BIS hallmark — enter or scan), Barcode / Tag No (auto-generated), Tag type (RFID/Barcode), Tag printed (Y/N), Print tag button, Photo of finished item (upload), Certificate of authenticity (auto-generate), Move to finished goods stock (button), Linked to customer order (Y/N), Ready for dispatch (Y/N)
Production | 16 | [BUILD] Settlement | High | Medium | Settlement ID, Job ID, Design Code, Customer (if made-to-order), Settlement date, Gold issued (gm), Gold returned in piece (gm), Wastage collected (gm: filing dust + polish dust + casting sprue), Total accounted gold (gm auto), Unaccounted gold (issued − returned − wastage — should be 0), Karigar making charges (₹), Deductions (excess wastage × gold rate), Net payable to karigar (₹), Settlement mode (Cash/Bank), Settled (Y/N), Settlement date, Approved by
Production | 17 | [EXTEND] Worker Material Management | Medium | Small | Worker/Karigar Name, Date, Gold in hand (current — gm), Pending jobs (count), Material issued today: (Job ID ¦ Material ¦ Weight gm), Material returned today: (Job ID ¦ Material ¦ Weight gm), Accumulated wastage collected (gm), Net gold balance with worker (gm), Alert if gold in hand >X gm for >Y days, Tools issued (list), Tool condition, Payment advance given (₹)
Production | 18 | [BUILD] Jobwork Register (Karigar) | High | Medium | Job Work ID, Issue date, Karigar name, Trade (Goldsmith/Stone setter/Polisher/Fitter/Engraver), Design Code, Production Order No, Metal issued (gm), Purity, Stones issued (type/qty/carats), Findings issued, Expected return date, Actual return date, Metal returned in piece (gm), Stones returned (Y/N), Allowed wastage % (by trade), Allowed wastage gm (auto), Actual wastage gm (issued − returned), Excess wastage gm (actual − allowed), Excess wastage deduction (₹ = excess × gold rate), Making charges (₹), Net payable, Payment status
Wholesale | 1 | [EXTEND] Order Booking (Wholesale) | High | Small | Order No (auto), Order date, Customer (retailer/wholesaler), Customer GST, Design Code / Catalogue reference, Item description, Metal, Purity, Qty (pieces), Approx weight per piece (gm), Making charges agreed (₹/gm), Stone charges (if any), Advance paid (₹), Payment terms, Delivery date, Special instructions, Sketch / reference image attached, Production order auto-created (Y/N), Order status (Booked/In production/Ready/Dispatched)
Wholesale | 2 | [BUILD] Jobwork Processing (Wholesale) | High | Medium | Jobwork ID, Customer name, Date received, Customer gold received (gm, purity — customer sends own gold), Design Code, Qty pieces, Making charges agreed (₹/gm or ₹/piece), Stone setting charges, Timeline, Gold issued to karigar (from customer account), Production tracking (same as production flow), Finished pieces (gm), Customer gold balance (gm auto), Invoice: making charges only (not gold value), Customer approval required (Y/N), Ready for delivery
Wholesale | 3 | [EXTEND] Inventory Inward (Wholesale) | High | Small | GRN No (auto), Date, Supplier, Invoice No, Item: Design Code, Metal, Purity, Gross weight (gm), Stone weight (gm), Net gold weight (gm), HUID No, Barcode No, Rate (₹/gm), Making charges (₹), Stone value (₹), Total value (₹), QC done (Y/N), Storage location, Certificate attached, Tag printed (Y/N)
Wholesale | 4 | [EXTEND] Barcode & Inventory (Wholesale) | High | Small | Item Tag No / Barcode, Design Code, Description, Metal, Purity, Gross weight (gm), Net gold weight (gm), Stone details, HUID No, Location (showcase/vault/safe), Status (Available/On approval/Sold/On repair/In transit), Gold value (auto: net weight × today's rate), Making charges, Total value, Customer holding (if on approval), Days in stock, Movement history
Wholesale | 5 | [BUILD] Remodeling & Repair Process | Medium | Medium | Repair/Remodel ID, Date received, Customer name, Item description, Metal, Purity, Weight received (gm), Issue reported (Broken clasp/Resizing/Stone reset/Polish/Full remodel), Customer instructions, Photo on receipt (upload), Additional gold required (gm), Additional gold source (Customer provides/We supply), Making charges (₹), Estimated delivery date, Karigar assigned, Status (Received/In work/Ready/Delivered), Final weight (gm), Final photo, Customer sign-off
Wholesale | 6 | [BUILD] Bullion Transactions (Wholesale) | High | Medium | Transaction ID, Date, Transaction type (Purchase/Sale/Exchange/Rate cut), Party name, Metal (Gold/Silver/Platinum), Purity (999/995/916/875/etc.), Form (Bar/Coin/Granule/Scrap), Weight (gm / troy oz / kg), Rate agreed (₹/gm), Agreed rate date, Rate source (MCX/IBJA/Negotiated), Amount (₹ auto), Rate cut (₹ — discount for impurity), Net amount, Payment mode, Tax (GST — 3% on bullion), e-Way bill required (Y/N), Assay certificate attached
Wholesale | 7 | [EXTEND] Inventory & Distribution Transfers | Medium | Small | Transfer ID, Date, From branch/location, To branch/location, Items: (Tag No ¦ Design Code ¦ Metal ¦ Purity ¦ Weight gm ¦ Value ₹), Total weight transferred (gm), Total value (₹), Transfer type (Sale/Stock movement/Approval/Return), Transit insurance (Y/N), Insured value, Vehicle/courier, Driver, E-way bill No, Received by, Received on, Discrepancy (Y/N), Discrepancy weight (gm)
Wholesale | 8 | [EXTEND] Quotation Engine | Medium | Small | Quotation No, Date, Valid till, Customer, Item: Design Code, Metal, Purity, Weight (gm), Today's gold rate (auto from MCX), Gold value (auto: weight × rate), Making charges (₹/gm or ₹/piece), Stone charges, Wastage % (add-on), Hallmarking charges, Packaging, GST (3% on gold value), Total quotation value (₹), Margin % (internal view only), Convert to order (button), Download PDF, Share on WhatsApp
Wholesale | 9 | [BUILD] Line-wise Sales & Inventory | Medium | Medium | Line / Product category (22K Plain / 18K Diamond / Silver / etc.), Opening stock (pieces + gm), Inward (pieces + gm), Sales (pieces + gm), Returns (pieces + gm), Closing stock (pieces + gm), Closing gold value (₹ auto at today's rate), Stock aging (0–30 / 31–60 / 60–90 / 90+ days), Fast-moving designs (top 10 by pieces), Slow-moving (>60 days unsold), Reorder suggestion, Filter by branch / date
Wholesale | 10 | [EXTEND] Sales & Dispatch Process | High | Small | Invoice No, Date, Customer, Items: (Tag No ¦ Design Code ¦ Metal ¦ Purity ¦ Gross wt gm ¦ Net gold wt gm ¦ HUID ¦ Making charges ¦ Gold value ¦ Total), Total weight (gm), Total invoice value (₹), GST breakup (3% on gold / 5% on making), E-way bill No, Delivery challan No, Transit insurance (Y/N), Insured value (₹), Vehicle No / courier, Customer signature on receipt, Payment received (Y/N)
Wholesale | 11 | [BUILD] Quality Testing & Hallmarking | High | Medium | Batch ID, Date, Items submitted: (Tag No ¦ Design Code ¦ Metal ¦ Claimed purity ¦ Weight gm), Submitted to hallmarking centre, BIS licence No of centre, Date submitted, Testing method (XRF/Acid/Cupellation), Tested purity (result), HUID assigned (per piece), Date received back, Rejected pieces (reason), Hallmark certificate upload, Update item tag (auto-links HUID to barcode/RFID), Cost (₹/piece × qty), Batch summary report
Retail | 1 | [EXTEND] Inventory Inward (Retail) | High | Small | Same as Wholesale Inventory Inward — with additional: Branch/store received at, Source (Own manufacture/External supplier/HO transfer), Showcase placement (Showcase No / Tray No), Customer-facing tag updated (Y/N)
Retail | 2 | [EXTEND] Barcode & Inventory (Retail) | High | Small | Same as Wholesale Barcode & Inventory — add: Showcase No, Tray No, Customer-visible display price (gold value + making), Walk-in customer enquiry count (if RFID), Days on display
Retail | 3 | [BUILD] Quality Testing & Hallmarking (Retail) | High | Small | Same as Wholesale Quality Testing & Hallmarking — built once, used by both
Retail | 4 | [BUILD] Bullion Transactions (Retail) | Medium | Small | Same as Wholesale Bullion Transactions — Customer old gold purchase (rate cut applied), Bullion sale to customer (coins/bars), Exchange transaction
Retail | 5 | [EXTEND] Inventory Transfer & Distribution | Medium | Small | Same as Wholesale Inventory Transfers — add: Triggered by HO / self-initiated, Approval required for transfers >X gm
Retail | 6 | [BUILD] Promotions & Rewards Setup | Medium | Small | Promotion ID, Name, Type (Making charge waiver / Flat discount / Gift on purchase / Gold coin on purchase / Double points), Applicable categories (All/22K/18K/Silver/Diamond/etc.), Min purchase value / weight, Discount value or %, Valid from/to, Applicable branches (All/specific), Customer segment (All/Gold member/Platinum), Stackable with loyalty points (Y/N), Terms & conditions, Active toggle, Usage count, Budget allocated (₹)
Retail | 7 | [BUILD] Refining Process (Retail) | Medium | Medium | Refinery Entry ID, Source (Customer old gold / Workshop wastage / Returned goods), Customer name (if customer gold), Item description, Gross weight received (gm), Assay result (purity %), Net fine gold (gm), Refinery name, Date sent, Date received, Refined gold (gm), Recovery % (received/sent), Loss (gm), Loss within acceptable % (Y/N), Refined gold credited: Customer account / Own stock, Payment to/from customer (₹ if applicable), Certificate upload
Retail | 8 | [BUILD] Order & Jobwork Process (Retail) | High | Medium | Order ID, Customer name, Mobile, Date, Order type (New design/Remodel/Repair/Stone change/Resizing), Design reference (catalogue/custom sketch), Metal, Purity, Approx weight (gm), Making charges quote (₹), Stone requirements, Advance collected (₹), Balance due, Customer gold provided (gm — if customer sends own gold), Expected delivery date, Assigned to: own workshop/external karigar, Status (Booked/In work/Ready/Delivered/Cancelled), Customer notified (Y/N)
Retail | 9 | [BUILD] Repairs & Remodeling (Retail) | Medium | Medium | Repair ID, Date received, Customer name, Mobile, Item: description/photo, Metal, Purity, Weight received (gm), Reported problem (Broken/Loose stone/Resize/Polish/Replating/Full remodel), Estimate given (₹), Customer approval (Y/N), Additional gold needed (gm), Gold source (Customer/Shop), Karigar assigned, Work done description, Additional charges (₹), Final weight (gm), Ready date, Customer sign-off, Delivery photo
Retail | 10 | [BUILD] Customer Approval Management | Medium | Small | Approval ID, Customer name, Mobile, Date items given on approval, Items: (Tag No ¦ Design Code ¦ Weight gm ¦ Value ₹), Total value on approval (₹), Security deposit collected (Y/N), Deposit amount, Expected return date, Actual return (Y/N), Return date, Items returned: (Tag No ¦ Condition — Good/Damaged), Items purchased (convert to sale), Items not returned (follow-up flag), Overdue alert (>N days), Follow-up call log
Retail | 11 | [BUILD] Order & Repair Booking | High | Small | Booking ID, Date, Customer, Mobile, Type (New order/Repair/Remodel/Resize/Stone setting), Quick capture: Voice memo / WhatsApp screenshot attach, Urgency (Normal/Urgent/VIP), Advance collected (₹), Receipt issued (Y/N), Assigned to technician, Expected ready date, Status (Booked/WIP/Ready/Collected), Customer reminder sent (WhatsApp/SMS), Counter staff name
Retail | 12 | [EXTEND] POS Management (Jewellery) | High | Large | Customer lookup (by name/mobile/loyalty ID), Customer profile: tier/points/outstanding, Item scan (barcode/RFID), Item: Tag No, Design Code, Metal, Purity, Gross weight, Net gold weight, HUID, Gold value (auto: weight × today's rate), Making charges, Stone charges, GST (auto), Total MRP, Multiple items in cart, Exchange old gold (weight/purity/value credited), Advance adjustment, Loyalty points redeem, Discount (if promotion active), Payment mode (Cash/Card/UPI/EMI/Part payment), Bill print, e-Invoice, Send bill on WhatsApp, Customer digital signature, Warranty card print
Retail | 13 | [BUILD] Estimation (Quotation at Counter) | High | Small | Customer name (optional), Date, Design reference (catalogue/custom), Metal, Purity, Approx weight (gm), Today's gold rate (auto), Gold value (auto), Making charges (₹/gm — configurable), Stone charges, Wastage % (add-on), Hallmarking charges, GST (auto), Total estimate (₹), Valid for N hours (gold rate-linked), PDF download, Share on WhatsApp, Convert to order (button), Counter staff name
Retail | 14 | [BUILD] Loyalty & Rewards Program | Medium | Medium | Programme tiers: (Silver/Gold/Platinum — auto-upgrade threshold ₹), Points earning: (₹ spent = X points, excluding gold value / on making charges only / on full value — configurable), Points redemption value (1 point = ₹X towards making charges), Tier benefits per level (priority service / free repair / gifting), Customer loyalty card (digital), Points expiry (N months), Birthday/anniversary bonus points, Redemption at POS (auto-deduct), Programme analytics (enrolled / active / points liability ₹)
Retail | 15 | [BUILD] Gold Chit Schemes | High | Large | Scheme ID, Scheme Name, Duration (months: 11/15/22/30), Monthly instalment (₹), Total instalment value (₹), Bonus: (1 month free / Discount on making / Gift), Start date, End date, Member: Name, Mobile, Aadhaar, Bank account, Photo, Monthly collection register: (Month ¦ Due date ¦ Amount ¦ Collected date ¦ Mode ¦ Receipt No ¦ Status: Paid/Pending/Late), Total collected (₹), Total due (₹), Defaulter flag (>1 month pending), Maturity date, Maturity value (₹ + bonus), Redemption: Cash / Gold purchase / Making charge credit, Scheme analytics: Active/Matured/Defaulted/Foreclosed count
Retail | 16 | [EXTEND] Credit & Debit Management | Medium | Small | Customer name, Credit limit (₹), Outstanding balance (₹), Overdue amount, Overdue days, Transaction history: (Date ¦ Invoice / Receipt ¦ Dr ¦ Cr ¦ Balance), Gold account balance (gm — if applicable), Credit limit alert, Block sales if overdue >N days (configurable), Statement download, Send statement on WhatsApp
Retail | 17 | [BUILD] Physical Inventory Control | High | Medium | Stock audit ID, Date, Branch/Location, Audit type (Full/Partial/Spot check), Auditor name, Stock as per system: (Tag No ¦ Design Code ¦ Metal ¦ Weight gm ¦ Location), Physical count: (Tag No found Y/N ¦ Actual weight gm ¦ Condition), Discrepancies: (Extra / Missing / Weight mismatch), Total system weight (gm), Total physical weight (gm), Discrepancy weight (gm), Discrepancy value (₹), Shrinkage % (alert if >0.1%), Approval by manager, Action taken (Adjust/Investigate), Next audit date scheduled
Retail | 18 | [EXTEND] MIS & Sales Analytics (Retail) | Medium | Small | Date range, Branch, Sales by metal (22K/18K/Silver/Diamond), Revenue: gold value vs making charges split, Avg transaction value (₹), Pieces sold, Weight sold (gm), Making charges revenue (₹ — key margin metric), Gold scheme collections (₹), Repair/jobwork revenue (₹), Old gold purchases (gm + ₹), Exchange transactions, Top selling designs (by pieces/value), Slow movers (>60 days on display), Staff-wise sales performance, Customer acquisition vs repeat
Retail | 19 | [BUILD] Customer Buy-back Management | Medium | Small | Buy-back ID, Date, Customer name, Mobile, Item: Description, Metal, Purity, Gross weight (gm), Stone weight (gm), Net gold weight (gm), Our original invoice (linked if purchased from us), Original making charges paid, Buy-back rate (% of today's gold rate — configurable, e.g. 95%), Buy-back value (₹ auto: net weight × rate%), Deductions (damage/stone missing/etc.), Net offered to customer (₹), Customer acceptance (Y/N), Payment mode (Cash/Credit to account/Adjust against new purchase), Stock updated (Y/N), Refinery or resale flag
Bullion Trade | 1 | [BUILD] Bullion Booking & Inward Process | High | Medium | Booking ID, Date, Party type (Supplier/Bank/Bullion dealer), Party name, Metal (Gold/Silver/Platinum/Palladium), Form (Bar/Coin/Granule/Wire/Sheet), Fineness (999.9/999/995/916), Weight unit (gm/troy oz/kg), Quantity, Weight (gm), Rate agreed (₹/gm or USD/troy oz), Exchange rate (if USD), Amount (₹ auto), Delivery type (Physical/Allocated/Unallocated), Expected delivery date, Actual delivery date, Received weight (gm), Weight discrepancy, Assay certificate No, Certificate upload, Payment terms (Advance/Credit/RTGS), GST (3%), TDS if applicable
Bullion Trade | 2 | [BUILD] Bullion Invoice & Rate Cuts | High | Medium | Invoice No, Date, Customer/Party, Metal, Form, Fineness, Weight invoiced (gm), Gross rate (₹/gm), Rate cut 1 (impurity deduction — ₹/gm or %), Rate cut 2 (wastage allowance — %), Rate cut 3 (refining charges — ₹/gm), Net rate after all cuts (₹/gm auto), Net amount (₹ auto), GST (3% on bullion — auto), Total invoice (₹), Payment received (Y/N), Due date, e-Way bill (for physical delivery), Download invoice PDF
Bullion Trade | 3 | [EXTEND] Logistics In / Out (Bullion) | High | Small | Movement ID, Date, Movement type (Inward/Outward), Party, Metal, Form, Weight (gm), Seal No / Box No, Armoured van / carrier name, Driver, Insurance policy No, Insured value (₹), e-Way bill No, Customs declaration (for import/export), Received by, Received at (vault/branch/refinery), Security seal intact (Y/N), GPS tracking ref (if applicable), Signature
Bullion Trade | 4 | [BUILD] Physical Inventory Control (Bullion Vault) | High | Medium | Vault audit ID, Date, Location (Vault A/B/Safe/Showroom), Auditors (min 2 required), Items: (Serial/Bar No ¦ Metal ¦ Fineness ¦ Weight gm ¦ Certificate No ¦ Verified Y/N ¦ Physical weight gm ¦ Variance gm), Total system weight (gm), Total physical weight (gm), Discrepancy (gm), Discrepancy value (₹), Seal check (intact Y/N), Tamper evidence, Photography (upload), Sign-off: 2 auditors + manager, Frequency (Daily/Weekly/Monthly), Alert if discrepancy >0.01 gm
Bullion Trade | 5 | [BUILD] Bullion Movement Tracking Dashboard | High | Medium | Live dashboard, Period filter, Total gold in (gm + ₹), Total gold out (gm + ₹), Current vault balance (gm + ₹ at today's rate), By location (Vault/Showroom/In transit/With karigar), By metal and form, Movement timeline (chart), Open bookings (delivery pending), In-transit consignments (map view if GPS), Rate exposure (total gold × today rate − purchase cost = unrealised P&L), Alerts: transit >24hrs, vault discrepancy, large movement pending approval
Gold Chit Schemes | 1 | [BUILD] Scheme Setup & Configuration | High | Small | Scheme ID, Scheme Name, Type (Fixed instalment/Gold weight accumulation), Duration (months), Monthly instalment (₹ or gm), Joining fee (₹), Bonus type (Free month/Making discount %/Gift/Gold coin), Bonus value, Max members per scheme batch, Start date, Auto-close date, Payment modes accepted (Cash/UPI/Bank), Late payment grace period (days), Late fee (₹ or %), Foreclosure penalty (%), Terms & conditions, Active (Y/N)
Gold Chit Schemes | 2 | [BUILD] Member Enrollment | High | Small | Enrollment ID, Scheme selected, Member Name, Mobile, Email, Aadhaar No, Photo, Address, Nominee name, Nominee relation, Bank account (for refunds), Monthly instalment amount (₹), First instalment date, Installment day of month (1st/5th/10th/etc.), Member agreement signed (Y/N), Agreement upload, Enrollment date, Staff who enrolled, Branch, Member ID / Scheme card No (auto), Welcome message sent (WhatsApp/SMS)
Gold Chit Schemes | 3 | [BUILD] Monthly Collection Register | High | Small | Scheme Name, Collection month, Members list: (Member ID ¦ Name ¦ Mobile ¦ Instalment amount ¦ Due date ¦ Paid date ¦ Mode: Cash/UPI/NEFT ¦ Receipt No ¦ Status: Paid/Pending/Late/Waived), Total collected (₹), Total pending (₹), Collection % (paid/total members), Defaulters count, Send reminder button (bulk WhatsApp/SMS), Daily collection summary by staff, Export to Excel
Gold Chit Schemes | 4 | [BUILD] Scheme Maturity Management | High | Small | Member ID, Name, Scheme, Start date, End date (maturity), Total instalments (count + ₹), Bonus (₹ or making discount %), Total maturity value (₹), Status (Approaching maturity / Matured / Redeemed), Reminder sent at: 60 days / 30 days / 10 days before maturity, Redemption options offered (Gold purchase / Cash / Extended scheme), Member response, Redemption processed (Y/N)
Gold Chit Schemes | 5 | [BUILD] Redemption (Gold / Cash / Purchase) | High | Small | Redemption ID, Member ID, Name, Scheme, Maturity amount (₹), Bonus (₹ or making credit ₹), Total redeemable (₹), Redemption type: Cash payout / Gold purchase (making charge credit applied) / Extend to new scheme, If gold purchase: Item selected (Tag No), Item value (₹), Making charges (after bonus discount), Gold rate on redemption date, Balance payable by customer (if any) or refund, Receipt issued, TDS deducted (if cash >₹10,000), Settlement complete (Y/N)
Gold Chit Schemes | 6 | [BUILD] Defaulter Management | Medium | Small | Defaulter ID, Member Name, Mobile, Scheme, Months paid, Months defaulted, Default amount (₹), Last paid date, Days since last payment, Action taken: (Date ¦ Action: Call/WhatsApp/Visit ¦ Response ¦ Next follow-up date), Foreclosure option offered (Y/N), Foreclosure value (paid amount − penalty), Legal notice issued (Y/N), Write-off flag (Y/N), Resolved (Y/N), Resolution type (Paid/Foreclosed/Written off)
Gold Chit Schemes | 7 | [BUILD] Scheme Reports & Analytics | Medium | Small | Period, Scheme-wise summary: (Scheme Name ¦ Active members ¦ Total collected ₹ ¦ Maturing this month ¦ Redeemed ¦ Defaulters), Cash flow from schemes (monthly bar chart), Upcoming maturities (next 3 months with ₹ value), Redemption trend (gold purchase % vs cash %), Scheme ROI for business (gold sold via scheme vs regular), Branch-wise collection, Staff-wise enrollment targets vs actual, Export to Excel / PDF
E-Catalog | 1 | [BUILD] Digital Catalogue Setup & Branding | Medium | Small | Catalogue ID, Catalogue name, Business name, Logo upload, Brand colours (primary/secondary hex), Catalogue URL / share link (auto-generated), Access type (Public link / Password protected / Time-based), Password (if protected), Expiry date/time (for time-based), Watermark text (e.g. 'Confidential — XYZ Jewellers'), Custom footer text, Default currency, Language (EN/Telugu/Hindi/Tamil), Active (Y/N)
E-Catalog | 2 | [EXTEND] Category & Product Management | Medium | Small | Category: Name, parent category, display order, cover image; Product: Design Code, Name, Category, Metal, Purity, Weight range (min–max gm), Images (upload multiple — min 4 angles), 360° video upload, Stone details, Available in sizes (Ring sizes/Bangle sizes), Price display: Hide price / Show MRP / Show making charges only / Show range, Stock availability: Show/Hide/Show as Available if >0, Tags/labels (New arrival/Bestseller/Limited edition/On offer)
E-Catalog | 3 | [BUILD] Customer Catalogue Sharing Portal | Medium | Medium | Share link generation (unique per customer or general), Customer receives: Branded catalogue view, Category browsing, Quick item lookup (search by name/code/purity), Multi-image view with interactive zoom, 360° product view, One-tap image sharing (WhatsApp/Email), Add to enquiry list, Submit enquiry (items + quantities + notes), Content protection: disable screenshot (where technically possible), Watermark on images, Secure access with OTP, Session time limit, View analytics: which customer viewed what for how long
E-Catalog | 4 | [BUILD] Shelf Stock Monitoring (Track & Refill) | Medium | Small | Product: Design Code, Category, Current stock (pieces + gm), Min display stock (configurable), Max display stock, Alert if stock < min (auto WhatsApp to manager), Refill required (Y/N), Last restocked date, Source (Own manufacture / Supplier / Transfer from HO), Reorder trigger, Fast-moving items (refill frequently), Dead stock (no enquiry in >30 days), Catalogue visibility auto-hidden if stock = 0 (configurable)
E-Catalog | 5 | [BUILD] Catalogue Analytics | Medium | Small | Period filter, Catalogue views (total), Unique viewers, Most viewed categories, Most viewed items (Top 20 by views), Most shared items, Enquiries received (count + items), Conversion rate (enquiry to order %), Customer-wise engagement: (Customer ¦ Views ¦ Time spent ¦ Items viewed ¦ Enquiries raised), Catalogue sent vs opened vs acted, Export report
OMS | 1 | [BUILD] Online Order Booking Portal | High | Large | Customer login (mobile OTP), Customer profile, Browse: Category → Metal → Purity → Designs, Filter: price range / weight range / purity / style, Product page: multiple images, 360° view, weight, making charges, today's gold rate, estimated total price (live-updated), Customisation notes (size/colour/stone preference), Add to cart, Cart summary, Order notes (free text), Advance payment (online gateway), Order confirmation (SMS/WhatsApp/Email), Mobile + desktop responsive
OMS | 2 | [BUILD] Live Product Availability Display | High | Small | Real-time stock sync from ERP, Display: In stock / Made to order (N days) / Not available, Stock depletes in cart if others book same item, Pre-order option (Y/N — configurable per item), Notify me when available (WhatsApp/SMS opt-in), ETA for made-to-order items (from production planning auto-calculated)
OMS | 3 | [BUILD] Order Tracking Dashboard (Customer) | High | Small | Customer login, My orders: (Order ID ¦ Date ¦ Items ¦ Status ¦ Est delivery ¦ Actions), Order status timeline: Booked → Design confirmed → In production → Quality check → Ready → Dispatched → Delivered, WhatsApp notification at each stage, Live location tracking (if courier integrated), Estimated delivery date (updated dynamically), Raise issue button (if problem with order), Download invoice
OMS | 4 | [EXTEND] Order History with Status | Medium | Small | Extend SwachERP Sales Orders — add: Customer portal visible (Y/N), Production stage (live), WhatsApp notification log, Customer review/rating after delivery
OMS | 5 | [EXTEND] SMS / WhatsApp Alerts (OMS) | Medium | Small | Extend SwachERP's central WhatsApp service — add OMS triggers: Order placed / Production started / Ready for pickup / Dispatched / Delivered / Payment due / Scheme instalment due
E-Commerce | 1 | [BUILD] Jewellery Online Store Setup | High | Large | Store name, Domain/subdomain, Logo + branding, Store currency (INR/USD/AED/etc.), Default language + multi-language toggle, Gold rate source (MCX/IBJA/Manual), Rate update frequency (Every 15 min / Hourly / Manual), Making charges display: Included in price / Shown separately, Price validity message ('Price valid for next 30 minutes — gold rate linked'), Shipping zones + rates, COD available (Y/N), Return policy text, Terms & conditions, SEO meta fields, Google Analytics integration, WhatsApp chat widget
E-Commerce | 2 | [BUILD] Product Catalog with Metal Rate Pricing | High | Medium | Design Code, Product name, Category, Metal, Purity, Weight (gm), Making charges (₹/gm — stored), Stone charges (₹ — stored), Today's gold rate (live), Auto-calculated selling price (weight × rate + making + stone + GST), Price updates live as gold rate changes, Image gallery (multiple angles), 360° view, Weight range display, Customisation available (Y/N), Stock: In stock / Made to order, Certification: BIS hallmarked / IGI certified / GIA certified
E-Commerce | 3 | [BUILD] Live Gold Rate Price Calculator | High | Small | Visible widget on all product pages and homepage, Inputs: Metal (Gold/Silver), Purity (24K/22K/18K/Silver 925), Weight (gm) — editable, Making charges %, Output: Gold value (₹), Making charges (₹), GST (₹), Total estimate (₹), Rate source and timestamp shown ('MCX rate as of HH:MM'), 'Rate valid for N minutes' countdown, 'Get exact quote' button (links to enquiry/order form), Embeddable on WhatsApp link
E-Commerce | 4 | [BUILD] Cart, Checkout & Quote Request | High | Medium | Cart: Items (image, name, weight, live price — updates every refresh), Remove item, Update quantity, Apply coupon/offer, Estimated total (live-updated with gold rate), Quote request option (instead of direct buy — generates PDF quotation), Checkout: Delivery address, Shipping method, Payment: Razorpay/PayU/COD/Bank transfer/Gold scheme balance, Order summary with rate lock timestamp, Place order confirmation, EMI option display (if enabled)
E-Commerce | 5 | [BUILD] Customer Registration & Wishlist | Medium | Small | Registration: Name, Mobile (OTP), Email, Birthday/Anniversary (for reminders), City, Preferred metal/purity, Newsletter opt-in, Login: Mobile OTP / Google / Email+password, Wishlist: Add/remove items, WhatsApp share wishlist (for gifting), Price drop alert (if gold rate falls, notify wishlist items are cheaper), Saved cart, Order history, My account dashboard, Gold rate history chart, Loyalty points balance
E-Commerce | 6 | [EXTEND] Offer & Coupon Management | Medium | Small | Extend: existing CRM/Promotions — add e-commerce coupon codes: FLAT discount / % on making charges / Free shipping / Gift on order above ₹X, Coupon: single-use / multi-use / customer-specific, Track redemption, Expiry date
E-Commerce | 7 | [EXTEND] ERP Sync Dashboard | Medium | Small | Orders from e-commerce → auto-create in SwachERP Sales Orders, Stock from SwachERP → auto-update e-commerce availability, Customer data synced, Payment reconciliation, Sync status: (Last sync ¦ Orders synced ¦ Stock updates ¦ Errors), Manual sync trigger
RFID | 1 | [BUILD] RFID Tagging & Encoding Station | High | Large | Tag ID (auto-encoded), EPC code (assigned), Item linked: Design Code, Tag No/Barcode, Metal, Purity, Weight gm, HUID, Encoding station (printer/encoder device), Tag type (UHF RFID / HF NFC), Tag placement (on item / on tag card), Encoding date, Encoded by, Verification scan (confirm tag reads correctly), Failed encoding log, Tags encoded today (count), Batch encode (multiple items), Link to inventory auto (Y/N)
RFID | 2 | [BUILD] Bulk Inventory Scanning | High | Large | Scan session ID, Date, Location (Showroom/Vault/Safe/Showcase No), Scanner device ID, Scan start time, Scan end time, Items detected: (Tag ID ¦ Design Code ¦ Description ¦ Metal ¦ Weight gm ¦ Status: Found/Missing/Extra), Total expected (system), Total scanned (physical), Matched (count + gm), Missing (count + gm + value ₹), Extra (count — investigate), Discrepancy report, Auto-alert if missing items >0, Export scan report, History of scan sessions
RFID | 3 | [EXTEND] Inward & Outward Movement Tracking (RFID) | High | Medium | RFID gate reader at entry/exit, Auto-detect items passing gate, Movement entry: Date/time, Direction (In/Out), Items: (Tag ID ¦ Design Code ¦ Weight gm), Associated GRN/Invoice/Transfer, Authorised movement (Y/N), Unauthorised alert (item leaving without invoice/transfer), Dashboard: items in showroom vs vault vs safe vs in transit
RFID | 4 | [BUILD] Packing & Dispatch Validation (RFID) | High | Medium | Dispatch ID, Customer/Invoice linked, Expected items to pack: (Tag ID ¦ Design Code ¦ Weight gm), Scan items into package (RFID scan one by one or bulk), Validation: All expected items scanned? (Green=Yes / Red=Missing), Extra items detected (alert), Total weight packed (auto sum gm), Package sealed, Seal No recorded, Final scan count matches invoice (Y/N), Dispatch authorised, Exception override (requires manager password), Packing photos
RFID | 5 | [BUILD] Anti-Theft & Security Alerts | High | Large | Alert types: (Unauthorised exit — item leaving without invoice ¦ Ghost item — tag not in system ¦ Missing item — was in location, now not found ¦ Tampered tag — tag damaged/removed ¦ Unusual movement — item moved outside business hours), Alert log: (Date/time ¦ Alert type ¦ Item: Tag ID/Code/Description/Weight ¦ Location ¦ Triggered by ¦ Acknowledged by ¦ Action taken ¦ Resolved Y/N), Real-time push alert (app/SMS to manager), CCTV timestamp reference (if integrated), False alarm tracking
RFID | 6 | [BUILD] Live RFID Dashboard & Reports | High | Medium | Live stock map: items by location (Showroom: Showcase 1–10, Vault, Safe, Counter), Item heatmap: which showcases have most/least stock, Real-time weight in each location (gm), Value by location (₹ at today's rate), Last full scan date per location, Alerts active count, Scan accuracy % (scanned vs system), Items not scanned in >N days, Reports: Daily movement log, Weekly discrepancy, Missing items history, RFID utilisation (% of stock tagged), Export CSV
RFID | 7 | [BUILD] Mobile & Handheld RFID Scanner App | High | Large | Login with employee ID + PIN, Select mode: Spot check / Full audit / Packing scan / Single item lookup, Point and scan (camera + RFID reader), Scanned item details (name, weight, location, status — instant display), Flag item (missing/damaged/misplaced), Add note, Multi-scan session (accumulate list), Submit session (syncs to ERP), Works offline (queues and syncs), Battery-efficient scanning mode, Print label (if Bluetooth printer connected)
Business Analytics | 1 | [EXTEND] Live Stock Value Dashboard | High | Small | Total pieces in stock (count), Total gross weight (gm), Total net gold weight (gm), Today's gold rate (live), Live stock value (₹ = net gold weight × rate), Making charges embedded in stock (₹), Total stock value (gold + making), By metal/purity breakdown, By category breakdown, Stock value trend (30-day chart), Compare with yesterday/last week/last month, Branch-wise stock value, Alert if stock value crosses threshold
Business Analytics | 2 | [BUILD] Making Charge & Wastage Trends | High | Small | Period, Making charges collected (₹) — by category/metal, Making charge % of total revenue, Wastage generated (gm) by karigar/department, Wastage as % of gold issued, Refinery recovery % (refined gold returned/wastage sent), Month-on-month wastage trend, Karigar-wise wastage ranking (best to worst), Alert if karigar wastage >X% above average, Cost per gram of making by design category, Margin on making charges
Business Analytics | 3 | [BUILD] Item-wise & Tag-wise Insights | Medium | Small | Each item (tag): days in stock, views/enquiries (if RFID/catalogue), sold/unsold, rate of return (repurchased by customers), Bestsellers (by pieces/weight/revenue — last 30/90/365 days), Slow movers (>60 days unsold — with value at risk), Category performance (turnover ratio: sold/average stock), Design lifecycle (from production to sale — avg days), Re-order suggestions (designs selling fast, low stock)
Business Analytics | 4 | [BUILD] Weight & Purity Loss Reports | High | Small | Gold issued to karigar (gm), Gold returned in pieces (gm), Wastage collected (gm), Refinery send (gm), Refinery received (gm), Net loss (gm = issued − returned − collected + not yet recovered), Loss % (alert if >2%), Purity variance: issued purity vs received purity, Value of loss (₹ at market rate), Loss by karigar (accountability), Loss by process stage (casting/filing/polish), Month-on-month loss trend, Acceptable loss benchmark (configurable)
Business Analytics | 5 | [EXTEND] Job Work & Production Analytics | Medium | Small | Extend: Variance Analytics — add: Job completion rate (on-time %), Avg production days by design type, Karigar efficiency (pieces/gm output per day), Rework rate (QC failures %), Wastage per production order, Most efficient karigar (by output/wastage ratio), Production cost vs selling price margin
Business Analytics | 6 | [EXTEND] Customer Behaviour Analytics | Medium | Small | Extend: MIS Sales — add: Avg purchase frequency (orders/year), Avg order value (₹), Metal preference (% customers by 22K/18K/Silver/Diamond), Occasion-based buying (festival/wedding/birthday), Gold scheme participation %, Repair vs new purchase ratio, Lapsed customers (no purchase in >6 months), Top 100 customers by revenue
Business Analytics | 7 | [EXTEND] Sales Performance Analytics | Medium | Small | Extend: MIS Sales — add: Revenue split: gold value vs making charges vs stone charges, Gross margin % (making charges/total revenue), Sales by counter staff, Peak hours/days (hourly heatmap), Walk-in to sale conversion %, Scheme-led sales %, Festival season performance comparison
Business Analytics | 8 | [EXTEND] Billing & Margin Reports | Medium | Small | Extend: Financial Analytics — add: Making charges margin by category, Stone charges margin, Bullion trade margin (sell rate − buy rate), Total gold traded (gm/period), Avg buying rate vs avg selling rate (margin ₹/gm), Revenue per square foot (retail), Cost of unsold inventory (opportunity cost)
Business Analytics | 9 | [EXTEND] Purchase & Vendor Insights | Low | Small | Extend: Vendor Analytics — add: Gold purchased (gm by supplier), Avg purchase rate vs MCX rate (premium/discount %), Supplier quality score (rejection rate %), Lead time reliability, Payment terms compliance, Top 5 suppliers by volume
Business Analytics | 10 | [BUILD] Movement & Transfer Tracking | Medium | Small | Period, Branch-wise stock movement: (Sent gm ¦ Received gm ¦ Net change gm), Transfer efficiency (arrived complete Y/N), Items in transit currently (count + gm + value), Lost/damaged in transit (history), Karigar-wise material movement (issued/returned tracking), Refinery movement log (sent/received timeline), e-Way bill compliance (% transactions with e-way bill generated), Insurance coverage on movements
Finance (Jewellery) | 1 | [BUILD] Metal-Based Accounting (Gold/Silver/Platinum) | High | Large | Parallel weight ledger alongside ₹ ledger — every transaction records: ₹ amount + metal weight gm + purity, Account types: Gold stock account (gm), Gold purchase account (gm + ₹), Gold sales account (gm + ₹), Karigar payable (gm + ₹), Refinery account (gm), Wastage account (gm), Metal P&L: unrealised gain/loss (current stock weight × (today's rate − avg purchase rate)), Trial balance with weight column, Journal entries with weight field, Day book shows both ₹ and gm
Finance (Jewellery) | 2 | [BUILD] Multi-Branch Gold Stock Consolidation | High | Medium | HO consolidated view: All branches + main vault, Total gold in organisation (gm by purity), Total gold value (₹ at live rate), Unrealised P&L (total stock value − total purchase cost), Branch-wise breakdown: (Branch ¦ Gold in stock gm ¦ With karigar gm ¦ In transit gm ¦ Total gm ¦ Value ₹), Intercompany transfers (gm reconciliation), Daily closing gold position report (regulatory requirement for large dealers), Export to PDF/Excel
Finance (Jewellery) | 3 | [BUILD] Metal Rate-Based P&L | High | Medium | Period P&L with jewellery-specific lines: Revenue: Gold sales (₹) ¦ Making charges (₹) ¦ Stone charges (₹) ¦ Repair/jobwork (₹) ¦ Gold scheme income (₹) ¦ Bullion trading margin (₹), COGS: Gold purchase cost (gm × avg rate), Gross margin: Making charges + other non-gold revenue, Inventory holding gain/loss (stock at period-end rate vs purchase rate), Wastage cost (gm × rate), Refinery loss (gm × rate), Metal-adjusted net profit
Finance (Jewellery) | 4 | [BUILD] Weight & Purity Loss P&L Impact | High | Small | Period, Total gold issued (gm), Total gold recovered in products (gm), Total wastage sent to refinery (gm), Total refined gold received (gm), Unaccounted loss (gm = issued − products − refinery received), Unaccounted loss value (₹ = gm × gold rate), This goes to: Wastage expense account (P&L debit), Purity downgrade loss: items sold at lower purity than expected — rate difference × weight = loss (₹), Total metal loss impact on P&L (₹), Benchmark: acceptable loss % × total gold processed = benchmark loss
Finance (Jewellery) | 5 | [EXTEND] Cash Flow & Fund Flow (Jewellery) | Medium | Small | Extend: Cash Flow Statement — add: Gold scheme collections (₹ inflow), Gold purchases — cash outflow, Bullion trading cash flow, Karigar payments — cash outflow, Refinery payments/receipts, Large cash transactions flagged (>₹2L — Income Tax reporting required), Gold loan disbursement/collection (if gold loans offered)

## ✅ Reuse List (Config View)
Sub-Module | Screen Name | SwachERP Screen to Reuse / Minimal Config Needed
Wholesale | Vendor & Supplier Process | Reuse: Vendors screen with minor additions
Wholesale | Customer Ledger | Reuse: Ledger View with gold weight column
Wholesale | Receivables & Payables Tracking | Reuse: Aging Report
Wholesale | Approval Workflow | Reuse: Approval Workflows
Retail | Vendor & Supplier Process (Retail) | Reuse: Vendors
Bullion Trade | Receipts & Payments (Bullion) | Reuse: Invoice Payments
Bullion Trade | Vendor & Supplier Process (Bullion) | Reuse: Vendors
Bullion Trade | Customer Ledger (Bullion) | Reuse: Ledger View
OMS | Customer Ledger (OMS) | Reuse: Ledger View

## 📡 APIs to Build
Module | Method | Endpoint | Description | Status
Production | POST | /api/gold/designs | Add design to master library | 🆕 Build
| GET | /api/gold/designs | List designs with filters | 🆕 Build
| GET | /api/gold/designs/:id | Design detail + images + CAD file | 🆕 Build
| POST | /api/gold/production-orders | Create production order | 🆕 Build
| GET | /api/gold/production-orders | List production orders | 🆕 Build
| PUT | /api/gold/production-orders/:id/stage | Advance to next production stage | 🆕 Build
| GET | /api/gold/production-orders/:id/timeline | Full stage timeline for order | 🆕 Build
| POST | /api/gold/sketch | Create sketch entry for job | 🆕 Build
| POST | /api/gold/cad | Upload CAD file + metadata | 🆕 Build
| POST | /api/gold/cam | Upload CAM file + prototype details | 🆕 Build
| POST | /api/gold/casting-tree | Create casting tree record | 🆕 Build
| POST | /api/gold/ghat | Record weighing/assay entry | 🆕 Build
| GET | /api/gold/ghat/:job_id | Ghat history for job | 🆕 Build
| POST | /api/gold/casting | Record casting process entry | 🆕 Build
| POST | /api/gold/finishing/:stage | Record filing/buffing/fitting/polish | 🆕 Build
| POST | /api/gold/qc | Submit QC checklist for job | 🆕 Build
| PUT | /api/gold/qc/:id/result | Record QC pass/fail/rework | 🆕 Build
| POST | /api/gold/job-finalize | Finalize job + generate barcode/RFID | 🆕 Build
| POST | /api/gold/settlement | Settle karigar job work account | 🆕 Build
| GET | /api/gold/karigar/:id/material-balance | Gold in hand for karigar | 🆕 Build
| GET | /api/gold/karigar/:id/pending-jobs | Open job works for karigar | 🆕 Build
| POST | /api/gold/karigar/issue | Issue gold to karigar | 🆕 Build
| POST | /api/gold/karikar/receive | Receive finished piece from karigar | 🆕 Build
Wholesale | POST | /api/gold/orders | Create wholesale order | 🔧 Extend /api/sales-orders
| GET | /api/gold/orders | List wholesale orders | 🔧 Extend
| POST | /api/gold/jobwork | Create jobwork order (customer gold) | 🆕 Build
| GET | /api/gold/jobwork/:id | Jobwork detail + customer gold balance | 🆕 Build
| POST | /api/gold/inventory/tag | Add tagged item to inventory | 🔧 Extend /api/serial-lots
| GET | /api/gold/inventory/tag/:tag_no | Lookup item by tag/barcode | 🔧 Extend
| POST | /api/gold/repair | Create repair/remodel job | 🆕 Build
| GET | /api/gold/repair/:id | Repair job detail | 🆕 Build
| POST | /api/gold/bullion/transaction | Record bullion buy/sell/exchange | 🆕 Build
| GET | /api/gold/bullion/transactions | List bullion transactions | 🆕 Build
| GET | /api/gold/inventory/line-wise | Line-wise stock summary | 🆕 Build
| POST | /api/gold/dispatch/challan | Create delivery challan | 🔧 Extend /api/dispatch
| POST | /api/gold/quotation | Generate gold rate-based quotation | 🔧 Extend /api/price-lists
| GET | /api/gold/quotation/:id/pdf | Download quotation PDF | 🆕 Build
| POST | /api/gold/hallmarking/batch | Submit items for hallmarking | 🆕 Build
| PUT | /api/gold/hallmarking/batch/:id/receive | Record HUID received from centre | 🆕 Build
| GET | /api/gold/hallmarking/batch/:id | Hallmarking batch detail | 🆕 Build
Retail | POST | /api/gold/estimation | Create counter estimation/quote | 🆕 Build
| GET | /api/gold/estimation/:id/pdf | Download estimation PDF | 🆕 Build
| POST | /api/gold/pos/bill | Create jewellery POS bill | 🔧 Extend /api/pos/transactions
| POST | /api/gold/pos/old-gold | Record old gold exchange at POS | 🆕 Build
| POST | /api/gold/approval | Issue items on customer approval | 🆕 Build
| PUT | /api/gold/approval/:id/return | Record items returned from approval | 🆕 Build
| PUT | /api/gold/approval/:id/convert | Convert approval to sale | 🆕 Build
| POST | /api/gold/promotion | Create jewellery promotion | 🆕 Build
| GET | /api/gold/promotions/active | Active promotions for billing | 🆕 Build
| POST | /api/gold/loyalty/earn | Record loyalty points earned | 🔧 Extend /api/loyalty/earn
| POST | /api/gold/loyalty/redeem | Redeem points at POS | 🔧 Extend /api/loyalty/redeem
| POST | /api/gold/buyback | Record customer gold buy-back | 🆕 Build
| GET | /api/gold/buyback/:id | Buy-back transaction detail | 🆕 Build
| POST | /api/gold/physical-audit | Start physical inventory audit session | 🆕 Build
| POST | /api/gold/physical-audit/:id/item | Record physical count per item | 🆕 Build
| GET | /api/gold/physical-audit/:id/discrepancies | Discrepancy report | 🆕 Build
Gold Chit Schemes | POST | /api/gold/chit/schemes | Create chit scheme | 🆕 Build
| GET | /api/gold/chit/schemes | List all schemes | 🆕 Build
| POST | /api/gold/chit/enroll | Enroll member in scheme | 🆕 Build
| GET | /api/gold/chit/members | List scheme members | 🆕 Build
| POST | /api/gold/chit/collection | Record monthly instalment payment | 🆕 Build
| GET | /api/gold/chit/collection/:scheme_id | Collection register for scheme | 🆕 Build
| GET | /api/gold/chit/defaulters | List defaulting members | 🆕 Build
| GET | /api/gold/chit/maturing | Members maturing in next N days | 🆕 Build
| POST | /api/gold/chit/redeem | Process scheme maturity redemption | 🆕 Build
| GET | /api/gold/chit/analytics | Scheme analytics dashboard data | 🆕 Build
Bullion Trade | POST | /api/gold/bullion/booking | Create bullion booking | 🆕 Build
| GET | /api/gold/bullion/bookings | List bullion bookings | 🆕 Build
| POST | /api/gold/bullion/inward | Record physical bullion receipt | 🆕 Build
| POST | /api/gold/bullion/invoice | Create bullion invoice with rate cuts | 🆕 Build
| GET | /api/gold/bullion/movement | Bullion movement log | 🆕 Build
| GET | /api/gold/bullion/vault-balance | Current vault stock by metal/form | 🆕 Build
| POST | /api/gold/vault/audit | Trigger vault physical audit | 🆕 Build
| GET | /api/gold/bullion/dashboard | Bullion movement dashboard data | 🆕 Build
E-Catalog | POST | /api/gold/catalog | Create digital catalogue | 🆕 Build
| GET | /api/gold/catalog/:id | Get catalogue (customer view) | 🆕 Build
| POST | /api/gold/catalog/:id/share | Generate share link (with expiry/OTP) | 🆕 Build
| POST | /api/gold/catalog/enquiry | Submit enquiry from catalogue | 🆕 Build
| GET | /api/gold/catalog/:id/analytics | Catalogue view analytics | 🆕 Build
| GET | /api/gold/catalog/shelf-alerts | Low stock alerts for catalogue | 🆕 Build
OMS | POST | /api/gold/oms/orders | Place order via OMS portal | 🆕 Build
| GET | /api/gold/oms/orders/:customer_id | Customer order history | 🆕 Build
| GET | /api/gold/oms/orders/:id/tracking | Order tracking status | 🆕 Build
| GET | /api/gold/oms/products/availability | Live product availability for portal | 🆕 Build
| POST | /api/gold/oms/notify | Send WhatsApp/SMS order update | 🔧 Extend /api/whatsapp/send
E-Commerce | GET | /api/gold/ecom/rate | Live gold rate for store pricing | 🆕 Build
| GET | /api/gold/ecom/products | Product list with live prices | 🆕 Build
| GET | /api/gold/ecom/products/:id | Product detail with live price | 🆕 Build
| POST | /api/gold/ecom/cart | Add to cart / update cart | 🆕 Build
| POST | /api/gold/ecom/checkout | Place order + payment initiation | 🆕 Build
| GET | /api/gold/ecom/orders/:id | Order status for customer | 🆕 Build
| POST | /api/gold/ecom/wishlist | Add to wishlist | 🆕 Build
| POST | /api/gold/ecom/coupons/validate | Validate coupon code | 🔧 Extend
| GET | /api/gold/ecom/erp-sync | ERP sync status for e-commerce | 🔧 Extend /api/channels/sync
RFID | POST | /api/rfid/tags/encode | Encode RFID tag and link to item | 🆕 Build
| GET | /api/rfid/tags/:tag_id | Lookup item by RFID tag | 🆕 Build
| POST | /api/rfid/scan/session | Start bulk scan session | 🆕 Build
| POST | /api/rfid/scan/session/:id/items | Upload scanned tag list | 🆕 Build
| GET | /api/rfid/scan/session/:id/report | Discrepancy report for scan session | 🆕 Build
| POST | /api/rfid/movement | Record RFID gate movement event | 🆕 Build
| POST | /api/rfid/alert | Trigger security alert | 🆕 Build
| GET | /api/rfid/dashboard | Live RFID dashboard data | 🆕 Build
| POST | /api/rfid/dispatch/validate | Validate RFID scan vs dispatch items | 🆕 Build
Business Analytics | GET | /api/gold/analytics/stock-value | Live gold stock value dashboard | 🔧 Extend /api/mis/inventory-analytics
| GET | /api/gold/analytics/making-charges | Making charge & wastage trend data | 🆕 Build
| GET | /api/gold/analytics/weight-loss | Weight & purity loss report | 🆕 Build
| GET | /api/gold/analytics/item-insights | Item/tag-wise performance | 🆕 Build
| GET | /api/gold/analytics/movement | Gold movement & transfer analytics | 🆕 Build
| GET | /api/gold/analytics/customer | Customer behaviour analytics | 🔧 Extend /api/mis/sales-analytics
| GET | /api/gold/analytics/production | Production efficiency analytics | 🔧 Extend /api/analytics/variance
Finance (Jewellery) | POST | /api/gold/finance/journal | Create journal entry with weight field | 🔧 Extend /api/journal-entries
| GET | /api/gold/finance/metal-ledger | Metal (weight) ledger for account | 🆕 Build
| GET | /api/gold/finance/stock-consolidation | Multi-branch gold stock consolidation | 🆕 Build
| GET | /api/gold/finance/metal-pl | Metal rate-based P&L report | 🆕 Build
| GET | /api/gold/finance/loss-impact | Weight/purity loss P&L impact | 🆕 Build
| GET | /api/gold/finance/unrealised-gain | Unrealised gold P&L on stock | 🆕 Build

## 🔗 Integrations
Category | Integration | Purpose | Priority | SwachERP Status
Gold Rate | MCX / IBJA API | Live gold & silver rate feed — powers pricing across all modules | Critical | Already identified
Hallmarking | BIS HUID Portal | Bulk HUID registration and certificate download for finished items | Critical | 🆕 New integration
E-Way Bill | NIC e-Way Bill Portal | Auto-generate e-way bill for gold movement >₹50,000 | High | 🔧 Extend existing GST integration
E-Invoice | GST e-Invoice API | Auto e-invoice for B2B jewellery sales and bullion transactions | High | ✅ Already in SwachERP
Payment | Razorpay / PayU | Online payments for e-commerce, OMS, gold chit installments | High | ✅ Already in SwachERP
RFID Hardware | RFID Encoder (Zebra/Alien) | Tag encoding at production stage — USB/network connected device | Critical | 🆕 New hardware integration
RFID Hardware | Handheld RFID Scanner (Zebra/Chainway) | Bulk inventory scanning — mobile app API integration | Critical | 🆕 New hardware integration
RFID Hardware | RFID Gate Reader | Inward/outward movement detection — LAN/WiFi API integration | High | 🆕 New hardware integration
Insurance | HDFC Ergo / Bajaj Allianz API | Transit insurance for gold shipments and delivery challans | Medium | 🆕 New integration
CAD | RhinoGold / JewelCAD | CAD file import (.3dm/.stl) for weight estimation in production | Medium | 🆕 New file format support
Assay | XRF Analyser (Olympus/Bruker) | Import assay/purity test results from XRF device | Medium | 🆕 New device integration
WhatsApp | WhatsApp Business API | Order updates, scheme reminders, estimation, catalogue share | High | ✅ Already in SwachERP (central service)
SMS | SMS Gateway (Textlocal/MSG91) | Chit scheme reminders, OMS updates, OTP | Medium | ✅ Already in SwachERP
Shipping | Shiprocket / Delhivery | Courier dispatch for e-commerce and OMS orders | Medium | 🆕 New integration
Social | WhatsApp / Instagram sharing | Catalogue item sharing from E-catalog portal | Low | 🆕 New integration
TDS / Tax | TRACES Portal | TDS on gold chit cash payouts >₹10,000 | Medium | 🆕 New integration
Multi-branch | Google Maps API | Branch locator for retail customers in OMS/e-commerce | Low | ✅ Already in SwachERP
3PL / Armoured | Brinks / SIS Prosegur | Armoured van integration for bullion logistics tracking | Medium | 🆕 New integration (for large bullion dealers)