## Phase Status Map
SwachERP — 19 Phases: Already Built vs Still To Build
Existing codebase audit · Only NEW Gold ERP phases need development · Major cost saving
| ALREADY BUILT |  | STILL TO BUILD |  | REVISED BUDGET
| 10 Phases |  | 9 Phases |  | ₹6.5–7.5L
| ~73% of platform work done |  | All Gold ERP specific modules |  | Save ₹2.5–3.5L vs full build
| Ph# | Phase Name | Category | Status | Days Saved | Notes
| 1 | Core ERP Platform & Multi-tenancy | Platform | ✔ BUILT | 2 days | AsyncLocalStorage + tenant isolation complete
| 2 | Authentication, RBAC & Permissions | Platform | ✔ BUILT | 2 days | scrypt login, roles, role_permissions done
| 3 | GST Invoicing & Double-Entry Accounting | Finance | ✔ BUILT | 3 days | Full journal engine + GST invoice with IRN
| 4 | Purchase Orders, GRN & 3-Way Match | Procurement | ✔ BUILT | 3 days | PR → PO → GRN → invoice matching complete
| 5 | Inventory, Warehouses & Stock Transfer | Inventory | ✔ BUILT | 3 days | Multi-warehouse, UOM, serial/lot done
| 6 | HR, Payroll & Attendance | HR | ✔ BUILT | 3 days | Employees, payroll, leaves, expense claims
| 7 | CRM & Customer Portal | CRM | ✔ BUILT | 2 days | Leads, follow-ups, customer master done
| 8 | WhatsApp 2-Way Integration | Integrations | ✔ BUILT | 3 days | Meta Cloud API + Colloki Flow wired up
| 9 | Module Marketplace & SaaS Billing | Platform | ✔ BUILT | 3 days | 27-module catalog, Razorpay billing live
| 10 | GSTR Reports, Audit Trail & Approvals | Finance | ✔ BUILT | 2 days | GSTR-1/3B, audit_logs, approval engine done
| 11 | Metal Rate Engine (IBJA / MCX live) | Gold ERP | ⚒ TO BUILD | — | New: live rate API + history + WhatsApp alert
| 12 | Jewellery Item Master & Price Engine | Gold ERP | ⚒ TO BUILD | — | New: making%, wastage%, purity config
| 13 | Karigar Management & Job Orders | Gold ERP | ⚒ TO BUILD | — | New: karigar master, advances, weight ledger
| 14 | Retail Billing with Making Charges | Gold ERP | ⚒ TO BUILD | — | New: jewellery GST bill + old gold exchange
| 15 | Bullion Trading & Scrap Buy/Sell | Gold ERP | ⚒ TO BUILD | — | New: bar/coin/scrap transactions
| 16 | Gold Savings Chit Schemes | Gold ERP | ⚒ TO BUILD | — | New: enrolment, instalment, redemption
| 17 | Repair Orders & Design Catalogue | Gold ERP | ⚒ TO BUILD | — | New: repair tracking + design image upload
| 18 | Hallmarking, BIS & HUID Generation | Gold ERP | ⚒ TO BUILD | — | New: HUID + assay centre integration
| 19 | Gold Analytics, Licensing & AMC | Gold ERP | ⚒ TO BUILD | — | New: MIS dashboard + license keys + AMC
WHAT THIS MEANS FOR YOUR PROJECT
10 out of 19 phases are ALREADY BUILT in SwachERP. You only need to build the 9 Gold ERP phases.
This saves ~22 dev-days. Revised quote: ₹6.5–7.5 Lakhs ¦ Timeline: 18–22 days instead of 30.

## Revised Build Plan
Revised Build Plan — 9 New Gold ERP Phases Only
Platform already built · Only Gold ERP modules to develop · 18–22 days · ₹6.5–7.5 Lakhs
| NEW PHASES |  | TIMELINE |  | CLIENT COST
| 9 |  | 18–22 Days |  | ₹6.5–7.5L
| All Gold ERP specific |  | vs 30 days original plan |  | Fixed price, all inclusive
| Ph# | Gold ERP Phase — What We Build | Track | Days | Budget | Key Deliverables
| 11 | Metal Rate Engine | Dev A+B | 2 days | 80000 | IBJA/MCX live API, rate history, purity-wise rates, dashboard widget, WhatsApp rate alert
| 12 | Jewellery Item Master | Dev A | 2 days | 80000 | jw_items, jw_purity tables; making charge config; stone/wastage config; item search
| 13 | Karigar Management | Dev A | 3 days | 100000 | Karigar master; job orders; advance ledger; weight issue/receive; wage calc; statement
| 14 | Retail Billing | Dev A | 3 days | 100000 | Gold GST invoice; making + stone + wastage; old gold exchange; melt calc; thermal print
| 15 | Bullion Trading & Scrap | Dev B | 2 days | 70000 | Bar/coin buy-sell; scrap purchase; refinery tracking; bullion P&L; stock in grams
| 16 | Chit / Gold Scheme | Dev A | 2 days | 70000 | Scheme master; member enrolment; monthly instalment; maturity; redemption options
| 17 | Repair & Design Catalogue | Dev B | 2 days | 70000 | Repair job card; before/after photos; status tracking; design image upload + tags
| 18 | Hallmarking & BIS | Dev A | 2 days | 70000 | HUID generation; BIS lot; purity certificate; hallmarked flag on billing
| 19 | Analytics, Licensing & AMC | Dev A+B | 3 days | 100000 | Gold MIS dashboard; karigar P&L; branch sales; license keys; AMC schedule; go-live
|  | TOTAL — 9 NEW GOLD ERP PHASES |  | 19 days | 740000
REVISED COST SUMMARY
Development Cost (9 phases) | [5 empty] | 740000
Infrastructure — 22 days | [5 empty] | 12000
QA & Testing (3 days) | [5 empty] | 35000
Go-Live & Deployment | [5 empty] | 20000
Contingency Buffer (5%) | [5 empty] | 40350
TOTAL INTERNAL COST | [5 empty] | 847350
CLIENT QUOTE — Option A (Lean) | [5 empty] | 650000
CLIENT QUOTE — Option B (Recommended) | [5 empty] | 750000
NOTE: The full Platform (Auth, Finance, HR, Inventory, CRM, WhatsApp, Marketplace) is already live in SwachERP. Client gets all 19 phases at ₹6.5–7.5L.

## 20-Day Gantt
SwachERP Gold ERP — 20-Day Sprint Gantt (9 New Phases Only)
Dev A: Gold ERP Core · Dev B: Supporting modules · Tech Lead: Architecture + QA oversight
# | Phase / Task | Dev | Days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
|  |  |  | W1 | [6 empty] | W2 | [6 empty] | W3
11 | Metal Rate Engine + WhatsApp alert | Dev A+B | 1
12 | Jewellery Item Master & Price Config | Dev A | 2
13 | Karigar Module + Job Orders | Dev A | 3
14 | Retail Billing + Old Gold Exchange | Dev A | 3
15 | Bullion Trading & Scrap | Dev B | 2
16 | Gold Savings Chit Schemes | Dev A | 2
17 | Repair Orders + Design Catalogue | Dev B | 2
18 | Hallmarking & BIS / HUID | Dev A | 2
19 | Gold Analytics Dashboard | Dev A | 2
L | License Keys + AMC Module | Dev B | 2
Q | Integration Testing & Bug Fixes | QA | 3
U | UAT, Training & Go-Live Deploy | All | 2
Dev A: Gold ERP |  |  | Dev B: Platform |  |  | Dev A+B |  |  | QA |  |  | All

## Quote Options
Quote Options for Client — SwachERP Gold ERP
3 options based on scope · Platform already built · Pay only for what is new
|  | OPTION A Gold ERP — Lean | OPTION B Gold ERP + Branding ★ RECOMMENDED | OPTION C Full 19-Phase Rebuild
| Scope | 9 new phases (Gold ERP only) | 9 phases + custom UI + training | All 19 phases, new codebase
| Timeline | 18–20 Days | 22–24 Days | 30 Days
| Price | ₹6,50,000 | ₹7,50,000 | ₹10,00,000
| Gold ERP | ✓ Core Gold ERP (9 modules) | ✓ Core Gold ERP (9 modules) | ✓ Full 19-phase build
| Platform | ✓ Yes — already live | ✓ Yes — already live | ✓ Built from scratch
| WhatsApp | ✓ Basic alerts | ✓ WhatsApp + SMS | ✓ Full integration
| Reports | ✓ Standard MIS | ✓ Advanced analytics | ✓ Full analytics suite
| Support | ✓ 30-day bug fixes | ✓ 60-day support + training | ✓ 90-day support + training
| AMC | ✓ ₹60K/year | ✓ ₹60K/year | ✓ ₹1L/year
Option B is recommended — delivers full Gold ERP value with branding, training and extended support within ₹7.5 Lakhs.