## 1. Master Overview
KINTO SMART OPS — SaaS & Multitenancy Master Plan
Comprehensive plan: DB migration · Auth · Trial system · Deletion · Backups · Billing · Deployment
PRODUCT VISION
Kinto Smart Ops is a SaaS ERP platform for Indian manufacturing companies. A single codebase serves multiple tenants (companies) with complete data isolation, per-tenant licensing, automated billing, and white-labeling support. The system is designed for a shared-database architecture where every table carries a tenant_id column, with all queries automatically scoped to the requesting tenant.
11-PHASE IMPLEMENTATION ROADMAP
Phase | Name | What Gets Built | Key Deliverables | Duration | Priority | Depends On | Status
Phase 1 | DB Migration to Multitenant | Add tenant_id DEFAULT 1 to all 39 tables. Create tenants, plans, subscriptions tables. | ALTER TABLE scripts · tenants table · plans table · subscriptions table | 1 week | P1 — Critical | — | Pending
Phase 2 | Auth — Two-Step Login | Company slug lookup → user login. Session carries tenant_id + plan. | Company lookup page · Updated login flow · Session middleware | 1 week | P1 — Critical | Phase 1 | Pending
Phase 3 | API Tenant Middleware | Every API route auto-scopes queries by tenant_id from session. No cross-tenant data leakage. | getTenantId() middleware · All 200+ routes updated · Integration tests | 2 weeks | P1 — Critical | Phase 2 | Pending
Phase 4 | Trial & License Engine | Account state machine: trial → active → grace → suspended → deleted. Nightly cron jobs. | 6 cron jobs · account_status middleware · reminder emails · WhatsApp alerts | 1 week | P1 — Critical | Phase 2 | Pending
Phase 5 | File Upload Scoping | All uploaded files stored under /uploads/tenants/{id}/ prefix. No cross-tenant file access. | Updated upload handlers · Cloudflare R2 bucket structure · Signed URL generation | 3 days | P1 — Critical | Phase 3 | Pending
Phase 6 | Tenant Admin Portal | Each tenant manages their company: users, roles, subscription, billing, data export. | Tenant settings page · User management · Subscription page · Data export button | 1 week | P2 — High | Phase 4 | Pending
Phase 7 | Super Admin Panel | God-mode panel: view all tenants, impersonate, extend trials, trigger deletion, view metrics. | Super-admin dashboard · Tenant list · Trial management · Deletion controls | 1 week | P2 — High | Phase 6 | Pending
Phase 8 | Razorpay Billing | Monthly subscription billing. Webhook: payment success/failure → account status update. | Razorpay subscription API · Payment webhook · Invoice generation · Receipts | 1 week | P2 — High | Phase 4 | Pending
Phase 9 | Per-Tenant Backups & Deletion | Weekly backup per tenant. 11-step deletion sequence. Retention policies. PITR via Neon. | exportTenantData() · deletion cron · deletion_audit table · R2 lifecycle rules | 1 week | P2 — High | Phase 5 | Pending
Phase 10 | Per-Tenant Notifications | WhatsApp account name, email from-name, and notification settings per tenant. | Tenant notification config table · Per-tenant WhatsApp sender · Per-tenant email | 3 days | P3 — Medium | Phase 3 | Pending
Phase 11 | White-Labeling & Branding | Per-tenant logo, colors, company name on all reports, invoices, and emails. | Tenant branding table · Dynamic report headers · Custom email signatures | 3 days | P3 — Medium | Phase 6 | Pending
PLAN DOCUMENT STRUCTURE (This Workbook)
Sheet | Title | Covers | Key Decisions | For Whom
Sheet 1 | Master Overview | Vision, 11-phase roadmap, this index | Architecture choices at the top level | CTO, Management
Sheet 2 | Database Plan | All 39 tables + tenant_id column · New tables needed · Schema changes | Shared DB vs separate DB → Shared with tenant_id isolation | Engineering Lead
Sheet 3 | Auth & Session | Two-step login · Session design · Role + tenant in token | Company slug → user login flow · JWT vs session cookies | Engineering
Sheet 4 | Trial & License Engine | Account states · Trial rules · DB columns · State machine | 14 vs 30 days · Grace periods · Plan feature gates | Engineering, Product
Sheet 5 | Auto-Expiry & Deletion | 6 cron jobs · 11-step deletion · Table deletion order | Soft delete vs hard delete → Hard delete after 60-day grace | Engineering
Sheet 6 | Per-Tenant Backups | Backup types · Schedule · Retention · Restore procedure | Full dump vs per-tenant export → Both, different schedules | Engineering, Ops
Sheet 7 | Billing & Plans | 3 plan tiers · Razorpay integration · Webhook handling · Upgrade/downgrade | Monthly billing · Annual discount · Per-user add-ons | Engineering, Finance
Sheet 8 | Integrations Impact | WhatsApp, email, file storage per-tenant · API changes | Shared vs per-tenant WhatsApp number → Per-tenant sender | Engineering
Sheet 9 | Tenant & Super Admin | Tenant portal features · Super-admin panel features | What tenants control vs what only super-admin can do | Product, Engineering
Sheet 10 | Deployment & Infra | Replit hosting → VPS migration path · Domain setup · Env vars | Single app serves all tenants · Subdomain routing plan | DevOps, CTO
Sheet 11 | Customization Pricing | Fixed-price model · Feature scope by tier · Sales process | No hourly billing · 50% advance · Feature list per price | Sales, Management
Sheet 12 | Implementation Checklist | 50+ tasks across all phases with priority and status | Master tracking sheet for all engineering work | Engineering Lead

## 2. Database Plan
Database Plan — Multitenancy Migration
All 39 existing tables + tenant_id · 5 new SaaS tables · Schema additions · Migration strategy
ARCHITECTURE DECISION: SHARED DATABASE, TENANT_ID ISOLATION
Chosen approach: Single PostgreSQL database. Every table has a tenant_id column (DEFAULT 1 for existing data). All queries in the API middleware are automatically scoped: WHERE tenant_id = currentTenantId(). This is simpler than separate DBs per tenant, cheaper to operate, and sufficient for our scale target (300 tenants within 3 years). Tenant isolation is enforced at the application layer by middleware — not at the DB level. All new tables also carry tenant_id.
PART A — NEW SAAS TABLES TO CREATE
Table Name | Purpose | Key Columns | Type | Indexed On | Notes
tenants | One row per company/customer using Kinto | id, name, slug, owner_email, plan_id, account_status, trial_start_date, trial_end_date, grace_period_end, scheduled_deletion_date, payment_status, data_export_url, deleted_at, data_purged, logo_url, primary_color, created_at | Master | slug (UNIQUE), plan_id, account_status | NEVER DELETE this row even after tenant deletion. account_status tracks lifecycle.
plans | Subscription plan definitions (Starter, Pro, Enterprise) | id, name, price_monthly, price_annual, trial_days, max_users, max_storage_gb, features (jsonb), is_active | Master | is_active | features JSONB: { bom:true, whatsapp:true, mis:true, api:false } — used by license middleware to gate features
subscriptions | Billing subscription records per tenant | id, tenant_id, plan_id, razorpay_sub_id, status, current_period_start, current_period_end, cancel_at, created_at | Transaction | tenant_id, razorpay_sub_id, status | status: created, authenticated, active, paused, halted, cancelled, completed, expired
billing_payments | Individual payment records from Razorpay webhooks | id, tenant_id, subscription_id, razorpay_payment_id, amount, currency, status, paid_at, invoice_url | Transaction | tenant_id, subscription_id, status | Immutable log. One row per payment attempt. Never update, only insert.
deletion_audit | Permanent record of every tenant deletion — legal compliance | id, tenant_id, tenant_name, owner_email, deleted_at, rows_deleted (jsonb), export_url, export_expires_at, deleted_by | Audit | tenant_id, deleted_at | NEVER DELETE rows from this table. rows_deleted: { invoices:142, customers:38, ... }
PART B — TENANT_ID COLUMN: ALL 39 EXISTING TABLES
Table Name | Category | Migration SQL | Data Risk | Test Query | Migration Order
users | Auth | ALTER TABLE users ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low — existing users → tenant 1 | SELECT COUNT(*) FROM users WHERE tenant_id IS NULL | 1 — First (others depend on users)
customers | Master | ALTER TABLE customers ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | SELECT COUNT(*) FROM customers WHERE tenant_id IS NULL | 2
vendors | Master | ALTER TABLE vendors ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | SELECT COUNT(*) FROM vendors WHERE tenant_id IS NULL | 3
products | Master | ALTER TABLE products ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | SELECT COUNT(*) FROM products WHERE tenant_id IS NULL | 4
raw_materials | Master | ALTER TABLE raw_materials ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 5
product_categories | Master | ALTER TABLE product_categories ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 6
product_types | Master | ALTER TABLE product_types ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 7
roles | Master | ALTER TABLE roles ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 8
role_permissions | Master | ALTER TABLE role_permissions ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 9
invoices | Transaction | ALTER TABLE invoices ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 10
invoice_items | Detail | ALTER TABLE invoice_items ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 11
sales_orders | Transaction | ALTER TABLE sales_orders ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 12
sales_order_items | Detail | ALTER TABLE sales_order_items ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 13
purchase_orders | Transaction | ALTER TABLE purchase_orders ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 14
po_items | Detail | ALTER TABLE po_items ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 15
payments | Transaction | ALTER TABLE payments ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 16
payment_allocations | Detail | ALTER TABLE payment_allocations ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 17
gatepasses | Transaction | ALTER TABLE gatepasses ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 18
dispatch_events | Detail | ALTER TABLE dispatch_events ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 19
productions | Transaction | ALTER TABLE productions ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 20
production_entries | Detail | ALTER TABLE production_entries ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 21
inventory_batches | Inventory | ALTER TABLE inventory_batches ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 22
finished_goods | Inventory | ALTER TABLE finished_goods ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 23
bom_items | Master | ALTER TABLE bom_items ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 24
expenses | Transaction | ALTER TABLE expenses ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 25
monthly_expenses | Transaction | ALTER TABLE monthly_expenses ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 26
credit_notes | Transaction | ALTER TABLE credit_notes ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 27
debit_notes | Transaction | ALTER TABLE debit_notes ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 28
advances | Transaction | ALTER TABLE advances ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 29
documents | Master | ALTER TABLE documents ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 30
journal_entries | Accounting | ALTER TABLE journal_entries ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 31
journal_lines | Detail | ALTER TABLE journal_lines ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 32
chart_of_accounts | Accounting | ALTER TABLE chart_of_accounts ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 33
sales_returns | Transaction | ALTER TABLE sales_returns ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 34
cash_register | Transaction | ALTER TABLE cash_register ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 35
checklist_templates | Master | ALTER TABLE checklist_templates ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 36
checklist_responses | Transaction | ALTER TABLE checklist_responses ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 37
audit_logs | Audit | ALTER TABLE audit_logs ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 38
sessions | Auth | ALTER TABLE sessions ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1 NOT NULL | Low | — | 39

## 3. Auth & Session
Auth & Session Design
Two-step login · Session structure · Middleware · Role + Tenant in every request
TWO-STEP LOGIN FLOW
Step | User Action | System Action | On Failure
Step 1 — Company Lookup | User visits kintoops.com/login Enters company slug (e.g. "acme-industries") | Look up tenants table: SELECT * FROM tenants WHERE slug = $1 Check account_status — if suspended/deleted → show error Check if tenant is active/trial | Slug not found → "Company not found. Check your company URL." Account suspended → "Account suspended. Contact support."
Step 2 — User Login | User enters email + password on company-specific login page | Authenticate: SELECT * FROM users WHERE email=$1 AND tenant_id=$2 Verify scrypt password hash Create session: { userId, tenantId, tenantSlug, planId, accountStatus, roles } | Wrong password → "Invalid credentials" User not found in this tenant → "User not found"
Session Created | — | Store session in DB with tenant_id. Every subsequent API request reads tenant_id from session. Middleware attaches: req.tenantId, req.userId, req.plan, req.roles | Session expired → redirect to /login
Feature Gate Check | User tries to access a feature | License middleware checks: plans.features[featureName] for this tenant's plan If not in plan → 403 with "Upgrade to Professional to access this feature" | Show upgrade prompt with link to billing page
SESSION OBJECT STRUCTURE
Field | Type | Value Example | Purpose
userId | integer | 42 | Identifies the logged-in user
tenantId | integer | 7 | Scopes all DB queries to this tenant
tenantSlug | string | "acme-industries" | Used for subdomain routing and display
planId | integer | 2 | References plans table (1=Starter,2=Pro,3=Enterprise)
planFeatures | jsonb | { bom:true, whatsapp:true, mis:true, api:false } | Feature gate map — cached from plans table on login
accountStatus | string | "trial" | Current account state — checked on every request
trialEndsAt | date | "2026-04-21" | Shown in UI as countdown. Checked by middleware.
roles | string[] | ["admin","manager"] | User's roles within this tenant
sessionId | uuid | abc-123-... | Used to invalidate session on logout or suspension
API MIDDLEWARE CHAIN (every request)
Middleware | Checks | On Pass | On Fail
1. Session Auth | Valid session cookie exists | Attaches req.session to request | 401 — redirect to /login
2. Tenant Resolver | req.session.tenantId is valid. Tenant row exists in DB. | Sets req.tenantId for use in all route handlers | 403 — "Tenant not found"
3. Account Status Check | account_status IN ("trial","active","grace_period") If grace_period → sets req.readOnly=true | Allows request to proceed (with readOnly flag if grace_period) | 403 — "Account suspended. Reactivate to continue."
4. Feature Gate | req.plan.features[featureName] === true for gated routes | Allows access to feature | 403 — "This feature requires the Professional plan. Upgrade to access."
5. Role Permission | User's roles have permission for this route (from role_permissions table) | Allows the action | 403 — "You do not have permission to perform this action."
6. Read-Only Enforcement | If req.readOnly === true AND method is POST/PUT/PATCH/DELETE | Block — grace period accounts cannot write new data | 403 — "Account in grace period. Subscribe to continue creating records."

## 4. Trial & License Engine
Trial System & License Engine
Account states · Trial rules · DB columns · Feature gates · Reminder schedule
TRIAL PLAN CONFIGURATION
Plan | Trial Duration | Features During Trial | Trial Start Trigger | Reminder Schedule | After Trial Ends
Starter (₹999/mo) | 14 days | Full Starter: Invoicing, GST, Accounting, Expenses, Reports, Purchase Orders | Self-signup OR admin account creation | Day 7: "7 days left" email+WhatsApp Day 12: "2 days left" email Day 14: "Trial ended" email+WhatsApp | → grace_period (7 days). Read-only. Subscribe to reactivate.
Professional (₹2,499/mo) | 14 days | All Pro: BOM, WhatsApp Checklists, MIS, Documents + all Starter features | Self-signup OR admin upgrades existing trial to Pro | Day 7: "7 days left" email Day 12: "2 days left" email Day 14: "Trial ended" email+WhatsApp | → grace_period (7 days). Downgrade to Starter if previously Starter, else suspended.
Enterprise (Custom) | 30 days | All Enterprise: API access, unlimited users, custom reports + all Pro features | Manual activation by super-admin only (sales-assisted) | Day 15, Day 25, Day 28, Day 30 | → grace_period (14 days). Account manager contacts. Manual extension possible.
ACCOUNT STATE MACHINE
State | Code | Meaning | What Is Allowed | What Is Blocked | Auto-Transitions To
TRIAL | trial | Within free trial window | Full feature access per plan All data entry All modules | Customization (Enterprise-only features) | → GRACE_PERIOD on trial_end_date
ACTIVE | active | Paid subscriber in good standing | Full feature access per plan All modules All data entry | — | → GRACE_PERIOD on payment failure → SUSPENDED on explicit cancel after period end
GRACE PERIOD | grace_period | Trial ended OR payment failed 7 days (Starter/Pro) 14 days (Enterprise) | Read-only access View all data Download reports Make payment to reactivate | All POST/PUT/PATCH/DELETE New invoices, orders, entries | → ACTIVE on payment received → SUSPENDED on grace_period_end
SUSPENDED | suspended | Grace period expired. Account frozen. | Login allowed (read-only) View data Download data export Make payment to reactivate | All write operations All new data entry | → ACTIVE on payment → SCHEDULED_DELETION after 60 days
SCHEDULED DELETION | scheduled_deletion | 60-day suspension passed. Deletion queued. | Nothing — login blocked Only super-admin can view | All actions | → DELETED on scheduled_deletion_date
DELETED | deleted | All data permanently erased. Tenant row kept for audit. | Nothing | Everything | Terminal state — no further transitions
TENANT TABLE — TRIAL/BILLING COLUMNS TO ADD
Column | Type | Purpose | Example Value | Set By | Notes
plan_id | integer FK → plans.id | Current plan | 2 (Professional) | System on signup | Changes on upgrade/downgrade
account_status | varchar(30) | State machine status | trial | System | Values: trial, active, grace_period, suspended, scheduled_deletion, deleted
trial_start_date | date | Trial start | 2026-04-07 | System on signup | Auto-set on account creation
trial_end_date | date | Trial expiry (start + trial_days) | 2026-04-21 | System on signup | Checked by nightly cron
trial_days | integer | Trial length stored per tenant | 14 | Copied from plan | Preserved even if plan changes later
subscription_start | date | When paid subscription began | null (still trial) | System on payment | Null = never paid
subscription_end | date | Current billing period end | 2026-05-07 | System on payment | Null = monthly rolling or trial
grace_period_end | date | Grace period expiry | null | System on trial expiry / payment failure | Set by cron job
scheduled_deletion_date | date | Permanent deletion date (suspension + 60d) | null | System on suspension | 60 days after suspension
payment_status | varchar(20) | Latest payment status | pending | Razorpay webhook | Values: paid, pending, failed, refunded
last_reminder_sent | timestamptz | Last trial reminder timestamp | 2026-04-14 09:00 | Cron job | Prevents duplicate reminder sends
data_export_url | text | Signed URL to last data export | https://r2.../export.zip | System before deletion | Valid 30 days. Sent to tenant email.

## 5. Auto-Expiry & Deletion
Auto-Expiry, Suspension & Permanent Deletion
6 cron jobs · 11-step deletion sequence · Table deletion order
NIGHTLY CRON JOB SCHEDULE
Time (IST) | Job Name | Trigger Condition | Action | Notification | Logged To
6:00 AM | trial-reminder-job | account_status=trial AND trial_end_date IN (today+7, today+2, today+1) | Send reminder. Update last_reminder_sent. | Email + WhatsApp: "X days left in trial" | audit_logs: trial_reminder_sent
6:30 AM | trial-expiry-job | account_status=trial AND trial_end_date < today | SET account_status=grace_period SET grace_period_end=today+7 (or +14 Enterprise) Block all writes | Email + WhatsApp: "Trial ended. 7 days to subscribe." | audit_logs: trial_expired
7:00 AM | grace-expiry-job | account_status=grace_period AND grace_period_end < today | SET account_status=suspended SET scheduled_deletion_date=today+60 Login still works (read-only) | Email + WhatsApp: "Account suspended. Export data now. Deletion in 60 days." | audit_logs: account_suspended
7:30 AM | deletion-warning-job | account_status=suspended AND scheduled_deletion_date IN (today+30, today+7, today+3, today+1) | Generate data export ZIP. Upload to R2. SET data_export_url. Send email. | Email: "Data deleted on [date]. Download export: [link]" | audit_logs: deletion_warning_sent
8:00 AM | permanent-deletion-job | account_status=suspended AND scheduled_deletion_date <= today | Run 11-step deletion sequence (see below). SET account_status=deleted. | Email: "Your Kinto account data has been permanently deleted." | deletion_audit table: permanent record
8:30 AM | payment-failure-job | account_status=active AND subscription_end < today AND payment_status != paid | SET account_status=grace_period SET grace_period_end=today+7 | Email: "Payment failed. Update payment within 7 days." | audit_logs: payment_failure_grace_started
11-STEP PERMANENT DATA DELETION SEQUENCE
Step | Operation | Description | SQL / Code | Reversible? | Failure Action
1 | Export tenant data | Generate full ZIP export (all tables WHERE tenant_id=X) + all files | exportTenantData(tenantId) → R2 upload → signed URL | Yes — export kept 90d after deletion | If export fails → ABORT entire job. Alert super-admin.
2 | Revoke sessions | Invalidate all active sessions for this tenant | DELETE FROM sessions WHERE tenant_id = X | Yes — no data lost | Log and continue
3 | Block login | Prevent any new login while deletion proceeds | UPDATE tenants SET account_status="scheduled_deletion" WHERE id=X | Yes — admin can revert | Must succeed or abort
4 | Delete detail tables | Delete all child/line-item records | DELETE FROM invoice_items, journal_lines, sales_order_items, po_items, bom_items, production_entries, dispatch_events, payment_allocations, expense_items WHERE tenant_id=X | No | Wrap in transaction. Rollback on error.
5 | Delete parent tables | Delete all header/transaction records | DELETE FROM invoices, sales_orders, purchase_orders, productions, gatepasses, payments, expenses, journal_entries, credit_notes, debit_notes, advances, cash_register, sales_returns WHERE tenant_id=X | No | Transaction. Rollback on error.
6 | Delete master data | Delete customers, vendors, products, raw materials, BOM, inventory | DELETE FROM customers, vendors, products, raw_materials, inventory_batches, finished_goods, chart_of_accounts, documents, checklist_templates, monthly_expenses, checklist_responses WHERE tenant_id=X | No | Transaction. Rollback on error.
7 | Delete role data | Delete roles, permissions, audit logs for this tenant | DELETE FROM role_permissions, roles, audit_logs WHERE tenant_id=X | No | Transaction. Rollback on error.
8 | Delete users | Remove all user accounts for this tenant | DELETE FROM users WHERE tenant_id=X | No | After all user-dependent records are gone.
9 | Delete files from R2 | Remove all uploaded files under tenants/{id}/ prefix | deleteFolder(r2, "tenants/"+tenantId) | No | Log files deleted. Alert if any fail.
10 | Mark tenant deleted | Update tenant row. DO NOT delete the row — needed for audit. | UPDATE tenants SET account_status="deleted", deleted_at=NOW(), data_purged=true WHERE id=X | N/A — row kept | Must succeed or job incomplete.
11 | Write deletion audit + send email | Permanent audit record + final email to tenant owner | INSERT INTO deletion_audit (...) sendEmail(owner_email, "Data permanently deleted. Export: [url]") | N/A — audit is permanent | Email failure: log and retry once.

## 6. Per-Tenant Backups
Per-Tenant Backup Strategy
Backup types · Schedule · Retention · Restore procedure · Tenant data isolation
BACKUP TYPES AND SCHEDULE
Backup Type | Scope | Frequency | What is Backed Up | Retention | Storage Location
Full DB Snapshot | Entire database (all tenants) | Daily at 2:00 AM IST | Complete PostgreSQL dump — all tables, all tenants, schema + data | 30 days rolling | Neon auto-backup + copy to Cloudflare R2: /backups/full/{date}/
Per-Tenant Export | Single tenant (tenant_id=X) | Weekly Sundays 3:00 AM IST + on-demand via admin panel | All rows for that tenant exported as JSON+CSV ZIP | 90 days (or until deletion + 30 days) | R2: /backups/tenants/{tenant_id}/{date}/
File & Document Backup | Uploaded files per tenant | Daily mirror sync | All uploaded files — invoice PDFs, photos, documents, logos | 30 days versioning (R2 versioning enabled) | R2: /uploads/tenants/{tenant_id}/ with versioning
Pre-Deletion Backup | Single tenant (forced before deletion) | One-time — triggered automatically before deletion job | Full data export: JSON of all tables + all files as single ZIP | 90 days after deletion (legal hold) | R2: /deletion-exports/tenants/{tenant_id}/
WAL / PITR Logs | Entire DB (Neon-managed) | Continuous — every 5 minutes | PostgreSQL Write-Ahead Logs. Enables point-in-time restore. | 7 days (Neon built-in PITR) | Neon DB managed — no action needed
Schema / Migrations | DB schema only | On every deployment | Drizzle migration files + schema snapshot | Indefinite — version controlled | GitHub repo + R2: /backups/schema/
RETENTION POLICY SUMMARY
Backup Type | Active Tenant | Suspended Tenant | Post-Deletion | Legal Hold?
Full DB Snapshot | 30 days rolling | 30 days rolling | N/A — other tenant data stays | No
Per-Tenant Weekly Export | 90 days | 90 days from last export | 90 days from deletion date | No
File Uploads | 30 days versioned | 30 days | 90 days after deletion | No
Pre-Deletion Export | N/A — taken once | N/A | 90 days minimum (hard limit) | Yes — cannot be deleted before 90 days
WAL / PITR | 7 days (Neon) | 7 days | Not retained | No
Schema / Migrations | Indefinite (Git) | Indefinite | Indefinite | Yes — never auto-deleted
deletion_audit table row | Permanent | Permanent | Permanent — row never deleted | Yes — legal compliance
RESTORE PROCEDURE
Restore Type | Step | Action | Command / Tool | Who Approves
Full DB Restore | 1. Maintenance mode | Put app in maintenance mode | pm2 stop kinto | CTO
Full DB Restore | 2. Restore dump | Load backup into DB | pg_restore -d kinto_db latest.sql.gz | CTO
Full DB Restore | 3. Verify + restart | Check row counts. Restart app. | pm2 start kinto | CTO
Single Tenant Restore | 1. Restore to staging | Load backup to staging DB | pg_restore -d kinto_staging backup.sql.gz | Super-Admin
Single Tenant Restore | 2. Extract rows | Query only affected tenant | SELECT * FROM [table] WHERE tenant_id=X | Super-Admin
Single Tenant Restore | 3. Re-import to prod | Insert rows in transaction | BEGIN; INSERT INTO prod... SELECT...; COMMIT; | Super-Admin + 2nd approval
Single Tenant Restore | 4. Notify tenant | Email tenant of restored data | Auto-email with what changed | Automated
PITR (Point-in-Time) | 1. Choose timestamp | Select restore time in Neon dashboard | Neon console → select time | Super-Admin
PITR (Point-in-Time) | 2. Branch DB | Neon creates branch at that timestamp | Neon console → Create Branch | Automated (Neon)
PITR (Point-in-Time) | 3. Verify + promote | Verify data. Promote if correct. | Neon console → Promote Branch | CTO approval required

## 7. Billing & Plans
Billing & Subscription Plans
3 plan tiers · Razorpay integration · Webhook events · Upgrade/downgrade logic
PLAN TIERS — FEATURE MATRIX
Feature / Module | Starter ₹999/mo | Professional ₹2,499/mo | Enterprise Custom
Max Users | 3 | 10 | Unlimited
Storage | 5 GB | 25 GB | Unlimited
GST Invoicing | ✓ | ✓ | ✓
Purchase Orders | ✓ | ✓ | ✓
Double-Entry Accounting | ✓ | ✓ | ✓
Expense Tracking | ✓ | ✓ | ✓
Pending Payments Dashboard | ✓ | ✓ | ✓
Standard Reports | ✓ | ✓ | ✓
BOM & Production Tracking | ✗ | ✓ | ✓
WhatsApp Checklists | ✗ | ✓ | ✓
Inventory Batch Management (FIFO) | ✗ | ✓ | ✓
Dispatch & Gatepass Tracking | ✗ | ✓ | ✓
Sales Returns & Credit Notes | ✗ | ✓ | ✓
Document Management | ✗ | ✓ | ✓
Monthly Expense Tracking | ✗ | ✓ | ✓
MIS Executive Dashboard | ✗ | ✗ | ✓
REST API Access | ✗ | ✗ | ✓
Custom Reports | ✗ | ✗ | ✓
White-labeling (custom logo/colors) | ✗ | ✗ | ✓
Dedicated Account Manager | ✗ | ✗ | ✓
SLA (99.9% uptime guarantee) | ✗ | ✗ | ✓
Trial Duration | 14 days | 14 days | 30 days
Annual Discount | 2 months free | 2 months free | Negotiated
Email Support | ✓ | ✓ | ✓
Phone / WhatsApp Support | ✗ | ✓ | ✓
RAZORPAY WEBHOOK EVENTS & ACTIONS
Webhook Event | Trigger | System Action | Notification Sent
subscription.activated | Customer completes first payment after trial | SET account_status=active SET subscription_start=today SET payment_status=paid Record in billing_payments | Email: "Subscription active! Welcome to Kinto Professional."
subscription.charged | Monthly recurring payment successful | SET subscription_end=next_period_end SET payment_status=paid Record in billing_payments | Email: "Payment received. Invoice attached."
subscription.payment_failed | Payment attempt failed (card issue, insufficient funds) | SET payment_status=failed Start grace period if active sub (see cron job) | Email: "Payment failed. Update your payment method within 7 days."
subscription.cancelled | Customer cancels subscription | SET subscription_end=end_of_current_period Plan: continue until period end, then expire | Email: "Subscription cancelled. Access continues until [date]."
subscription.completed | Subscription period ended (if fixed-term) | SET account_status=grace_period SET grace_period_end=today+7 | Email: "Subscription ended. Renew to continue."
subscription.halted | Too many payment failures — Razorpay halts | SET account_status=grace_period immediately | Email: "Subscription halted by payment processor. Please update card."
payment.captured | One-time payment captured (e.g. customization fee) | Record in billing_payments with type=customization | Email: "Payment received for [service]. Thank you."
refund.processed | Refund issued | Record in billing_payments with status=refunded | Email: "Refund of ₹X processed. 5-7 working days to reflect."

## 8. Integrations Impact
Integrations Impact — Per-Tenant Configuration
WhatsApp · Email · File Storage · API keys — all scoped per tenant
INTEGRATION CHANGES FOR MULTITENANCY
Integration | Current (Single Tenant) | Multitenancy Change | Per-Tenant Config Needed | Storage Location | Plan Gate
WhatsApp (Colloki / Meta WABA) | Single phone number ID and access token in .env | Each tenant can configure their own WhatsApp Business number OR share the Kinto platform number | whatsapp_phone_number_id, whatsapp_access_token (optional — if own number) If not configured → use Kinto platform number | tenant_integrations table: { whatsapp_phone_number_id, whatsapp_access_token } | Professional and above
Email (Office 365 / SendGrid) | Single platform email in .env — all emails from Kinto address | Emails sent as "From: Kinto (on behalf of [Tenant Name])" or from tenant's own SMTP | email_from_name, email_from_address (optional — tenant SMTP) Default: platform email | tenant_integrations table: { email_smtp_host, email_smtp_user, email_smtp_pass } | Enterprise only (custom SMTP). All plans get platform email.
File Storage (Cloudflare R2) | All files in /uploads/ with no tenant scoping | All files stored under /uploads/tenants/{tenant_id}/ prefix. Strict prefix enforcement. | No per-tenant API key needed — all use platform R2 bucket, scoped by path prefix | R2 bucket path: /uploads/tenants/{tenant_id}/ | All plans (storage limit enforced per plan)
Razorpay | Not currently integrated | New integration for SaaS billing. Per-tenant subscription on Razorpay. | razorpay_subscription_id stored per tenant in subscriptions table Webhook verifies against platform Razorpay account | subscriptions.razorpay_sub_id | All plans
Neon PostgreSQL | Single DB for all data | No change to connection. Isolation via tenant_id column in all queries. | No per-tenant config — shared DB with middleware isolation | Single DATABASE_URL in .env | All plans
Drizzle ORM | All queries without tenant filter | All queries must pass through getTenantId() middleware. Queries auto-include WHERE tenant_id=X. | No per-tenant config — all queries use req.tenantId from session | Server-side middleware | All plans
NEW TABLE: tenant_integrations
Stores per-tenant integration credentials. All sensitive values encrypted at rest. Never returned to frontend.
Column | Type | Example | Purpose
id | serial PK | 1 | —
tenant_id | integer FK → tenants.id | 7 | Links to tenant
integration_name | varchar(50) | "whatsapp" | Identifies which integration
config | jsonb (encrypted) | { phone_number_id: "...", access_token: "..." } | Per-tenant credentials — AES-256 encrypted
is_active | boolean | true | Whether this integration is enabled for this tenant
created_at | timestamptz | 2026-04-07 10:00 | —
updated_at | timestamptz | 2026-04-07 10:00 | —

## 9. Deployment & Infra
Deployment & Infrastructure Plan
Replit hosting → VPS migration · Domain/subdomain routing · Env vars · Security
HOSTING STRATEGY — PHASE-BY-PHASE
Phase | Hosting | Tenant Access URL | Capacity | When to Move
Launch Phase (0–50 tenants) | Replit Deployment (Autoscale) | kintoops.com/{company-slug} or subdomain via Replit custom domain | Up to 50 tenants comfortable on Replit Autoscale | Move to VPS when monthly Replit cost > VPS equivalent OR need custom subdomain per tenant
Growth Phase (50–200 tenants) | VPS — Hetzner or DigitalOcean (4 vCPU, 8GB RAM) | {company-slug}.kintoops.com — wildcard subdomain via Nginx | ~200 concurrent tenants. Database still on Neon. | Move to dedicated DB when Neon cost grows OR latency increases
Scale Phase (200+ tenants) | VPS cluster (2+ nodes) + load balancer | {company-slug}.kintoops.com | Horizontal scaling. Add nodes as needed. | Standard DevOps scale-out
ENVIRONMENT VARIABLES — PLATFORM LEVEL
Variable | Value Type | Purpose | Secret?
DATABASE_URL | Connection string | Neon PostgreSQL connection | Yes — secret
SESSION_SECRET | Random 64-char string | Express session signing | Yes — secret
RAZORPAY_KEY_ID | Razorpay API key | Payment integration | Yes — secret
RAZORPAY_KEY_SECRET | Razorpay secret | Payment webhook verification | Yes — secret
COLLOKI_FLOW_API_KEY | Colloki API key | Platform-level WhatsApp (fallback) | Yes — secret
WHATSAPP_PHONE_NUMBER_ID | Meta WABA phone ID | Platform WhatsApp sender (default) | Yes — secret
WHATSAPP_ACCESS_TOKEN | Meta WABA token | Platform WhatsApp sender (default) | Yes — secret
R2_ACCOUNT_ID | Cloudflare account ID | File storage bucket access | Yes — secret
R2_ACCESS_KEY_ID | Cloudflare R2 key | File storage access | Yes — secret
R2_SECRET_ACCESS_KEY | Cloudflare R2 secret | File storage access | Yes — secret
R2_BUCKET_NAME | String: kinto-uploads | R2 bucket name | No
SENDGRID_API_KEY (or SMTP) | API key | Platform email sending | Yes — secret
SUPER_ADMIN_SECRET | Random string | Protects super-admin routes | Yes — secret
NODE_ENV | production/development | Environment detection | No

## 10. Customization Pricing
Customization Pricing — Fixed Price Model
All customization work is quoted at fixed price. No hourly billing. Ever.
PRICING MODEL RULES
Rule 1: All custom work is fixed-price only. No hourly rates. Quote upfront, customer approves, then work begins. Rule 2: Payment terms — 50% advance before work starts, 50% on delivery. Rule 3: Scope is locked at quote acceptance. Changes after start = new quote. Rule 4: Delivery timeline is included in every quote. Delays due to client (missing data, approvals) extend timeline accordingly. Rule 5: Bug fixes on delivered work are free for 30 days. New features are a new quote.
CUSTOMIZATION PRICE LIST
Customization Type | Base Price (₹) | Complexity Add-on | Delivery Time | Includes | Not Included
Custom Report / MIS View | ₹8,000 – ₹15,000 | Complex calculations: +₹5,000 Charts/graphs: +₹3,000 | 5–10 working days | Report design, backend query, PDF export, frontend display | Data entry, historical data import
New Module (small) | ₹25,000 – ₹50,000 | Integration with 3rd party: +₹10,000 Mobile optimization: +₹8,000 | 2–4 weeks | CRUD + workflow + reports for new module | Data migration from old system
New Module (large / complex) | ₹75,000 – ₹1,50,000 | Multi-user approval flow: +₹15,000 WhatsApp integration: +₹20,000 | 6–12 weeks | Full module: master + transactions + reports + role permissions | Hardware, SMS costs, API subscriptions
WhatsApp Flow Customization | ₹12,000 – ₹25,000 | Custom AI response logic: +₹10,000 Multiple languages: +₹8,000 | 1–2 weeks | Flow design, Colloki/Meta config, testing | WhatsApp Business API fees (paid by client)
Data Migration (Tally/Vyapaar/Excel) | ₹10,000 – ₹30,000 | Fuzzy matching required: +₹5,000 Multiple years of history: +₹8,000/yr | 1–2 weeks per data set | Import scripts, validation, reconciliation report | Source system errors/inconsistencies
Custom Branding Package | ₹5,000 – ₹10,000 | Custom domain setup: +₹3,000 | 2–3 working days | Logo, colors, report headers, email signature per tenant | Domain registration cost (paid by client)
API Integration (3rd party) | ₹15,000 – ₹40,000 | Complex auth (OAuth etc): +₹8,000 Bidirectional sync: +₹12,000 | 2–4 weeks | Integration design, testing, error handling | 3rd party API subscription fees
User Training & Onboarding | ₹5,000 / session (2 hrs) | Multi-location training: +₹3,000/location Video recording: +₹5,000 | Scheduled on delivery | 2-hour video call training, documentation | Travel (for on-site training — quoted separately)

## 11. Admin Panels
Tenant Admin & Super Admin Panel Design
What each portal does · Who sees what · Feature scope
TENANT ADMIN PORTAL (Each tenant manages their own)
Section | Features | Who Can Access | Notes
Company Settings | Company name, logo, address, GST number, financial year Primary contact, timezone, currency | Admin role only | Edits reflect on all invoices, reports, emails immediately
User Management | Add/remove users, set passwords, assign roles View last login, active sessions | Admin role only | Cannot exceed plan's max user limit. Upgrade prompt if limit reached.
Subscription & Billing | Current plan, trial days remaining, next billing date Upgrade/downgrade plan, payment history, download invoices Cancel subscription button | Admin role only | Cancel = access until end of current period. No refund for mid-period cancel.
Data Export | Download all company data as ZIP (JSON + CSV) Available anytime — even during suspension | Admin role only | Export generated fresh each time. Sent via email if large. Also available before deletion.
WhatsApp Settings | Configure own WhatsApp Business number (Pro/Enterprise) Or use Kinto platform number | Admin role only | Requires Meta WABA setup. Kinto provides guide.
Notification Settings | Set reminder schedules, notification recipients per event type Enable/disable WhatsApp vs email per notification | Admin role only | —
Branding (Enterprise) | Upload logo, set primary color, custom report header Custom email from-name | Admin role — Enterprise plan only | Report PDFs, invoice headers, email signatures all updated.
Audit Log | View last 90 days of user activity within tenant Filter by user, action type, date | Admin + Manager roles | Cannot see other tenants. Super-admin can see all.
SUPER ADMIN PANEL (Kinto internal team only)
Section | Features | Access Level | Risk Level
Tenant Dashboard | All tenants list: name, plan, status, trial days left, revenue Filter by status, plan, created date Search by company name or email | Super-admin only (SUPER_ADMIN_SECRET env var required) | Read — Low risk
Tenant Management | View single tenant detail Extend trial (set new trial_end_date) Manually activate / suspend / restore Switch plan (up/downgrade without payment) | Super-admin only | Write — Medium risk. Logged to audit.
Impersonation | Log in as any tenant's admin user (read-only mode) See exactly what the tenant sees for support purposes | Super-admin only | Write — High risk. Always logged with super-admin ID + reason.
Billing Override | Mark payment as paid (for bank transfer customers) Issue manual credit Cancel without penalty | Super-admin only | Write — High risk. Requires reason field.
Deletion Controls | View scheduled deletions Cancel deletion (extend 30 days) Trigger immediate deletion (with 2nd approval) Download tenant's data export before deletion | Super-admin only — immediate deletion requires 2nd super-admin approval | Delete — Critical. Full audit logged.
System Health | Cron job status, last run, success/failure Backup status, last backup timestamp R2 storage usage per tenant Failed notification log | Super-admin only | Read — Low risk
Revenue Analytics | MRR, ARR, churn rate, trial conversion rate Revenue by plan, new signups per month Customization revenue tracker | Super-admin only | Read — Low risk

## 12. Implementation Checklist
Master Implementation Checklist — All Phases
50 tasks across 11 phases. Update Status column as work progresses.
# | Task | Phase | Category | Description / Acceptance Criteria | Priority | Status
1 | Add tenant_id to all 39 tables | Phase 1 — DB | Database | ALTER TABLE ... ADD COLUMN IF NOT EXISTS tenant_id INT DEFAULT 1. Run for all 39 tables. Verify: SELECT COUNT(*) FROM [table] WHERE tenant_id IS NULL = 0 | P1 | Pending
2 | Create tenants table | Phase 1 — DB | Database | All columns: id, name, slug, owner_email, plan_id, account_status, trial_start_date, trial_end_date, grace_period_end, scheduled_deletion_date, payment_status, data_export_url, deleted_at, data_purged, logo_url, primary_color, created_at | P1 | Pending
3 | Create plans table | Phase 1 — DB | Database | id, name, price_monthly, price_annual, trial_days, max_users, max_storage_gb, features (jsonb), is_active. Seed with 3 plans. | P1 | Pending
4 | Create subscriptions table | Phase 1 — DB | Database | id, tenant_id, plan_id, razorpay_sub_id, status, current_period_start, current_period_end, cancel_at, created_at | P1 | Pending
5 | Create billing_payments table | Phase 1 — DB | Database | id, tenant_id, subscription_id, razorpay_payment_id, amount, status, paid_at, invoice_url. Immutable ledger. | P1 | Pending
6 | Create deletion_audit table | Phase 1 — DB | Database | id, tenant_id, tenant_name, owner_email, deleted_at, rows_deleted (jsonb), export_url, export_expires_at, deleted_by. NEVER delete rows. | P1 | Pending
7 | Create tenant_integrations table | Phase 1 — DB | Database | id, tenant_id, integration_name, config (jsonb encrypted), is_active. For per-tenant WhatsApp/email config. | P1 | Pending
8 | Build company slug lookup (Step 1 login) | Phase 2 — Auth | Backend | POST /api/auth/lookup-tenant. Input: slug. Output: tenantId + plan info. Error: "Company not found" or "Account suspended". | P1 | Pending
9 | Update login to include tenant_id (Step 2 login) | Phase 2 — Auth | Backend | POST /api/auth/login. Add tenantId to WHERE clause. Session must include tenantId, planId, planFeatures, accountStatus. | P1 | Pending
10 | Update session object structure | Phase 2 — Auth | Backend | Session: { userId, tenantId, tenantSlug, planId, planFeatures (jsonb), accountStatus, trialEndsAt, roles } | P1 | Pending
11 | Build two-step login UI | Phase 2 — Auth | Frontend | Step 1: company slug input page. Step 2: email+password page (shows company name). Error states for each step. | P1 | Pending
12 | Build tenant resolver middleware | Phase 3 — API | Backend | On every request: extract tenantId from session. Validate tenant exists. Set req.tenantId. | P1 | Pending
13 | Build account status middleware | Phase 3 — API | Backend | Check account_status. If suspended/deleted → 403. If grace_period → set req.readOnly=true. | P1 | Pending
14 | Build read-only enforcement middleware | Phase 3 — API | Backend | If req.readOnly=true AND method is POST/PUT/PATCH/DELETE → return 403 with grace period message. | P1 | Pending
15 | Build feature gate middleware | Phase 3 — API | Backend | For gated routes (BOM, WhatsApp, MIS, API): check req.session.planFeatures. If not included → 403 with upgrade prompt. | P1 | Pending
16 | Update all 200+ API routes to use tenant_id | Phase 3 — API | Backend | Every DB query must include WHERE tenant_id = req.tenantId. No query should return cross-tenant data. Full audit of all routes. | P1 | Pending
17 | Write integration tests for tenant isolation | Phase 3 — API | Testing | Create two test tenants. Verify Tenant A cannot read Tenant B's data via any API route. 100% routes covered. | P1 | Pending
18 | Build nightly cron job system | Phase 4 — Trial | Backend | 6 cron jobs using node-cron or pg_cron. Each job must be idempotent (safe to run twice). | P1 | Pending
19 | Implement trial-reminder-job | Phase 4 — Trial | Backend | Days 7, 2, 1 before trial end. Send email + WhatsApp. Update last_reminder_sent. Check: does not send duplicate. | P1 | Pending
20 | Implement trial-expiry-job | Phase 4 — Trial | Backend | On trial_end_date: SET account_status=grace_period, SET grace_period_end=+7 days. Log to audit_logs. | P1 | Pending
21 | Implement grace-expiry-job | Phase 4 — Trial | Backend | On grace_period_end: SET account_status=suspended, SET scheduled_deletion_date=+60 days. Send suspension email. | P1 | Pending
22 | Implement deletion-warning-job | Phase 4 — Trial | Backend | 30, 7, 3, 1 day before deletion: generate export, upload to R2, send email with link. | P1 | Pending
23 | Implement permanent-deletion-job | Phase 4 — Trial | Backend | On scheduled_deletion_date: run 11-step deletion sequence. Log to deletion_audit. Send final email. | P1 | Pending
24 | Implement payment-failure-job | Phase 4 — Trial | Backend | On active sub with subscription_end < today and payment_status != paid: start grace period. | P1 | Pending
25 | Update all file upload handlers for tenant scoping | Phase 5 — Files | Backend | All uploads go to /uploads/tenants/{tenantId}/{type}/{filename}. No upload can go outside tenant prefix. | P1 | Pending
26 | Set up Cloudflare R2 bucket structure | Phase 5 — Files | Infrastructure | /backups/full/ · /backups/tenants/{id}/ · /uploads/tenants/{id}/ · /deletion-exports/tenants/{id}/. Enable versioning on uploads. | P1 | Pending
27 | Set R2 lifecycle rules | Phase 5 — Files | Infrastructure | /backups/full/: delete after 30 days. /deletion-exports/: delete after 90 days. Test rules before enabling. | P2 | Pending
28 | Build tenant admin portal — Company Settings | Phase 6 — Portal | Frontend | Edit company name, logo, GST number, address. Changes reflect on all documents immediately. | P2 | Pending
29 | Build tenant admin portal — User Management | Phase 6 — Portal | Frontend | Add/remove users. Assign roles. Show plan user limit. Block add if limit reached with upgrade prompt. | P2 | Pending
30 | Build tenant admin portal — Subscription page | Phase 6 — Portal | Frontend | Current plan. Trial countdown. Upgrade button. Payment history. Cancel button. Annual switch button. | P2 | Pending
31 | Build tenant admin portal — Data Export | Phase 6 — Portal | Frontend | Button: "Download my data". Triggers exportTenantData(). Shows progress. Emails link if large. | P2 | Pending
32 | Build super admin dashboard — Tenant list | Phase 7 — SuperAdmin | Frontend | Table: all tenants, status badge, plan, trial days left, MRR. Filter + search. Links to tenant detail. | P2 | Pending
33 | Build super admin — Tenant detail & management | Phase 7 — SuperAdmin | Frontend | View all tenant info. Extend trial. Activate/suspend/restore. Switch plan. All actions logged. | P2 | Pending
34 | Build super admin — Impersonation | Phase 7 — SuperAdmin | Frontend | Log in as tenant admin (read-only). Reason field required. Logged with super-admin ID + timestamp. | P2 | Pending
35 | Build super admin — Deletion controls | Phase 7 — SuperAdmin | Frontend | View scheduled deletions. Cancel deletion. Trigger immediate deletion (requires 2nd super-admin approval). Download export. | P2 | Pending
36 | Build super admin — System health | Phase 7 — SuperAdmin | Frontend | Cron job status, last run, success/failure log. Backup status. R2 usage per tenant. Failed notifications. | P2 | Pending
37 | Integrate Razorpay subscription API | Phase 8 — Billing | Backend | Create subscription on Razorpay. Store razorpay_sub_id in subscriptions table. Handle plan selection. | P2 | Pending
38 | Build Razorpay webhook handler | Phase 8 — Billing | Backend | Handle all 8 webhook events. Verify signature. Update account_status and payment_status accordingly. | P2 | Pending
39 | Build payment history UI | Phase 8 — Billing | Frontend | List of payments, amounts, dates, status. Download invoice button. Razorpay hosted payment page for unpaid. | P2 | Pending
40 | Build exportTenantData() function | Phase 9 — Backups | Backend | Query all tables WHERE tenant_id=X. Export as JSON+CSV. ZIP everything. Upload to R2. Return signed URL. | P1 | Pending
41 | Configure Neon PITR | Phase 9 — Backups | Infrastructure | Verify 7-day PITR window in Neon dashboard. Test branch creation + data verification. Document restore procedure. | P1 | Pending
42 | Build weekly per-tenant backup cron job | Phase 9 — Backups | Backend | Sunday 3:00 AM: for each active tenant, run exportTenantData(), upload to R2 /backups/tenants/{id}/{date}/. | P2 | Pending
43 | Test full 11-step deletion on staging | Phase 9 — Backups | Testing | Create test tenant. Run deletion job. Verify: 0 rows in all tables for that tenant_id. Export retained. Email sent. Audit logged. | P1 | Pending
44 | Build trial reminder email templates (3 templates) | Phase 10 — Notifications | Backend | 7-day, 2-day, expired. Upgrade CTA in each. WhatsApp template (requires WABA pre-approval from Meta). | P2 | Pending
45 | Build suspension + deletion warning email templates | Phase 10 — Notifications | Backend | Suspension email (1). Deletion warnings at 30d, 7d, 3d, 1d (4 templates). Each includes fresh export link. | P2 | Pending
46 | Per-tenant notification settings | Phase 10 — Notifications | Backend + Frontend | tenant_integrations: per-tenant WhatsApp sender. Notification settings: which events → email vs WhatsApp. | P3 | Pending
47 | Build white-labeling system (Enterprise) | Phase 11 — Branding | Backend + Frontend | Tenant logo + primary color → applied to all report PDFs, invoice headers, email signatures. | P3 | Pending
48 | Custom domain support (Enterprise) | Phase 11 — Branding | Infrastructure | Wildcard subdomain: {slug}.kintoops.com. Nginx config. SSL via Let's Encrypt wildcard cert. | P3 | Pending
49 | Write end-to-end tests for trial flow | General — Testing | Testing | Simulate: signup → trial → expiry → grace → suspension → deletion. Verify each state transition and notification. | P1 | Pending
50 | Update Privacy Policy for data retention | General — Legal | Legal | Document: retention = 90 days post-deletion. Right to erasure. Data export on request. PDPB compliance note. | P2 | Pending