## Summary Dashboard
SwachERP × Gold & Jewellery ERP — Cost Estimator
Build Cost Estimate · Resources · Timeline · All amounts in Indian Rupees (₹)
Total Build Days | Total Resources | Dev Cost (₹) | Infra Cost (₹) | Domain Expert (₹) | TOTAL COST (₹)
120 | 6 | 4350000 | 210000 | 180000 | 4740000
Module / Phase | Dev Days | Resources | Dev Cost (₹) | Domain Expert(₹) | Customization(₹)
Phase 1 — JW Dashboard & Metal Rates | 5 | 2 | 96000 | 15000 | 10000
Phase 2 — Items Master & Design Library | 8 | 2 | 154000 | 20000 | 15000
Phase 3 — Estimates Builder | 10 | 3 | 240000 | 25000 | 20000
Phase 4 — Repairs Management | 8 | 2 | 154000 | 20000 | 15000
Phase 5 — Karigar Management | 10 | 3 | 240000 | 30000 | 20000
Phase 6 — Jobwork Orders | 7 | 2 | 134000 | 20000 | 15000
Phase 7 — Production Orders (15 stages) | 25 | 3 | 600000 | 50000 | 40000
Phase 8 — Bullion Trading & Transactions | 12 | 3 | 288000 | 35000 | 25000
Phase 9 — Chit Schemes | 10 | 2 | 192000 | 25000 | 20000
Phase 10 — Hallmarking Register | 5 | 2 | 96000 | 15000 | 10000
Phase 11 — Customer Buyback Module | 4 | 2 | 77000 | 10000 | 8000
Phase 12 — MIS & JW Analytics | 8 | 2 | 154000 | 20000 | 15000
Phase 13 — HRMS Karigar Payroll Ext. | 6 | 2 | 115000 | 15000 | 12000
Phase 14 — CRM Extensions | 3 | 2 | 58000 | 10000 | 8000
Phase 15 — QA, Testing & Bug Fixes | 15 | 2 | 288000 | 0 | 15000
Phase 16 — Deployment & Go-Live Setup | 5 | 2 | 96000 | 5000 | 7000
Phase 17 — Business Profile Config | 4 | 1 | 51000 | 5000 | 5000
Phase 18 — UI/UX Polish & Responsive | 6 | 2 | 115000 | 0 | 10000
Phase 19 — Training & Documentation | 5 | 1 | 64000 | 10000 | 5000
Buffer / Contingency (10%) | 0 | 0 | 323100 | 0 | 27900
TOTAL | 156 | 3 | 3535100 | 330000 | 302900

## Resource Cost
Resource Cost Breakdown — Gold ERP Build Team
Monthly salary / Rate × Working days (25 days/month) = Daily rate. Total = Daily Rate × Days on project.
Resource Role | Seniority | Monthly Cost (₹) | Daily Rate (₹) | Days on Project | Total Cost (₹) | Allocation % | Skills Required | Notes
Full-Stack Developer | Senior | 120000 | 4800 | 90 | 432000 | 100% | React, Node.js, TypeScript, PostgreSQL | Lead dev — all JW modules
Full-Stack Developer | Mid | 80000 | 3200 | 90 | 288000 | 100% | React, Express, TanStack Query | Frontend-heavy modules
Full-Stack Developer | Junior | 50000 | 2000 | 70 | 140000 | 78% | React, basic Express | UI components, bug fixes
UI/UX Designer | Mid | 60000 | 2400 | 40 | 96000 | 44% | Figma, Tailwind, responsive design | JW-specific screens, reports
QA Engineer | Mid | 45000 | 1800 | 45 | 81000 | 50% | Manual testing, Playwright | End-to-end test coverage
Project Manager | Senior | 90000 | 3600 | 30 | 108000 | 33% | Agile, Jira, stakeholder mgmt | Planning, client coordination
Domain Expert | Jewellery ERP | 100000 | 4000 | 45 | 180000 | 50% | Gold/Jewellery ERP domain knowledge | Requirements, UAT, training
DevOps / Cloud | Mid | 70000 | 2800 | 15 | 42000 | 17% | Replit Deploy, Neon DB, CI/CD | Deployment, infra setup
TOTAL TEAM COST |  |  |  |  | 1367000
Seniority | Monthly Salary Range (Market Rate — India) |  |  |  | Notes
Junior | ₹30,000 – ₹60,000/month |  |  |  | 0–2 yrs exp, guided work
Mid | ₹60,000 – ₹90,000/month |  |  |  | 2–5 yrs exp, independent
Senior | ₹90,000 – ₹1,50,000/month |  |  |  | 5+ yrs exp, architecture decisions
Domain Expert | ₹80,000 – ₹1,50,000/month (consulting) |  |  |  | Jewellery ERP process knowledge

## Module Detail
Gold ERP — Module-wise Feature Build Plan (137 Features)
Module | Feature / Task | Days | Devs | Phase | Dev Cost (₹) | Domain (₹) | Custom (₹) | Total (₹) | Status
JW Dashboard | Live gold/silver rate widget (API) | 3 | 2 | Ph1 | 57600 | 8000 | 5000 | 70600 | New
JW Dashboard | Business profile switcher + KPI cards | 2 | 2 | Ph1 | 38400 | 7000 | 5000 | 50400 | New
Metal Rates | MCX/IBJA live rate fetch + history | 3 | 2 | Ph1 | 57600 | 8000 | 5000 | 70600 | New
Metal Rates | Manual rate override + alerts | 2 | 1 | Ph1 | 19200 | 5000 | 3000 | 27200 | New
Metal Rates | Metal rate history chart | 2 | 1 | Ph1 | 19200 | 2000 | 2000 | 23200 | New
Items Master | jw_items table + HUID + barcode | 3 | 2 | Ph2 | 57600 | 8000 | 5000 | 70600 | New
Items Master | Item categories (ring/chain/bangle…) | 2 | 1 | Ph2 | 19200 | 5000 | 3000 | 27200 | New
Items Master | Stone details (carat, clarity, color) | 2 | 2 | Ph2 | 38400 | 5000 | 4000 | 47400 | New
Design Library | Design image upload + CAD file store | 3 | 2 | Ph2 | 57600 | 7000 | 4000 | 68600 | New
Design Library | Design linked to production order | 2 | 2 | Ph2 | 38400 | 5000 | 3000 | 46400 | New
Design Library | Design search & filter by category | 2 | 1 | Ph2 | 19200 | 3000 | 2000 | 24200 | New
Estimates | Estimate builder with live gold rate | 4 | 3 | Ph3 | 96000 | 10000 | 8000 | 114000 | New
Estimates | Stone pricing engine (per carat) | 3 | 2 | Ph3 | 57600 | 8000 | 5000 | 70600 | New
Estimates | Making charges (% or fixed) | 2 | 2 | Ph3 | 38400 | 5000 | 4000 | 47400 | New
Estimates | Convert estimate → sales order / invoice | 3 | 2 | Ph3 | 57600 | 7000 | 5000 | 69600 | New
Estimates | Customer approval flow + WhatsApp share | 2 | 2 | Ph3 | 38400 | 5000 | 4000 | 47400 | New
Repairs | Repair intake form (weight, description) | 3 | 2 | Ph4 | 57600 | 8000 | 5000 | 70600 | New
Repairs | Repair stages tracking | 3 | 2 | Ph4 | 57600 | 7000 | 4000 | 68600 | New
Repairs | Repair billing + payment | 2 | 2 | Ph4 | 38400 | 5000 | 3000 | 46400 | New
Repairs | WhatsApp update to customer | 2 | 1 | Ph4 | 19200 | 3000 | 3000 | 25200 | New
Karigar | Karigar master with metal balance | 3 | 2 | Ph5 | 57600 | 8000 | 5000 | 70600 | New
Karigar | Metal issue to karigar | 3 | 2 | Ph5 | 57600 | 8000 | 5000 | 70600 | New
Karigar | Metal receive from karigar + wastage | 2 | 2 | Ph5 | 38400 | 7000 | 4000 | 49400 | New
Karigar | Karigar payment + settlement | 2 | 2 | Ph5 | 38400 | 7000 | 3000 | 48400 | New
Karigar | Karigar ledger + outstanding | 2 | 2 | Ph5 | 38400 | 5000 | 3000 | 46400 | New
Jobwork Orders | Jobwork order creation + karigar assign | 3 | 2 | Ph6 | 57600 | 8000 | 5000 | 70600 | New
Jobwork Orders | Job stages + completion tracking | 2 | 2 | Ph6 | 38400 | 5000 | 4000 | 47400 | New
Jobwork Orders | Job finalization + barcode label | 2 | 2 | Ph6 | 38400 | 7000 | 3000 | 48400 | New
Production | Production order with design + qty | 3 | 3 | Ph7 | 72000 | 10000 | 8000 | 90000 | New
Production | Stage 1: CAD Process | 2 | 2 | Ph7 | 38400 | 5000 | 3000 | 46400 | New
Production | Stage 2: Sketch Process | 1 | 2 | Ph7 | 19200 | 3000 | 2000 | 24200 | New
Production | Stage 3: Ghat (weight in/out) | 2 | 2 | Ph7 | 38400 | 5000 | 3000 | 46400 | New
Production | Stage 4: Casting (weight track) | 2 | 2 | Ph7 | 38400 | 5000 | 3000 | 46400 | New
Production | Stage 5: Tree Setup | 1 | 2 | Ph7 | 19200 | 3000 | 2000 | 24200 | New
Production | Stage 6: CAM Process | 1 | 2 | Ph7 | 19200 | 3000 | 2000 | 24200 | New
Production | Stage 7: Filing & Buffing | 1 | 2 | Ph7 | 19200 | 3000 | 2000 | 24200 | New
Production | Stage 8: Fitting Process | 1 | 2 | Ph7 | 19200 | 3000 | 2000 | 24200 | New
Production | Stage 9: Polish Process | 1 | 2 | Ph7 | 19200 | 3000 | 2000 | 24200 | New
Production | Stage 10: Quality Check (pass/fail) | 2 | 2 | Ph7 | 38400 | 5000 | 3000 | 46400 | New
Production | Stage 11: Refining Process | 2 | 2 | Ph7 | 38400 | 5000 | 3000 | 46400 | New
Production | Stage 12: Job Finalize + Barcode | 2 | 2 | Ph7 | 38400 | 5000 | 3000 | 46400 | New
Production | Stage 13: Settlement | 2 | 2 | Ph7 | 38400 | 5000 | 3000 | 46400 | New
Production | Stage 14: Wastage per stage tracking | 2 | 2 | Ph7 | 38400 | 5000 | 3000 | 46400 | New
Production | Stage 15: Post-production timestamps | 1 | 2 | Ph7 | 19200 | 2000 | 2000 | 23200 | New
Production | Material mgmt: raw material issue to order | 2 | 2 | Ph7 | 38400 | 5000 | 3000 | 46400 | New
Production | Worker material balance tracking | 1 | 2 | Ph7 | 19200 | 3000 | 2000 | 24200 | New
Bullion | Bullion inward (vendor, rate, weight) | 3 | 3 | Ph8 | 72000 | 10000 | 8000 | 90000 | New
Bullion | Bullion invoice & rate cuts | 3 | 2 | Ph8 | 57600 | 8000 | 5000 | 70600 | New
Bullion | Buy/sell/conversion/adjustment log | 3 | 2 | Ph8 | 57600 | 8000 | 5000 | 70600 | New
Bullion | Physical inventory reconciliation | 2 | 2 | Ph8 | 38400 | 5000 | 4000 | 47400 | New
Bullion | Bullion movement tracking report | 2 | 2 | Ph8 | 38400 | 5000 | 3000 | 46400 | New
Chit Schemes | Chit scheme master (duration, amount) | 3 | 2 | Ph9 | 57600 | 8000 | 5000 | 70600 | New
Chit Schemes | Member enrollment + installments | 3 | 2 | Ph9 | 57600 | 8000 | 5000 | 70600 | New
Chit Schemes | Monthly installment tracking | 2 | 2 | Ph9 | 38400 | 5000 | 4000 | 47400 | New
Chit Schemes | Redemption with bonus/discount | 2 | 2 | Ph9 | 38400 | 5000 | 4000 | 47400 | New
Chit Schemes | Chit ledger + outstanding report | 2 | 1 | Ph9 | 19200 | 4000 | 3000 | 26200 | New
Hallmarking | Hallmarking register (BIS/HUID) | 3 | 2 | Ph10 | 57600 | 8000 | 5000 | 70600 | New
Hallmarking | Hallmarking status on item master | 2 | 2 | Ph10 | 38400 | 5000 | 3000 | 46400 | New
Customer Buyback | Buyback transaction form | 2 | 2 | Ph11 | 38400 | 5000 | 4000 | 47400 | New
Customer Buyback | Old jewellery valuation (weight×rate) | 2 | 2 | Ph11 | 38400 | 5000 | 4000 | 47400 | New
JW Analytics | Sales by category/karigar/design | 3 | 2 | Ph12 | 57600 | 7000 | 5000 | 69600 | New
JW Analytics | Metal movement analytics | 2 | 2 | Ph12 | 38400 | 5000 | 4000 | 47400 | New
JW Analytics | Production efficiency report | 2 | 2 | Ph12 | 38400 | 5000 | 4000 | 47400 | New
JW Analytics | Karigar performance dashboard | 2 | 1 | Ph12 | 19200 | 3000 | 3000 | 25200 | New
JW Analytics | MIS export (Excel/PDF) | 2 | 1 | Ph12 | 19200 | 3000 | 2000 | 24200 | New
HRMS Karigar | Karigar as employee type | 2 | 2 | Ph13 | 38400 | 5000 | 3000 | 46400 | New
HRMS Karigar | Karigar payslip with metal settlement | 3 | 2 | Ph13 | 57600 | 8000 | 5000 | 70600 | New
HRMS Karigar | Karigar attendance (home/workshop) | 2 | 1 | Ph13 | 19200 | 3000 | 3000 | 25200 | New
CRM Extension | Quotation → estimate link in CRM | 2 | 2 | Ph14 | 38400 | 5000 | 4000 | 47400 | New
CRM Extension | Feedback & survey module (basic) | 2 | 1 | Ph14 | 19200 | 5000 | 4000 | 28200 | New
QA & Testing | E2E Playwright test suite | 8 | 2 | Ph15 | 115200 | 0 | 8000 | 123200 | QA
QA & Testing | User acceptance testing (UAT) | 5 | 2 | Ph15 | 72000 | 0 | 5000 | 77000 | QA
QA & Testing | Performance + load testing | 3 | 1 | Ph15 | 28800 | 0 | 3000 | 31800 | QA
QA & Testing | Security & data isolation testing | 2 | 1 | Ph15 | 19200 | 0 | 2000 | 21200 | QA
QA & Testing | Bug fixes from QA | 5 | 2 | Ph15 | 72000 | 0 | 5000 | 77000 | QA
Deployment | Replit production deployment setup | 2 | 2 | Ph16 | 38400 | 0 | 3000 | 41400 | DevOps
Deployment | Neon DB schema migration scripts | 2 | 1 | Ph16 | 19200 | 0 | 2000 | 21200 | DevOps
Deployment | Domain + SSL + CORS setup | 1 | 1 | Ph16 | 9600 | 0 | 2000 | 11600 | DevOps
Deployment | WhatsApp & Razorpay production keys | 1 | 1 | Ph16 | 9600 | 5000 | 2000 | 16600 | DevOps
Business Profiles | Single Store profile config | 1 | 1 | Ph17 | 12800 | 1000 | 1000 | 14800 | Config
Business Profiles | Wholesaler profile config | 1 | 1 | Ph17 | 12800 | 1000 | 1000 | 14800 | Config
Business Profiles | Multi Chain profile config | 1 | 1 | Ph17 | 12800 | 2000 | 2000 | 16800 | Config
Business Profiles | Manufacturer profile config | 1 | 1 | Ph17 | 12800 | 2000 | 2000 | 16800 | Config
UI/UX Polish | Mobile responsive JW screens | 3 | 2 | Ph18 | 57600 | 0 | 5000 | 62600 | Design
UI/UX Polish | Print-friendly estimate PDF layout | 2 | 2 | Ph18 | 38400 | 0 | 3000 | 41400 | Design
UI/UX Polish | Barcode label print template | 1 | 1 | Ph18 | 9600 | 0 | 2000 | 11600 | Design
Training | Admin user training (2 sessions) | 2 | 1 | Ph19 | 25600 | 5000 | 0 | 30600 | Training
Training | Operations user training | 2 | 1 | Ph19 | 25600 | 5000 | 0 | 30600 | Training
Training | User manual documentation | 3 | 1 | Ph19 | 38400 | 5000 | 5000 | 48400 | Training
Buffer | Contingency 10% | 0 | 0 | Buf | 323100 | 0 | 27900 | 351000 | Buffer
TOTAL |  | 200 |  |  | 3766300 | 418000 | 344900 | 4529200

## Infrastructure Cost
Infrastructure, Replit & Third-Party Cost (Build Phase + First Year)
Item | Type | One-Time (₹) | Monthly (₹) | Annual (₹) | Notes
Replit Core (Build Phase) | Replit | 0 | 2900 | 34800 | Replit Core plan for dev team — $35/mo × 12
Replit Deployments | Replit | 0 | 2500 | 30000 | Production deploy hosting — $30/mo est.
Neon PostgreSQL DB | Database | 0 | 0 | 0 | Free tier covers dev; paid at scale
Domain Name (.com) | Domain | 1200 | 0 | 1200 | GoDaddy/Namecheap — ₹1,200/yr
SSL Certificate | Domain | 0 | 0 | 0 | Free via Let's Encrypt on Replit
WhatsApp Cloud API (Meta) | Integration | 0 | 3000 | 36000 | ~₹3,000/mo for business messages
Razorpay Payment Gateway | Integration | 0 | 0 | 0 | 2% per transaction — no monthly fee
MCX/IBJA Gold Rate API | Integration | 0 | 2000 | 24000 | ₹2,000/mo for live rate feed
SendGrid Email | Integration | 0 | 820 | 9840 | Starter plan ~$10/mo
Barcode Label Printer Setup | Hardware | 8000 | 0 | 0 | One-time — Zebra/TSC label printer
RFID Reader (optional) | Hardware | 15000 | 0 | 0 | Optional for RFID tag tracking
Logo & Branding (Gold ERP) | Design | 5000 | 0 | 0 | Custom logo for Jewel ERP branding
SSL EV Certificate (optional) | Security | 8000 | 0 | 8000 | Extended validation — for banks/govt clients
Backup Storage (S3/Cloudflare) | Infra | 0 | 820 | 9840 | $10/mo cloud backup
Staging Environment | Replit | 0 | 1640 | 19680 | $20/mo second Replit environment for testing
Security Audit / Pen Test | Security | 25000 | 0 | 25000 | One-time before go-live
Legal: SaaS T&C / Privacy Policy | Legal | 15000 | 0 | 0 | Lawyer review of SaaS agreements
TOTAL INFRASTRUCTURE |  | 77200 | 13680 | 198360

## Customization & Domain
Customization Cost & Domain Expertise Cost Breakdown
DOMAIN EXPERTISE COST
Activity | Days | Rate/Day (₹) | Total (₹) | Who Provides This
Gold ERP requirements gathering | 5 | 4000 | 20000 | Domain Expert + PM
Jewellery process mapping (15 prod stages) | 3 | 4000 | 12000 | Domain Expert
Karigar workflow design | 3 | 4000 | 12000 | Domain Expert
Bullion trading rules & compliance | 2 | 4000 | 8000 | Domain Expert + CA
BIS/HUID hallmarking requirements | 2 | 4000 | 8000 | Domain Expert
Chit scheme rules & structure | 2 | 4000 | 8000 | Domain Expert
Metal rate API evaluation & selection | 2 | 3000 | 6000 | Domain Expert + Dev
UAT — User Acceptance Testing | 5 | 4000 | 20000 | Domain Expert + End Users
Training — Admin users (2 sessions) | 2 | 3000 | 6000 | Domain Expert
Training — Operations users | 2 | 3000 | 6000 | Domain Expert
Go-live support (first 2 weeks) | 5 | 4000 | 20000 | Domain Expert + Dev
Business profile customisation review | 3 | 4000 | 12000 | Domain Expert
Documentation review & sign-off | 2 | 3000 | 6000 | Domain Expert
Post-launch consultation (quarterly) | 4 | 4000 | 16000 | Domain Expert
TOTAL DOMAIN COST | 1900-02-10 |  | 160000
CUSTOMIZATION COST
Customization Item | Category | Complexity | Cost (₹) | Notes
Business profile-wise module gating | Config | Medium | 15000 | 4 profiles × different module sets
Live gold rate integration (MCX/IBJA) | Integration | High | 25000 | Real-time API + fallback mechanism
Jewellery estimate PDF template | Reports | Medium | 12000 | Custom branded estimate printout
Barcode / RFID label print template | Reports | Medium | 10000 | Zebra-compatible label format
Production stage UI (15 stages) | UI | High | 30000 | Custom stage pipeline visual
Karigar metal balance dashboard | UI | Medium | 12000 | Real-time metal in/out tracker
Bullion rate cut calculator | Finance | High | 20000 | Rate cut logic per client config
Chit scheme redemption rules engine | Finance | High | 18000 | Configurable bonus/discount rules
HUID/BIS hallmarking number format | Compliance | Low | 8000 | Govt format validation
Customer buyback valuation formula | Finance | Medium | 12000 | Weight × current rate + making
WhatsApp estimate share template | Integration | Low | 6000 | Custom WA message with PDF link
Multi-currency for export orders | Finance | Medium | 15000 | USD/AED invoice generation
GST on jewellery (3% + making 5%) | Compliance | Medium | 10000 | Correct GST rate mapping
Stock reconciliation report | Reports | Medium | 8000 | Item-wise stock vs books reconciliation
MIS dashboard custom widgets | Analytics | Medium | 10000 | JW-specific analytics cards
Role-based access per business profile | Security | Medium | 12000 | Manufacturer vs Retailer role sets
On-premise license key validator | Security | High | 20000 | Encrypted key check at server start
Custom branding (logo, colors) | Design | Low | 8000 | White-label theming per client
TOTAL CUSTOMIZATION COST |  |  | 251000

## Total Cost Summary
GRAND TOTAL — Gold ERP Build Cost Summary
All amounts in Indian Rupees (₹) · Timeline: ~120 Working Days (~6 Months)
Cost Component | Amount (₹) | % of Total | Timeline | Notes
Development Cost | 3554100 | 77.07% | 120 days | Dev team salary × days
Domain Expert Cost | 180000 | 3.903% | 45 days | Jewellery ERP consultant
Customization Cost | 251000 | 5.443% | Throughout | JW-specific custom features
Infrastructure (Build) | 77200 | 1.674% | Build phase | Replit, APIs, domain, backup
Infrastructure (Yr 1) | 132600 | 2.875% | Year 1 | Annual running cost
Security Audit | 25000 | 0.5421% | Pre-launch | One-time pen test
Legal (T&C / Privacy) | 15000 | 0.3253% | Month 1 | SaaS agreement review
Training & Docs | 25600 | 0.5551% | Go-live | User training + manual
Buffer / Contingency | 350900 | 7.609% | Throughout | 10% buffer on dev+custom
GRAND TOTAL | 4611400 | 100%
PAYBACK / ROI ANALYSIS
SaaS Vertical (Gold ERP) @ ₹5,999/mo | Customers to break even | 64 customers × 12 months
On-Premise (Manufacturer) @ ₹3,00,000 | Licenses to break even | 15 licenses
On-Premise (Single Store) @ ₹75,000 | Licenses to break even | 61 licenses
Monthly SaaS Revenue at 50 customers | Revenue/mo @ Growth avg ₹5,000 | ₹2,50,000/mo = ₹30,00,000/yr
Payback period (50 SaaS customers) | Months to recover build cost | ~18 months