## Overview
KINTO SMART OPS — MULTITENANCY & SAAS PLAN
Final Implementation Blueprint ¦ April 2026
WHAT IS BEING BUILT
The existing Kinto Smart Ops system will be converted into a full SaaS platform where multiple manufacturing companies can use the same software independently, each with their own isolated data, users, files, and billing.
Architecture: Shared database with tenant_id isolation — the simplest, most maintainable approach for the existing codebase.
Every existing table gets a tenant_id column. All current data is automatically assigned to Tenant 1 (KINTO). Zero data loss.
Deployment: Replit (no AWS/GCP required). Publish once, accessible globally via custom domain with HTTPS.
10 KEY PRINCIPLES
# | Principle | Detail
1 | Zero data loss | Existing data stamped with tenant_id=1. No records touched.
2 | Same login UX | Credentials unchanged. Two-step picker only shown if user is in 2+ companies.
3 | Auto isolation | Every API query auto-filtered by tenant from session. No manual passing.
4 | File isolation | Uploads stored in /uploads/{tenantId}/ — cross-tenant access blocked at route level.
5 | License enforcement | User limits, module access, storage quota all enforced in middleware.
6 | Grace period | 7-day read-only grace after expiry. Data kept 90 days after suspension.
7 | Per-tenant WhatsApp | Each tenant can have own WhatsApp Business number or share Kinto's.
8 | Branded exports | Excel/PDF exports show tenant's company name, logo, GSTIN.
9 | Super Admin | Kinto staff panel to manage all tenants, impersonate, view MRR.
10 | SaaS-ready | Signup → wizard → trial → Razorpay subscription. Full self-service.

## Database Plan
DATABASE MIGRATION PLAN
New Tables + Column Additions to All Existing Tables
NEW TABLES
# | Table Name | Columns / Purpose
1 | tenants | id, name, slug, gstin, address, logo_path, status (active/trial/suspended), trial_expires_at, created_at
2 | license_plans | id, name, price_monthly_paise, user_limit, storage_gb, has_whatsapp, has_production, has_mis, has_accounting
3 | tenant_subscriptions | id, tenant_id, plan_id, billing_cycle (monthly/annual), start_date, end_date, status, user_limit_override
4 | tenant_users | id, tenant_id, user_id, role, is_admin, joined_at, status
5 | tenant_billing_invoices | id, tenant_id, period_month, amount_paise, gst_paise, status (draft/sent/paid/overdue), due_date, paid_at
6 | tenant_billing_payments | id, invoice_id, amount_paise, payment_mode, razorpay_reference, paid_at
MIGRATION: tenant_id ADDED TO ALL EXISTING TABLES
SQL applied to every table: ALTER TABLE <table> ADD COLUMN IF NOT EXISTS tenant_id INTEGER NOT NULL DEFAULT 1
# | Table | # | Table | # | Table | #
1 | users | 2 | customers | 3 | vendors
4 | invoices | 5 | invoice_items | 6 | payments
7 | gatepasses | 8 | purchase_orders | 9 | raw_materials
10 | products | 11 | product_categories | 12 | bom
13 | bom_items | 14 | production_entries | 15 | inventory_batches
16 | expenses | 17 | expense_categories | 18 | monthly_expenses
19 | documents | 20 | sales_orders | 21 | sales_order_items
22 | journal_entries | 23 | journal_lines | 24 | chart_of_accounts
25 | account_types | 26 | machines | 27 | checklists
28 | checklist_items | 29 | roles | 30 | permissions
31 | role_permissions | 32 | dispatch_tracking | 33 | credit_notes
34 | debit_notes | 35 | advances | 36 | sales_returns
37 | scrap_entries | 38 | cash_register | 39 | mis_snapshots
DEFAULT TENANT (inserted before migration runs)
id=1 ¦ name="KINTO Operations" ¦ slug="kinto" ¦ status="active" ¦ All existing users → tenant_id=1 ¦ All existing data → tenant_id=1

## Auth & Session
AUTHENTICATION & SESSION DESIGN
Two-Step Login ¦ Multi-Company Support ¦ Session Structure
TWO-STEP LOGIN FLOW
# | Step | Detail
| Step 1 | User enters username/email + password (exactly like today — no change to login form)
| Step 2 | System checks: find all tenants where these credentials are valid
| Result A | 1 tenant found → login directly, no extra screen shown
| Result B | 2+ tenants found → show "Select Your Company" picker screen
| Result C | 0 matches → show "Invalid credentials" (unchanged)
| After login | Session stores: userId, tenantId, role, tenantSlug, tenantName, planFlags
SESSION OBJECT (after login)
# | Session Key | Example Value | Description
| userId | 42 | User's database ID
| tenantId | 1 | Which company this session belongs to
| role | "manager" | Their role in THIS tenant (can differ per tenant)
| tenantSlug | "kinto" | Short code for the tenant
| tenantName | "KINTO Operations" | Display name
| planFlags.hasWhatsapp | true/false | Whether tenant's plan includes WhatsApp module
| planFlags.hasProduction | true/false | Whether tenant's plan includes BOM / Production
| planFlags.hasMis | true/false | Whether tenant's plan includes MIS Analytics
| planFlags.hasAccounting | true/false | Whether tenant's plan includes Accounting
MULTI-COMPANY SUPPORT
# | Feature | Detail
| Same user, different tenants | john can be admin at KINTO and viewer at ABC Mfg — different roles per tenant
| Company switcher | Header shows company name with dropdown to switch tenant (no re-login needed)
| Session update on switch | tenantId, role, planFlags updated in session when user switches company
| Super Admin | isSuperAdmin=true flag — bypasses all tenant filters, sees all data

## Licensing Plans
LICENSING & PLAN STRUCTURE
Subscription Tiers ¦ Enforcement Points ¦ Grace Period Policy
SUBSCRIPTION PLANS
Feature | Starter | Professional | Enterprise | Notes
Monthly Price | ₹999/mo | ₹2,499/mo | Custom | 2 months free on annual plan
Users included | 3 users | 10 users | Unlimited | Extra user: ₹199/user/mo (Starter), ₹149 (Pro)
File Storage | 5 GB | 25 GB | Unlimited | Enforced at upload time
Invoicing & GST | Yes | Yes | Yes | Core module — always included
Accounting / Ledger | Yes | Yes | Yes | Core module — always included
Sales Orders | Yes | Yes | Yes | Core module — always included
Purchase Orders | Yes | Yes | Yes | Core module — always included
WhatsApp Integration | No | Yes | Yes | Checklist reminders via WhatsApp
BOM / Production | No | Yes | Yes | Bill of Materials, production tracking
MIS Analytics | No | No | Yes | Executive dashboard, KPI reports
Document Management | No | Yes | Yes | Contracts, certificates, expiry alerts
API Access | No | No | Yes | REST API for external integrations
Custom Domain | No | Yes | Yes | company.kintoops.com
Priority Support | Email only | Email + Phone | Dedicated
Free Trial | 14 days | 14 days | 30 days | Full Professional access during trial
ENFORCEMENT POINTS
Limit | Where Enforced | What Happens to User
| User limit exceeded | 400 error: "User limit reached. Upgrade your plan."
| Module not in plan | 403 error: "This feature requires Professional plan or above."
| Storage quota reached | 400 error: "Storage limit reached. Please upgrade."
| Subscription expired | 402 error: "Subscription expired. Please renew to continue."
| In grace period (Day 1-7) | Read-only mode: can view, cannot create/edit/delete
| Trial ended | 402 error: "Trial ended. Please choose a plan to continue."
| Account suspended | Login blocked. Data preserved. Contact admin to reactivate.
GRACE PERIOD POLICY
Timeline | Event | Action / User Impact
| Day 0 | Grace period begins. Read-only mode.
| Day 1–7 | User can view all data but cannot create new records. Reminder emails sent.
| Day 8 | Account suspended. Login blocked. Data fully preserved.
| Day 8–90 | Data retained. Reactivate anytime by renewing subscription.
| Day 91 | Email sent: "Your data will be deleted in 30 days."
| Day 120 | All tenant data permanently deleted from database and file storage.

## Implementation Phases
IMPLEMENTATION PHASES
Phased Build Plan ¦ Scope ¦ Effort ¦ Timeline
Phase | Name | Scope / Key Work Items | Days | Cumul. | Priority | Status
1 | DB Foundation | New tables (tenants, subscriptions, plans, billing). Add tenant_id to all 39 existing tables with DEFAULT 1. Insert default tenant (KINTO). Link all existing users to tenant 1. | 3 | 3 | Critical | Pending
2 | Auth & Session | Two-step login flow. Tenant resolution on login. tenantId stored in session. Company switcher in header. Super admin flag. | 3 | 6 | Critical | Pending
3 | API Middleware | Tenant injection middleware. All 200+ routes auto-filtered by tenantId. Subscription check. Module gate. Super admin bypass. | 4 | 10 | Critical | Pending
4 | File Upload Scoping | Restructure /uploads/{tenantId}/ folders. Migrate existing files to /uploads/1/. All upload routes prefix with tenantId. Storage quota check. | 2 | 12 | High | Pending
5 | License Engine | Plans table seeded. User limit enforcement on user create. Module access flags checked in middleware. Storage quota enforced at upload. | 3 | 15 | High | Pending
6 | Tenant Admin Portal | Settings section for tenant admin: company profile, logo upload, user management, subscription view, billing invoices. | 4 | 19 | High | Pending
7 | Super Admin Panel | All tenants list, create/suspend/reactivate, plan override, impersonation (audit-logged), billing overview, MRR dashboard. | 4 | 23 | High | Pending
8 | Billing Engine | Razorpay integration. Monthly auto-invoice generation (cron). Payment webhook. Receipt emails. Failed payment reminders. Grace period cron. | 5 | 28 | Medium | Pending
9 | WhatsApp & Email per Tenant | Per-tenant WhatsApp credentials in settings. Webhook routes by phone_number_id to correct tenant. Branded emails (company name, logo, reply-to). | 3 | 31 | Medium | Pending
10 | Reports & Exports | Tenant company name + logo + GSTIN in all Excel/PDF exports. Super admin cross-tenant reports (MRR, usage, expiring). | 2 | 33 | Medium | Pending
11 | Testing & Hardening | Cross-tenant data leak tests. Module enforcement tests. Billing flow tests. Load testing. Security audit. UAT with KINTO. | 3 | 36 | Critical | Pending
TOTAL ESTIMATED EFFORT: ~33–36 working days ¦ ~7–8 weeks
WHAT STAYS EXACTLY THE SAME (ZERO CHANGES)
All existing features: invoices, BOM, production, MIS, accounting, gatepasses, sales orders, purchase orders, checklists, documents, expenses
All existing user credentials and passwords — users log in exactly the same way
All existing data — auto-assigned to Tenant 1 with zero manual work
The entire UI, navigation, and page structure
All existing reports, Excel exports, and print layouts (tenant branding is additive, not replacing)

## SaaS & Deployment
SAAS PRODUCT & DEPLOYMENT
Publishing on Replit ¦ Cloud Options ¦ SaaS Business Model
DEPLOYMENT STAGES
Stage | Platform | Why | Monthly Cost (est.)
Launch → First 50 tenants | Replit Deployments | Zero DevOps. Click Publish. Auto-SSL. Custom domain. Focus on product not infrastructure. | ₹2,000–4,000/mo
50–500 tenants | AWS EC2 + RDS (Mumbai region) | More control. Indian data residency. Cost-effective at scale. | ₹8,000–20,000/mo
500+ tenants | AWS/GCP with Docker + Kubernetes | Full scalability. Load balancing. Auto-scaling. Multi-region. | Custom
WHAT REPLIT DEPLOYMENT GIVES YOU
Feature | Detail
yourapp.replit.app — accessible anywhere in the world instantly
Point kintoops.com or app.kintoops.com to your deployment
Included, no setup, auto-renews
Runs even when browser is closed
Zero downtime from application errors
All API keys (Razorpay, WhatsApp, SendGrid) stay secure
No EC2, no Docker, no Linux, no DevOps needed
SAAS BUSINESS MODEL
Item | Detail
= SaaS Vendor. Your company uses the system for free as Tenant 1.
= Manufacturing companies paying monthly subscriptions.
MRR (Monthly Recurring Revenue) from all active tenants.
Customers sign up, complete wizard, start 14-day trial, choose plan, pay via Razorpay.
Starter → Professional → Enterprise as companies grow.
Razorpay supports UPI, NEFT, credit/debit cards — best for Indian B2B.
Offer 2 months free on annual plan to encourage commitment.
50 tenants or 500 tenants — same codebase, same Replit deployment until you need more.

## Integrations Impact
INTEGRATIONS & SERVICES IMPACT
WhatsApp ¦ Email ¦ Files ¦ Reports ¦ API
WHATSAPP INTEGRATION
Aspect | Current | After Multitenancy
| Credentials | Low
| Incoming webhook | Medium
| Outgoing reminders | Low
| Checklist completion | Low
EMAIL NOTIFICATIONS
Setting | Current | After Multitenancy
| Sender name | Low
| Reply-to | Low
| Email logo | Low
| Machine reminders | None
| Document expiry alerts | None
| Subscription reminders | Medium
FILE UPLOADS & DOCUMENTS
Aspect | Current | After Multitenancy
| Folder structure | Low
| Access control | Low
| Existing files | Low
| Storage quota | Medium
| Cross-tenant access | Low
REPORTS & EXCEL EXPORTS
Report | Change | After Multitenancy
| All operational reports | None
| Excel exports | Low
| PDF invoices / gatepasses | Low
| MIS Dashboard | None
| Trial Balance / P&L / Balance Sheet | None
| Super Admin MRR report | Medium

## Customization Pricing
CUSTOMIZATION PRICING
Fixed Price Model ¦ One Clear Rate ¦ No Hourly Billing
RULE: All customizations are Fixed Price only. Quote upfront. Customer approves before work starts. No hourly billing. No ambiguity.
CUSTOMIZATION PRICE LIST
Customization Type | Min Price | Max Price | What It Includes
Custom Report | ₹5,000 | ₹15,000 | New Excel or PDF report specific to one customer — layout, data, columns as per their requirement
Custom Fields in a Module | ₹3,000 | ₹8,000 | Additional fields not in standard forms — invoices, production, checklist, etc.
Custom Workflow / Approval Flow | ₹10,000 | ₹30,000 | Different approval stages, state changes, rules or conditions specific to one customer
API / Tally / ERP Integration | ₹15,000 | ₹50,000 | Connect Kinto with customer's existing Tally, ERP, or third-party software via API
WhatsApp Custom Flow | ₹8,000 | ₹20,000 | Custom bot messages, custom checklist templates, custom reminder logic for WhatsApp
Custom MIS Dashboard | ₹10,000 | ₹25,000 | New MIS widgets, KPIs, charts or analytics screens specific to customer's operations
Data Migration (Historical Import) | ₹5,000 | ₹20,000 | Import customer's historical data from Excel, Tally, or other software into Kinto
Training Session | ₹3,000 | ₹8,000 | Per session — on-site or remote training for customer's team (per session rate)
Priority Support SLA (Monthly) | ₹2,000/mo | ₹5,000/mo | Guaranteed response time add-on (e.g. 4-hour response). Billed monthly on top of subscription.
THE PROCESS — HOW EVERY CUSTOMIZATION WORKS
Step | Action | Who Does It
| 1 | Customer
| 2 | Kinto team
| 3 | Kinto team
| 4 | Customer
| 5 | Kinto team
| 6 | Both
| 7 | Kinto team
WHAT IS INCLUDED IN SUBSCRIPTION (NO EXTRA CHARGE)
Standard features available to all tenants on their plan
Bug fixes and error corrections in existing functionality
New platform features released by Kinto to all tenants (everyone gets them automatically)
Configuration within the app — roles, permissions, categories, expense types, chart of accounts, etc.
Email and WhatsApp support for how-to questions within standard usage
KEY RULE: STANDARD vs CUSTOM
If a customization built for one customer is useful to all customers → add it to the standard platform (free for everyone, grows the product). If it is specific only to that one customer → charge separately and maintain it as their private feature.